## Progress Summary
[5 empty] | 28 | 28 | 28 | 28 |  |  |  |  | 29 | 29 | 29 | 29
Cut_Off Date
2026-08-28
Table 8: Work Package 1B EPCI Jacket & Pile DDE Progress by Platform
|  |  | Descriptions | % WT | Last Week Cumulative (%) |  |  |  | This Week Period (%) |  |  |  | Cumulative up to this week (%)
[5 empty] | Plan [A] | Forecast [B] | Actual [C] | Var. [C-A] | Plan [A] | Forecast [B] | Actual [C] | Var. [C-A] | Plan [A] | Forecast [B] | Actual [C] | Var. [C-A]
7 | 8 | 9 | ZWP-21 | 25% | 69.4% | 69.4% | 68.54% | -0.8604% | 1.848% | 1.848% | 2.238% | 0.3904% | 71.24% | 71.24% | 70.77% | -0.47%
14 | 15 | 16 | ZWP-23 | 25% | 58.98% | 58.98% | 59.64% | 0.6612% | 2.516% | 2.516% | 1.344% | -1.171% | 61.49% | 61.49% | 60.98% | -0.51%
21 | 22 | 23 | ZWP-22 | 25% | 46.97% | 46.97% | 48.42% | 1.448% | 3.713% | 3.713% | 3.919% | 0.2056% | 50.68% | 50.68% | 52.34% | 1.654%
28 | 29 | 30 | ZWP-20 | 25% | 30.38% | 30.38% | 37.87% | 7.482% | 3.622% | 3.622% | 4.633% | 1.011% | 34.01% | 34.01% | 42.5% | 8.494%
|  |  | Overall Jacket & Pile DDE Progress | 100% | 51.43% | 51.43% | 53.61% | 2.183% | 2.925% | 2.925% | 3.034% | 0.109% | 54.36% | 54.36% | 56.65% | 2.292%
Click Here to Change the cut_off

## Cut_Off (hidden)
2026-03-20 | Overall DDE Jacket | 35
2026-03-27 | ZWP-23 Jacket | 14
2026-04-03 | ZWP-20 Jacket | 28
2026-04-10 | ZWP-21 Jacket | 7
2026-04-17 | ZWP-22 Jacket | 21
2026-04-24
2026-05-01
2026-05-08
2026-05-15
2026-05-22
2026-05-29
2026-06-05
2026-06-12
2026-06-19
2026-06-26
2026-07-03
2026-07-10
2026-07-17
2026-07-24
2026-07-31
2026-08-07
2026-08-14
2026-08-21
2026-08-28
2026-09-04
2026-09-11
2026-09-18
2026-09-25
2026-10-02
2026-10-09
2026-10-16
2026-10-23
2026-10-30
2026-11-06
2026-11-13
2026-11-20
2026-11-27
2026-12-04
2026-12-11
2026-12-18
2026-12-25
2027-01-01
2027-01-08
2027-01-15
2027-01-22
2027-01-29
2027-02-05
2027-02-12
2027-02-19
2027-02-26
2027-03-05
2027-03-12
2027-03-19
2027-03-26
2027-04-02
2027-04-09
2027-04-16
2027-04-23
2027-04-30
2027-05-07
2027-05-14
2027-05-21
2027-05-28
2027-06-04
2027-06-11
2027-06-18
2027-06-25
2027-07-02
2027-07-09
2027-07-16
2027-07-23
2027-07-30
2027-08-06
2027-08-13
2027-08-20
2027-08-27
2027-09-03
2027-09-10
2027-09-17
2027-09-24
2027-10-01
2027-10-08
2027-10-15
2027-10-22
2027-10-29
2027-11-05
2027-11-12
2027-11-19
2027-11-26
2027-12-03
2027-12-10
2027-12-17
2027-12-24
2027-12-31
2028-01-07
2028-01-14
2028-01-21
2028-01-28
2028-02-04
2028-02-11
2028-02-18
2028-02-25
2028-03-03

## Progress%
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98
2 |  |  | Cut_Off
3 |  |  | 2026-08-28
4
5 | Scope | Total WF | WF% | Jacket & Pile ZWP-21
6 | time axis 2026-03-20 to 2027-12-24
7 | ZWP-21 | 25 | 25% | Plan | 0% | 0% | 4% | 5.8% | 6.6% | 7.6% | 9.8% | 14.75% | 19.55% | 23.03% | 25.82% | 29.45% | 34.11% | 40.66% | 43.57% | 47.34% | 49.69% | 51.6% | 56.38% | 59.29% | 62.53% | 65.82% | 69.4% | 71.24% | 75.03% | 77.33% | 80.09% | 82.2% | 83.36% | 85.32% | 86.04% | 86.04% | 87.4% | 87.4% | 88.36% | 88.76% | 89.4% | 89.4% | 89.4% | 89.4% | 89.4% | 89.6% | 89.6% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90%
8 | ZWP-21 | 25 | 25% | Forecast | 0% | 0% | 4% | 5.8% | 6.6% | 7.6% | 9.8% | 14.75% | 19.55% | 23.03% | 25.82% | 29.45% | 34.11% | 40.66% | 43.57% | 47.34% | 49.69% | 51.6% | 56.38% | 59.29% | 62.53% | 65.82% | 69.4% | 71.24% | 75.03% | 77.33% | 80.09% | 82.2% | 83.36% | 85.32% | 86.04% | 86.04% | 87.4% | 87.4% | 88.36% | 88.76% | 89.4% | 89.4% | 89.4% | 89.4% | 89.4% | 89.6% | 89.6% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90%
9 | ZWP-21 | 25 | 25% | Actual | 0% | 0% | 2.8% | 4.8% | 4.8% | 8.466% | 14.01% | 15.21% | 16.68% | 21.62% | 24.2% | 29.03% | 30.38% | 37.8% | 41.07% | 46.27% | 49.27% | 53.6% | 56.44% | 59.58% | 62.78% | 66.23% | 68.54% | 70.77% | 70.77% | 70.81% | 70.81% | 70.89% | 70.89% | 70.89% | 70.89% | 70.89% | 70.89% | 70.89% | 70.89% | 70.89% | 70.89% | 70.89% | 70.89% | 70.89% | 70.89% | 70.89% | 70.89% | 70.89% | 70.89% | 70.89% | 70.89% | 70.89% | 70.89% | 70.89% | 70.89% | 70.89% | 70.89% | 70.89% | 70.89% | 70.89% | 70.89% | 70.89% | 70.89% | 70.89% | 70.89% | 70.89% | 70.89% | 70.89% | 70.89% | 70.89% | 70.89% | 70.89% | 70.89% | 70.89% | 70.89% | 70.89% | 70.89% | 70.89% | 70.89% | 70.89% | 70.89% | 70.89% | 70.89% | 70.89% | 70.89% | 70.89% | 70.89% | 70.89% | 70.89% | 70.89% | 70.89% | 70.89% | 70.89% | 70.89% | 70.89% | 70.89% | 70.89%
10
11
12 | Scope | Total WF | WF% | Jacket & Pile ZWP-23
13 | time axis 2026-03-20 to 2027-12-24
14 | ZWP-23 | 25 | 25% | Plan | 0% | 0% | 2% | 2.8% | 3.6% | 3.6% | 6.8% | 7.8% | 9.8% | 11.12% | 12.44% | 16.89% | 20.67% | 23.83% | 27.18% | 30.97% | 36.11% | 42.03% | 44.82% | 48.43% | 51.89% | 53.58% | 58.98% | 61.49% | 64.31% | 67.6% | 70.7% | 72.44% | 75.93% | 77.83% | 80.79% | 82.5% | 83.56% | 85.52% | 86.04% | 86.04% | 87.4% | 87.4% | 88.36% | 88.76% | 89.4% | 89.4% | 89.4% | 89.4% | 89.4% | 89.6% | 89.6% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90%
15 | ZWP-23 | 25 | 25% | Forecast | 0% | 0% | 2% | 2.8% | 3.6% | 3.6% | 6.8% | 7.8% | 9.8% | 11.12% | 12.44% | 16.89% | 20.67% | 23.83% | 27.18% | 30.97% | 36.11% | 42.03% | 44.82% | 48.43% | 51.89% | 53.58% | 58.98% | 61.49% | 64.31% | 67.6% | 70.7% | 72.44% | 75.93% | 77.83% | 80.79% | 82.5% | 83.56% | 85.52% | 86.04% | 86.04% | 87.4% | 87.4% | 88.36% | 88.76% | 89.4% | 89.4% | 89.4% | 89.4% | 89.4% | 89.6% | 89.6% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90%
16 | ZWP-23 | 25 | 25% | Actual | 0% | 0% | 2.8% | 4.8% | 4.8% | 6.68% | 10.25% | 14.74% | 17.49% | 19.25% | 20.73% | 22.04% | 25.98% | 30.64% | 30.88% | 32.99% | 34.83% | 42.09% | 46.34% | 49.41% | 51.58% | 58.05% | 59.64% | 60.98% | 60.98% | 60.98% | 60.98% | 60.98% | 60.98% | 60.98% | 60.98% | 60.98% | 60.98% | 60.98% | 60.98% | 60.98% | 60.98% | 60.98% | 60.98% | 60.98% | 60.98% | 60.98% | 60.98% | 60.98% | 60.98% | 60.98% | 60.98% | 60.98% | 60.98% | 60.98% | 60.98% | 60.98% | 60.98% | 60.98% | 60.98% | 60.98% | 60.98% | 60.98% | 60.98% | 60.98% | 60.98% | 60.98% | 60.98% | 60.98% | 60.98% | 60.98% | 60.98% | 60.98% | 60.98% | 60.98% | 60.98% | 60.98% | 60.98% | 60.98% | 60.98% | 60.98% | 60.98% | 60.98% | 60.98% | 60.98% | 60.98% | 60.98% | 60.98% | 60.98% | 60.98% | 60.98% | 60.98% | 60.98% | 60.98% | 60.98% | 60.98% | 60.98% | 60.98%
17
18
19 | Scope | Total WF | WF% | Jacket & Pile ZWP-22
20 | time axis 2026-03-20 to 2027-12-24
21 | ZWP-22 | 25 | 25% | Plan | 0% | 0% | 2% | 2.8% | 3.6% | 3.6% | 4.8% | 4.8% | 6.8% | 7.12% | 9.44% | 10.44% | 10.92% | 11.92% | 13.8% | 18.91% | 22.67% | 26.15% | 29.18% | 32.81% | 37.71% | 44.26% | 46.97% | 50.68% | 52.47% | 54.36% | 58.68% | 61.89% | 64.71% | 68.2% | 71.1% | 72.84% | 75.63% | 77.83% | 80.19% | 82.5% | 83.56% | 85.52% | 86.04% | 86.04% | 87.4% | 87.4% | 88.36% | 88.76% | 89.4% | 89.4% | 89.4% | 89.4% | 89.4% | 89.6% | 89.6% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90%
22 | ZWP-22 | 25 | 25% | Forecast | 0% | 0% | 2% | 2.8% | 3.6% | 3.6% | 4.8% | 4.8% | 6.8% | 7.12% | 9.44% | 10.44% | 10.92% | 11.92% | 13.8% | 18.91% | 22.67% | 26.15% | 29.18% | 32.81% | 37.71% | 44.26% | 46.97% | 50.68% | 52.47% | 54.36% | 58.68% | 61.89% | 64.71% | 68.2% | 71.1% | 72.84% | 75.63% | 77.83% | 80.19% | 82.5% | 83.56% | 85.52% | 86.04% | 86.04% | 87.4% | 87.4% | 88.36% | 88.76% | 89.4% | 89.4% | 89.4% | 89.4% | 89.4% | 89.6% | 89.6% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90%
23 | ZWP-22 | 25 | 25% | Actual | 0% | 0% | 2.8% | 2.8% | 2.8% | 6.68% | 10.25% | 11.74% | 12.39% | 17.15% | 18.63% | 21.04% | 21.98% | 24.2% | 24.44% | 26.18% | 26.57% | 26.73% | 31.91% | 34.87% | 37.99% | 43.99% | 48.42% | 52.34% | 52.34% | 52.34% | 52.34% | 52.34% | 52.34% | 52.34% | 52.34% | 52.34% | 52.34% | 52.34% | 52.34% | 52.34% | 52.34% | 52.34% | 52.34% | 52.34% | 52.34% | 52.34% | 52.34% | 52.34% | 52.34% | 52.34% | 52.34% | 52.34% | 52.34% | 52.34% | 52.34% | 52.34% | 52.34% | 52.34% | 52.34% | 52.34% | 52.34% | 52.34% | 52.34% | 52.34% | 52.34% | 52.34% | 52.34% | 52.34% | 52.34% | 52.34% | 52.34% | 52.34% | 52.34% | 52.34% | 52.34% | 52.34% | 52.34% | 52.34% | 52.34% | 52.34% | 52.34% | 52.34% | 52.34% | 52.34% | 52.34% | 52.34% | 52.34% | 52.34% | 52.34% | 52.34% | 52.34% | 52.34% | 52.34% | 52.34% | 52.34% | 52.34% | 52.34%
24
25
26 | Scope | Total WF | WF% | Jacket & Pile ZWP-20
27 | time axis 2026-03-20 to 2027-12-24
28 | ZWP-20 | 25 | 25% | Plan | 0% | 0% | 2% | 2.8% | 3.6% | 3.6% | 4.8% | 4.8% | 6.8% | 7.12% | 7.44% | 7.44% | 7.92% | 7.92% | 10.8% | 11.96% | 12.92% | 14.24% | 15.8% | 20.75% | 24.27% | 27.43% | 30.38% | 34.01% | 39.21% | 44.74% | 46.97% | 50.68% | 52.47% | 54.36% | 59.78% | 61.89% | 65.72% | 68.2% | 71.1% | 72.84% | 75.93% | 77.83% | 80.79% | 82.5% | 83.56% | 85.52% | 86.04% | 86.04% | 87.4% | 87.4% | 88.36% | 88.76% | 89.4% | 89.4% | 89.4% | 89.4% | 89.4% | 89.6% | 89.6% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90%
29 | ZWP-20 | 25 | 25% | Forecast | 0% | 0% | 2% | 2.8% | 3.6% | 3.6% | 4.8% | 4.8% | 6.8% | 7.12% | 7.44% | 7.44% | 7.92% | 7.92% | 10.8% | 11.96% | 12.92% | 14.24% | 15.8% | 20.75% | 24.27% | 27.43% | 30.38% | 34.01% | 39.21% | 44.74% | 46.97% | 50.68% | 52.47% | 54.36% | 59.78% | 61.89% | 65.72% | 68.2% | 71.1% | 72.84% | 75.93% | 77.83% | 80.79% | 82.5% | 83.56% | 85.52% | 86.04% | 86.04% | 87.4% | 87.4% | 88.36% | 88.76% | 89.4% | 89.4% | 89.4% | 89.4% | 89.4% | 89.6% | 89.6% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90%
30 | ZWP-20 | 25 | 25% | Actual | 0% | 0% | 2.8% | 2.8% | 2.8% | 6.68% | 10.25% | 11.74% | 12.39% | 16.15% | 17.63% | 19.94% | 20.88% | 23.96% | 24.2% | 24.93% | 25.25% | 25.41% | 25.73% | 25.89% | 29.71% | 30.98% | 37.87% | 42.5% | 42.5% | 42.5% | 42.5% | 42.5% | 42.5% | 42.5% | 42.5% | 42.5% | 42.5% | 42.5% | 42.5% | 42.5% | 42.5% | 42.5% | 42.5% | 42.5% | 42.5% | 42.5% | 42.5% | 42.5% | 42.5% | 42.5% | 42.5% | 42.5% | 42.5% | 42.5% | 42.5% | 42.5% | 42.5% | 42.5% | 42.5% | 42.5% | 42.5% | 42.5% | 42.5% | 42.5% | 42.5% | 42.5% | 42.5% | 42.5% | 42.5% | 42.5% | 42.5% | 42.5% | 42.5% | 42.5% | 42.5% | 42.5% | 42.5% | 42.5% | 42.5% | 42.5% | 42.5% | 42.5% | 42.5% | 42.5% | 42.5% | 42.5% | 42.5% | 42.5% | 42.5% | 42.5% | 42.5% | 42.5% | 42.5% | 42.5% | 42.5% | 42.5% | 42.5%
31
32
33 | Scope | Total WF | WF% | Jacket & Pile - Overall DDE
34 | time axis 2026-03-20 to 2027-12-24
35 | Overall | 100 | 100% | Plan | 0% | 0% | 2.5% | 3.55% | 4.35% | 4.6% | 6.55% | 8.037% | 10.74% | 12.1% | 13.79% | 16.05% | 18.41% | 21.08% | 23.84% | 27.29% | 30.35% | 33.5% | 36.55% | 40.32% | 44.1% | 47.77% | 51.43% | 54.36% | 57.75% | 61.01% | 64.11% | 66.81% | 69.12% | 71.43% | 74.43% | 75.82% | 78.08% | 79.74% | 81.42% | 82.54% | 84.07% | 85.04% | 86.15% | 86.68% | 87.44% | 87.98% | 88.35% | 88.55% | 89.05% | 89.1% | 89.34% | 89.54% | 89.7% | 89.75% | 89.75% | 89.85% | 89.85% | 89.9% | 89.9% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90%
36 | Overall | 100 | 100% | Forecast | 0% | 0% | 2.5% | 3.55% | 4.35% | 4.6% | 6.55% | 8.037% | 10.74% | 12.1% | 13.79% | 16.05% | 18.41% | 21.08% | 23.84% | 27.29% | 30.35% | 33.5% | 36.55% | 40.32% | 44.1% | 47.77% | 51.43% | 54.36% | 57.75% | 61.01% | 64.11% | 66.81% | 69.12% | 71.43% | 74.43% | 75.82% | 78.08% | 79.74% | 81.42% | 82.54% | 84.07% | 85.04% | 86.15% | 86.68% | 87.44% | 87.98% | 88.35% | 88.55% | 89.05% | 89.1% | 89.34% | 89.54% | 89.7% | 89.75% | 89.75% | 89.85% | 89.85% | 89.9% | 89.9% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90%
37 | Overall | 100 | 100% | Actual | 0% | 0% | 2.8% | 3.8% | 3.8% | 7.127% | 11.19% | 13.35% | 14.74% | 18.54% | 20.3% | 23.01% | 24.81% | 29.15% | 30.15% | 32.59% | 33.98% | 36.96% | 40.1% | 42.44% | 45.51% | 49.81% | 53.61% | 56.65% | 56.65% | 56.66% | 56.66% | 56.68% | 56.68% | 56.68% | 56.68% | 56.68% | 56.68% | 56.68% | 56.68% | 56.68% | 56.68% | 56.68% | 56.68% | 56.68% | 56.68% | 56.68% | 56.68% | 56.68% | 56.68% | 56.68% | 56.68% | 56.68% | 56.68% | 56.68% | 56.68% | 56.68% | 56.68% | 56.68% | 56.68% | 56.68% | 56.68% | 56.68% | 56.68% | 56.68% | 56.68% | 56.68% | 56.68% | 56.68% | 56.68% | 56.68% | 56.68% | 56.68% | 56.68% | 56.68% | 56.68% | 56.68% | 56.68% | 56.68% | 56.68% | 56.68% | 56.68% | 56.68% | 56.68% | 56.68% | 56.68% | 56.68% | 56.68% | 56.68% | 56.68% | 56.68% | 56.68% | 56.68% | 56.68% | 56.68% | 56.68% | 56.68% | 56.68%

## S-Curves
Zawtika 1F
Jacket & Pile Detailed Design
|  |  | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98
Overall DDE Jacket |  | Description | time axis 2026-03-20 to 2027-12-24
35 |  | Cumulative Plan | 0% | 0% | 2.5% | 3.55% | 4.35% | 4.6% | 6.55% | 8.037% | 10.74% | 12.1% | 13.79% | 16.05% | 18.41% | 21.08% | 23.84% | 27.29% | 30.35% | 33.5% | 36.55% | 40.32% | 44.1% | 47.77% | 51.43% | 54.36% | 57.75% | 61.01% | 64.11% | 66.81% | 69.12% | 71.43% | 74.43% | 75.82% | 78.08% | 79.74% | 81.42% | 82.54% | 84.07% | 85.04% | 86.15% | 86.68% | 87.44% | 87.98% | 88.35% | 88.55% | 89.05% | 89.1% | 89.34% | 89.54% | 89.7% | 89.75% | 89.75% | 89.85% | 89.85% | 89.9% | 89.9% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90%
36 |  | Cumulative Forecast | 0% | 0% | 2.5% | 3.55% | 4.35% | 4.6% | 6.55% | 8.037% | 10.74% | 12.1% | 13.79% | 16.05% | 18.41% | 21.08% | 23.84% | 27.29% | 30.35% | 33.5% | 36.55% | 40.32% | 44.1% | 47.77% | 51.43% | 54.36% | 57.75% | 61.01% | 64.11% | 66.81% | 69.12% | 71.43% | 74.43% | 75.82% | 78.08% | 79.74% | 81.42% | 82.54% | 84.07% | 85.04% | 86.15% | 86.68% | 87.44% | 87.98% | 88.35% | 88.55% | 89.05% | 89.1% | 89.34% | 89.54% | 89.7% | 89.75% | 89.75% | 89.85% | 89.85% | 89.9% | 89.9% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90%
37 |  | Cumulative Actual | 2026-03-20: 0%; 2026-03-27: 0%; 2026-04-03: 2.8%; 2026-04-10: 3.8%; 2026-04-17: 3.8%; 2026-04-24: 7.127%; 2026-05-01: 11.19%; 2026-05-08: 13.35%; 2026-05-15: 14.74%; 2026-05-22: 18.54%; 2026-05-29: 20.3%; 2026-06-05: 23.01%; 2026-06-12: 24.81%; 2026-06-19: 29.15%; 2026-06-26: 30.15%; 2026-07-03: 32.59%; 2026-07-10: 33.98%; 2026-07-17: 36.96%; 2026-07-24: 40.1%; 2026-07-31: 42.44%; 2026-08-07: 45.51%; 2026-08-14: 49.81%; 2026-08-21: 53.61%; 2026-08-28: 56.65%
|  | Period Plan (Early) | 0% | 0% | 2.5% | 1.05% | 0.8% | 0.25% | 1.95% | 1.487% | 2.7% | 1.36% | 1.689% | 2.268% | 2.352% | 2.676% | 2.758% | 3.456% | 3.054% | 3.155% | 3.041% | 3.775% | 3.78% | 3.672% | 3.66% | 2.925% | 3.398% | 3.254% | 3.101% | 2.696% | 2.311% | 2.313% | 3% | 1.391% | 2.258% | 1.662% | 1.684% | 1.114% | 1.535% | 0.9664% | 1.11% | 0.5269% | 0.7634% | 0.541% | 0.37% | 0.2% | 0.5% | 0.05% | 0.24% | 0.2% | 0.16% | 0.05% | 0% | 0.1% | 0% | 0.05% | 0% | 0.1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Period Forecast | 0% | 0% | 2.5% | 1.05% | 0.8% | 0.25% | 1.95% | 1.487% | 2.7% | 1.36% | 1.689% | 2.268% | 2.352% | 2.676% | 2.758% | 3.456% | 3.054% | 3.155% | 3.041% | 3.775% | 3.78% | 3.672% | 3.66% | 2.925% | 3.398% | 3.254% | 3.101% | 2.696% | 2.311% | 2.313% | 3% | 1.391% | 2.258% | 1.662% | 1.684% | 1.114% | 1.535% | 0.9664% | 1.11% | 0.5269% | 0.7634% | 0.541% | 0.37% | 0.2% | 0.5% | 0.05% | 0.24% | 0.2% | 0.16% | 0.05% | 0% | 0.1% | 0% | 0.05% | 0% | 0.1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Remaining Units | Period Actual | 2026-03-20: 0%; 2026-03-27: 0%; 2026-04-03: 2.8%; 2026-04-10: 1%; 2026-04-17: 0%; 2026-04-24: 3.327%; 2026-05-01: 4.065%; 2026-05-08: 2.161%; 2026-05-15: 1.386%; 2026-05-22: 3.801%; 2026-05-29: 1.755%; 2026-06-05: 2.72%; 2026-06-12: 1.793%; 2026-06-19: 4.34%; 2026-06-26: 0.9996%; 2026-07-03: 2.447%; 2026-07-10: 1.388%; 2026-07-17: 2.978%; 2026-07-24: 3.145%; 2026-07-31: 2.334%; 2026-08-07: 3.076%; 2026-08-14: 4.296%; 2026-08-21: 3.804%; 2026-08-28: 3.034%

## EDSR
Cut-off Date |  | 2026-08-28
EDSR - JACKET & PILES | [8 empty] | IFR (50%) |  |  | IFA (20%) |  |  | AFC Sub (10%) |  |  | AFC App. (20%) |  |  | For Project control engineer follow up
Facility | Type | Deliverable Title | Description | Plan [A] | Forecast [B] | Actual [C] | Var. [C-A] | Weight % | Plan | Forecast | Actual | Plan | Forecast | Actual | Plan | Forecast | Actual | Plan | Forecast | Actual | IFR (50%) | IFA (20%) | AFC Sub (10%) | AFC App. (20%)
ZWP-21 | Report / Documents | MM-ZTK-1F-GEN-STR-SPE-2001 | SPECIFICATION FOR GROUT SEALS AND DIAPHRAGM | 100% | 100% | 100% | 0% | 0.2 | 2026-04-03 | 2026-04-03 | 2026-04-03 | 2026-05-15 | 2026-05-15 | 2026-06-18 | 2026-06-26 | 2026-06-26 | 2026-07-16 | 2026-07-10 | 2026-07-10 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-21 | Report / Documents | MM-ZTK-1F-GEN-STR-SPE-2002 | SPECIFICATION FOR STAINLESS STEEL BUNDLES | 100% | 100% | 100% | 0% | 0.2 | 2026-04-03 | 2026-04-03 | 2026-04-03 | 2026-05-15 | 2026-05-15 | 2026-05-29 | 2026-06-26 | 2026-06-26 | 2026-06-26 | 2026-07-10 | 2026-07-10 | 2026-07-01 | Completed | Completed | Completed | Completed
ZWP-21 | Report / Documents | MM-ZTK-1F-GEN-STR-SPE-2003 | SPECIFICATIONS FOR GRIPPER PERFORMANCE | 100% | 100% | 100% | 0% | 0.2 | 2026-04-03 | 2026-04-03 | 2026-04-03 | 2026-05-15 | 2026-05-15 | 2026-05-29 | 2026-06-26 | 2026-06-26 | 2026-07-16 | 2026-07-10 | 2026-07-10 | 2026-07-30 | Completed | Completed | Completed | Completed
ZWP-21 | Report / Documents | MM-ZTK-1F-GEN-STR-SPE-2004 | SPECIFICATION FOR GROUTING AND INSTALLATION | 100% | 100% | 70% | -30% | 0.2 | 2026-04-03 | 2026-04-03 | 2026-04-03 | 2026-05-15 | 2026-05-15 | 2026-05-29 | 2026-06-26 | 2026-06-26 |  | 2026-07-10 | 2026-07-10 |  | Completed | Completed | Overdue | Overdue
ZWP-21 | Report / Documents | MM-ZTK-1F-GEN-STR-SPE-2005 | SPECIFICATION FOR HYDRAULIC DRIVEN FLOODING SYSTEMS | 100% | 100% | 100% | 0% | 0.2 | 2026-04-03 | 2026-04-03 | 2026-04-03 | 2026-05-15 | 2026-05-15 | 2026-06-26 | 2026-06-26 | 2026-06-26 | 2026-07-02 | 2026-07-10 | 2026-07-10 | 2026-07-10 | Completed | Completed | Completed | Completed
ZWP-21 | Report / Documents | MM-ZTK-1F-ZWP21-STR-CAL-2001 | ZWP21 JACKET COMPUTER MODELING AND LOAD FORMULATION - SUPERSEDED | 100% | 100% | 100% | 0% | 0.25 | 2026-04-10 | 2026-04-10 | 2026-04-30 | 2026-05-22 | 2026-05-22 | 2026-07-03 | 2026-07-03 | 2026-07-03 | 2026-07-24 | 2026-07-17 | 2026-07-17 | 2026-07-24 | Completed | Completed | Completed | Completed
ZWP-21 | Report / Documents | MM-ZTK-1F-ZWP21-STR-CAL-2001 | ZWP21 JACKET COMPUTER MODELING AND LOAD FORMULATION - NEW WATER DEPTH | 80% | 80% | 70% | -10% | 0.25 | 2026-04-10 | 2026-04-10 | 2026-04-30 | 2026-05-22 | 2026-05-22 | 2026-07-03 | 2026-08-15 | 2026-08-15 |  | 2026-08-29 | 2026-08-29 |  | Completed | Completed | Overdue | Overdue
ZWP-21 | Report / Documents | MM-ZTK-1F-ZWP21-STR-CAL-2011 | ZWP21 JACKET IN-PLACE ANALYSIS - SUPERSEDED | 100% | 100% | 100% | 0% | 0.25 | 2026-04-24 | 2026-04-24 | 2026-05-22 | 2026-06-05 | 2026-06-05 | 2026-07-03 | 2026-07-17 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-07-31 | 2026-07-24 | Completed | Completed | Completed | Completed
ZWP-21 | Report / Documents | MM-ZTK-1F-ZWP21-STR-CAL-2011 | ZWP21 JACKET IN-PLACE ANALYSIS - NEW WATER DEPTH | 80% | 80% | 70% | -10% | 0.25 | 2026-04-24 | 2026-04-24 | 2026-05-22 | 2026-06-05 | 2026-06-05 | 2026-07-03 | 2026-08-22 | 2026-08-22 |  | 2026-09-05 | 2026-09-05 |  | Completed | Completed | Overdue | Follow-This Week
ZWP-21 | Report / Documents | MM-ZTK-1F-ZWP21-STR-CAL-2012 | ZWP21 JACKET DYNAMIC ANALYSIS - SUPERSEDED | 100% | 100% | 100% | 0% | 0.25 | 2026-05-01 | 2026-05-01 | 2026-05-19 | 2026-06-12 | 2026-06-12 | 2026-06-26 | 2026-07-24 | 2026-07-24 | 2026-07-24 | 2026-08-07 | 2026-08-07 | 2026-07-24 | Completed | Completed | Completed | Completed
ZWP-21 | Report / Documents | MM-ZTK-1F-ZWP21-STR-CAL-2012 | ZWP21 JACKET DYNAMIC ANALYSIS - NEW WATER DEPTH | 80% | 80% | 80% | 0% | 0.25 | 2026-05-01 | 2026-05-01 | 2026-05-19 | 2026-06-12 | 2026-06-12 | 2026-06-26 | 2026-08-15 | 2026-08-15 | 2026-08-28 | 2026-08-29 | 2026-08-29 |  | Completed | Completed | Completed | Overdue
ZWP-21 | Report / Documents | MM-ZTK-1F-ZWP21-STR-CAL-2014 | ZWP21 JACKET LOADOUT ANALYSIS - SUPERSEDED | 100% | 100% | 100% | 0% | 0.2 | 2026-05-08 | 2026-05-08 | 2026-04-30 | 2026-06-19 | 2026-06-19 | 2026-07-11 | 2026-07-31 | 2026-07-31 | 2026-08-21 | 2026-08-14 | 2026-08-14 | 2026-08-21 | Completed | Completed | Completed | Completed
ZWP-21 | Report / Documents | MM-ZTK-1F-ZWP21-STR-CAL-2014 | ZWP21 JACKET LOADOUT ANALYSIS - NEW WATER DEPTH | 100% | 100% | 70% | -30% | 0.3 | 2026-05-08 | 2026-05-08 | 2026-04-30 | 2026-06-19 | 2026-06-19 | 2026-07-11 | 2026-07-31 | 2026-07-31 |  | 2026-08-14 | 2026-08-14 |  | Completed | Completed | Overdue | Overdue
ZWP-21 | Report / Documents | MM-ZTK-1F-ZWP21-STR-CAL-2015 | ZWP21 JACKET TRANSPORTATION ANALYSIS - SUPERSEDED | 100% | 100% | 100% | 0% | 0.2 | 2026-05-22 | 2026-05-22 | 2026-05-13 | 2026-07-03 | 2026-07-03 | 2026-07-14 | 2026-08-14 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-08-28 | 2026-08-21 | Completed | Completed | Completed | Completed
ZWP-21 | Report / Documents | MM-ZTK-1F-ZWP21-STR-CAL-2015 | ZWP21 JACKET TRANSPORTATION ANALYSIS - NEW WATER DEPTH | 100% | 100% | 70% | -30% | 0.3 | 2026-05-22 | 2026-05-22 | 2026-05-13 | 2026-07-03 | 2026-07-03 | 2026-07-14 | 2026-08-14 | 2026-08-14 |  | 2026-08-28 | 2026-08-28 |  | Completed | Completed | Overdue | Overdue
ZWP-21 | Report / Documents | MM-ZTK-1F-ZWP21-STR-CAL-2016 | ZWP21 JACKET TRANSPORTATION FATIGUE | 80% | 80% | 70% | -10% | 0.5 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-07-17 | 2026-07-17 | 2026-07-23 | 2026-08-28 | 2026-08-28 |  | 2026-09-11 | 2026-09-11 |  | Completed | Completed | Overdue | Follow-Next Week
ZWP-21 | Report / Documents | MM-ZTK-1F-ZWP21-STR-CAL-2017 | ZWP21 JACKET BOAT IMPACT ANALYSIS | 70% | 70% | 70% | 0% | 0.5 | 2026-06-19 | 2026-06-19 | 2026-07-03 | 2026-07-31 | 2026-07-31 | 2026-07-09 | 2026-09-11 | 2026-09-11 |  | 2026-09-25 | 2026-09-25 |  | Completed | Completed | Follow-Next Week
ZWP-21 | Report / Documents | MM-ZTK-1F-ZWP21-STR-CAL-2018 | ZWP21 JACKET ON-BOTTOM STABILITY ANALYSIS - SUPERSEDED | 100% | 100% | 100% | 0% | 0.2 | 2026-05-15 | 2026-05-15 | 2026-06-02 | 2026-06-26 | 2026-06-26 | 2026-07-14 | 2026-08-07 | 2026-08-07 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Completed | Completed | Completed | Completed
ZWP-21 | Report / Documents | MM-ZTK-1F-ZWP21-STR-CAL-2018 | ZWP21 JACKET ON-BOTTOM STABILITY ANALYSIS - PILE PENETRATION OPTIMISATION | 100% | 100% | 70% | -30% | 0.3 | 2026-05-15 | 2026-05-15 | 2026-06-02 | 2026-06-26 | 2026-06-26 | 2026-07-14 | 2026-08-07 | 2026-08-07 |  | 2026-08-21 | 2026-08-21 |  | Completed | Completed | Overdue | Overdue
ZWP-21 | Report / Documents | MM-ZTK-1F-ZWP21-STR-CAL-2019 | ZWP21 JACKET MISCELLANEOUS DESIGN (SUPERSEDED) | 70% | 70% | 100% | 30% | 0.5 | 2026-06-15 | 2026-06-15 | 2026-06-19 | 2026-07-27 | 2026-07-27 | 2026-08-14 | 2026-09-07 | 2026-09-07 | 2026-08-14 | 2026-09-21 | 2026-09-21 | 2026-08-14 | Completed | Completed | Completed | Completed
ZWP-21 | Report / Documents | MM-ZTK-1F-ZWP21-STR-CAL-2019 | ZWP21 JACKET MISCELLANEOUS DESIGN (NEW WATER DEPTH) | 70% | 70% | 50% | -20% | 0.25 | 2026-06-15 | 2026-06-15 | 2026-06-19 | 2026-07-27 | 2026-07-27 |  | 2026-09-28 | 2026-09-28 |  | 2026-10-12 | 2026-10-12 |  | Completed | Overdue
ZWP-21 | Report / Documents | MM-ZTK-1F-ZWP21-STR-CAL-2020 | ZWP21 JACKET LEVELLING ANALYSIS | 70% | 70% | 70% | 0% | 0.5 | 2026-07-03 | 2026-07-03 | 2026-07-08 | 2026-08-14 | 2026-08-14 | 2026-07-20 | 2026-09-25 | 2026-09-25 |  | 2026-10-09 | 2026-10-09 |  | Completed | Completed
ZWP-21 | Report / Documents | MM-ZTK-1F-ZWP21-STR-CAL-2021 | ZWP21 JACKET PILE HANDLING AND STICK-UP ANALYSIS (SUPERSEDED) | 100% | 100% | 100% | 0% | 0.25 | 2026-05-08 | 2026-05-08 | 2026-07-03 | 2026-06-19 | 2026-06-19 | 2026-07-09 | 2026-07-31 | 2026-07-31 | 2026-08-14 | 2026-08-14 | 2026-08-14 | 2026-08-14 | Completed | Completed | Completed | Completed
ZWP-21 | Report / Documents | MM-ZTK-1F-ZWP21-STR-CAL-2021 | ZWP21 JACKET PILE HANDLING AND STICK-UP ANALYSIS (OPTIMISATION) | 70% | 70% | 70% | 0% | 0.25 | 2026-05-08 | 2026-05-08 | 2026-07-03 | 2026-06-19 | 2026-06-19 | 2026-07-09 | 2026-08-31 | 2026-08-31 |  | 2026-09-14 | 2026-09-14 |  | Completed | Completed | Follow-This Week
ZWP-21 | Report / Documents | MM-ZTK-1F-ZWP21-STR-CAL-2022 | ZWP21 PILE DRIVEABILITY AND PILE FATIGUE ANALYSIS (SUPERSEDED) | 100% | 100% | 100% | 0% | 0.25 | 2026-05-15 | 2026-05-15 | 2026-05-19 | 2026-06-26 | 2026-06-26 | 2026-07-15 | 2026-08-07 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-21 | 2026-08-14 | Completed | Completed | Completed | Completed
ZWP-21 | Report / Documents | MM-ZTK-1F-ZWP21-STR-CAL-2022 | ZWP21 PILE DRIVEABILITY AND PILE FATIGUE ANALYSIS (OPTIMISATION) | 70% | 70% | 70% | 0% | 0.25 | 2026-05-15 | 2026-05-15 | 2026-05-19 | 2026-06-26 | 2026-06-26 | 2026-07-15 | 2026-08-31 | 2026-08-31 |  | 2026-09-14 | 2026-09-14 |  | Completed | Completed | Follow-This Week
ZWP-21 | Report / Documents | MM-ZTK-1F-ZWP21-STR-CAL-2023 | ZWP21 JACKET PILE CLUSTER AND SKIRT PILE SLEEVE DESIGN WITH FEA - SUPERSEDED | 50% | 50% | 100% | 50% | 0.4 | 2026-07-24 | 2026-07-24 | 2026-07-31 | 2026-09-04 | 2026-09-04 | 2026-07-31 | 2026-10-16 | 2026-10-16 | 2026-07-31 | 2026-10-30 | 2026-10-30 | 2026-07-31 | Completed
ZWP-21 | Report / Documents | MM-ZTK-1F-ZWP21-STR-CAL-2023 | ZWP21 JACKET PILE CLUSTER AND SKIRT PILE SLEEVE DESIGN WITH FEA - NEW WATER DEPTH | 50% | 50% | 70% | 20% | 0.4 | 2026-07-24 | 2026-07-24 | 2026-07-31 | 2026-09-04 | 2026-09-04 | 2026-08-14 | 2026-10-16 | 2026-10-16 |  | 2026-10-30 | 2026-10-30 |  | Completed | Completed
ZWP-21 | Report / Documents | MM-ZTK-1F-ZWP21-STR-CAL-2024 | ZWP21 PILE GROUP EFFECT ANALYSIS | 50% | 50% | 70% | 20% | 0.8 | 2026-08-07 | 2026-08-07 | 2026-06-05 | 2026-09-18 | 2026-09-18 | 2026-06-19 | 2026-10-30 | 2026-10-30 |  | 2026-11-13 | 2026-11-13 |  | Completed | Completed
ZWP-21 | Report / Documents | MM-ZTK-1F-ZWP21-STR-CAL-2025 | ZWP21 MUDMAT FEA ANALYSIS | 50% | 50% | 70% | 20% | 0.8 | 2026-08-15 | 2026-08-15 | 2026-08-07 | 2026-09-26 | 2026-09-26 | 2026-08-14 | 2026-11-07 | 2026-11-07 |  | 2026-11-21 | 2026-11-21 |  | Completed | Completed
ZWP-21 | Report / Documents | MM-ZTK-1F-ZWP21-STR-CAL-2026 | ZWP21 JACKET PILE TRANSPORTATION FATIGUE | 0% | 0% | 0% | 0% | 0.5 | 2026-10-07 | 2026-10-07 |  | 2026-11-18 | 2026-11-18 |  | 2026-12-30 | 2026-12-30 |  | 2027-01-13 | 2027-01-13
ZWP-21 | Report / Documents | MM-ZTK-1F-ZWP21-STR-CAL-2041 | ZWP21 JACKET PUSHOVER ANALYSIS - SUPERSEDED | 80% | 80% | 100% | 20% | 0.2 | 2026-05-29 | 2026-05-29 | 2026-06-05 | 2026-07-10 | 2026-07-10 | 2026-07-17 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-09-04 | 2026-09-04 | 2026-08-21 | Completed | Completed | Completed | Completed
ZWP-21 | Report / Documents | MM-ZTK-1F-ZWP21-STR-CAL-2041 | ZWP21 JACKET PUSHOVER ANALYSIS - PILE PENETRATION OPTIMISATION | 80% | 80% | 70% | -10% | 0.3 | 2026-05-29 | 2026-05-29 | 2026-06-05 | 2026-07-10 | 2026-07-10 | 2026-07-17 | 2026-08-21 | 2026-08-21 |  | 2026-09-04 | 2026-09-04 |  | Completed | Completed | Overdue | Follow-This Week
ZWP-21 | Report / Documents | MM-ZTK-1F-ZWP21-STR-CAL-2050 | ZWP21 JACKET CONSTRUCTION MODEL REPORT | 50% | 50% | 70% | 20% | 0.5 | 2026-07-24 | 2026-07-24 | 2026-04-30 | 2026-09-04 | 2026-09-04 | 2026-07-15 | 2026-10-16 | 2026-10-16 |  | 2026-10-30 | 2026-10-30 |  | Completed | Completed
ZWP-21 | Report / Documents | MM-ZTK-1F-ZWP21-NVA-CAL-2011 | ZWP21 JACKET BARGE MOTION ANALYSIS - SUPERSEDED | 100% | 100% | 100% | 0% | 0.25 | 2026-05-22 | 2026-05-22 | 2026-05-19 | 2026-07-03 | 2026-07-03 | 2026-07-14 | 2026-08-14 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-08-28 | 2026-08-21 | Completed | Completed | Completed | Completed
ZWP-21 | Report / Documents | MM-ZTK-1F-ZWP21-NVA-CAL-2011 | ZWP21 JACKET BARGE MOTION ANALYSIS - NEW WATER DEPTH | 100% | 100% | 80% | -20% | 0.3 | 2026-05-22 | 2026-05-22 | 2026-05-19 | 2026-07-03 | 2026-07-03 | 2026-07-14 | 2026-08-14 | 2026-08-14 | 2026-08-28 | 2026-08-28 | 2026-08-28 |  | Completed | Completed | Completed | Overdue
ZWP-21 | Report / Documents | MM-ZTK-1F-ZWP21-NVA-CAL-2012 | ZWP21 JACKET LAUNCH ANALYSIS REPORT | 80% | 80% | 70% | -10% | 0.55 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-07-10 | 2026-07-10 | 2026-07-11 | 2026-08-21 | 2026-08-21 |  | 2026-09-04 | 2026-09-04 |  | Completed | Completed | Overdue | Follow-This Week
ZWP-21 | Report / Documents | MM-ZTK-1F-ZWP21-NVA-CAL-2013 | ZWP21 JACKER FREE FLOATATION AND UPENDING ANALYSIS REPORT | 70% | 70% | 70% | 0% | 0.75 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2026-07-31 | 2026-07-31 | 2026-07-17 | 2026-09-11 | 2026-09-11 |  | 2026-09-25 | 2026-09-25 |  | Completed | Completed | Follow-Next Week
ZWP-21 | Report / Documents | MM-ZTK-1F-ZWP21-STR-WCR-2001 | ZWP21 JACKET WEIGHT CONTROL REPORT - SUPERSEDED | 100% | 100% | 100% | 0% | 0.5 | 2026-04-03 | 2026-04-03 | 2026-04-10 | 2026-05-15 | 2026-05-15 | 2026-06-26 | 2026-06-26 | 2026-06-26 | 2026-07-24 | 2026-07-10 | 2026-07-10 | 2026-07-24 | Completed | Completed | Completed | Completed
ZWP-21 | Report / Documents | MM-ZTK-1F-ZWP21-STR-WCR-2001 | ZWP21 JACKET WEIGHT CONTROL REPORT - NEW WATER DEPTH | 80% | 80% | 80% | 0% | 0.5 | 2026-04-03 | 2026-04-03 | 2026-04-10 | 2026-05-15 | 2026-05-15 | 2026-06-26 | 2026-08-15 | 2026-08-15 | 2026-08-15 | 2026-08-29 | 2026-08-29 |  | Completed | Completed | Completed | Overdue
ZWP-21 | Report / Documents | MM-ZTK-1F-ZWP21-STR-MTO-2001 | ZWP21 JACKET PRIMARY STEEL AND PILE MTO REPORT | 80% | 80% | 100% | 20% | 0.4 | 2026-06-05 | 2026-06-05 | 2026-07-03 | 2026-07-17 | 2026-07-17 | 2026-07-09 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-09-11 | 2026-09-11 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-21 | Report / Documents | MM-ZTK-1F-ZWP21-STR-MTO-2001 | ZWP21 JACKET PRIMARY STEEL AND PILE MTO REPORT - UPDATE WD | 80% | 80% | 70% | -10% | 0.1 | 2026-06-05 | 2026-06-05 | 2026-07-03 | 2026-07-17 | 2026-07-17 | 2026-07-09 | 2026-08-28 | 2026-08-28 |  | 2026-09-11 | 2026-09-11 |  | Completed | Completed | Overdue | Follow-Next Week
ZWP-21 | Report / Documents | MM-ZTK-1F-ZWP21-STR-MTO-2002 | ZWP21 JACKET SECONDARY AND TERTIARY STEEL MTO REPORT | 70% | 70% | 70% | 0% | 0.5 | 2026-06-12 | 2026-06-12 | 2026-07-03 | 2026-07-24 | 2026-07-24 | 2026-07-09 | 2026-09-04 | 2026-09-04 |  | 2026-09-18 | 2026-09-18 |  | Completed | Completed | Follow-This Week
ZWP-21 | Report / Documents | MM-ZTK-1F-ZWP21-STR-MR-2001 | MATERIAL REQUISITION FOR ZWP21 JACKET PRIMARY TUBULAR STEEL | 100% | 100% | 100% | 0% | 0.3 | 2026-04-10 | 2026-04-10 | 2026-04-03 | 2026-05-22 | 2026-05-22 | 2026-06-18 | 2026-07-03 | 2026-07-03 | 2026-08-28 | 2026-07-17 | 2026-07-17 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-21 | Report / Documents | MM-ZTK-1F-ZWP21-STR-MR-2001 | MATERIAL REQUISITION FOR ZWP21 JACKET PRIMARY TUBULAR STEEL - UPDATE WD | 100% | 100% | 70% | -30% | 0.1 | 2026-04-10 | 2026-04-10 | 2026-04-03 | 2026-05-22 | 2026-05-22 | 2026-06-18 | 2026-07-03 | 2026-07-03 |  | 2026-07-17 | 2026-07-17 |  | Completed | Completed | Overdue | Overdue
ZWP-21 | Report / Documents | MM-ZTK-1F-ZWP21-STR-MR-2002 | MATERIAL REQUISITION FOR ZWP21 JACKET PRIMARY STEEL (PLATE) | 100% | 100% | 100% | 0% | 0.3 | 2026-04-17 | 2026-04-17 | 2026-04-30 | 2026-05-29 | 2026-05-29 | 2026-06-18 | 2026-07-10 | 2026-07-10 | 2026-08-28 | 2026-07-24 | 2026-07-24 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-21 | Report / Documents | MM-ZTK-1F-ZWP21-STR-MR-2002 | MATERIAL REQUISITION FOR ZWP21 JACKET PRIMARY STEEL (PLATE) - UPDATE WD | 100% | 100% | 70% | -30% | 0.1 | 2026-04-17 | 2026-04-17 | 2026-04-30 | 2026-05-29 | 2026-05-29 | 2026-06-18 | 2026-07-10 | 2026-07-10 |  | 2026-07-24 | 2026-07-24 |  | Completed | Completed | Overdue | Overdue
ZWP-21 | Report / Documents | MM-ZTK-1F-ZWP21-STR-MR-2003 | MATERIAL REQUISITION FOR ZWP21 JACKET SECONDARY AND TERTIARY STEEL |  |  |  |  | 0.2 | 2026-04-30 | 2026-04-30 | 2026-06-26 | 2026-06-11 | 2026-06-11 | 2026-06-26 | 2026-07-23 | 2026-07-23 | 2026-07-10 | 2026-08-06 | 2026-08-06 | 2026-08-06 | Completed | Completed | Completed | Completed
ZWP-21 | Report / Documents | MM-ZTK-1F-ZWP21-STR-MR-2003 | MATERIAL REQUISITION FOR ZEP21 JACKET MISCELLANEOUS STEEL | 70% | 70% | 80% | 10% |  | 2026-06-22 | 2026-06-22 | 2026-07-10 | 2026-08-03 | 2026-08-03 | 2026-07-10 | 2026-09-14 | 2026-09-14 | 2026-07-10 | 2026-09-28 | 2026-09-28 |  | Completed | Completed | Completed
ZWP-21 | Report / Documents | MM-ZTK-1F-GEN-STR-MR-0001 | MATERIAL REQUISITION FOR PILE GRIPPER WITH INTEGRAL DIAPHRAGM CLOSURE | 100% | 100% | 100% | 0% | 0.2 | 2026-05-15 | 2026-05-15 | 2026-05-08 | 2026-06-26 | 2026-06-26 | 2026-06-18 | 2026-08-07 | 2026-08-07 | 2026-07-24 | 2026-08-21 | 2026-08-21 | 2026-08-05 | Completed | Completed | Completed | Completed
ZWP-21 | Report / Documents | MM-ZTK-1F-GEN-STR-MR-0002 | MATERIAL REQUISITION FOR GROUT SEALS AND DIAPHRAGM CLOSURE | 100% | 100% | 100% | 0% | 0.2 | 2026-05-15 | 2026-05-15 | 2026-05-08 | 2026-06-26 | 2026-06-26 | 2026-06-18 | 2026-08-07 | 2026-08-07 | 2026-07-24 | 2026-08-21 | 2026-08-21 | 2026-08-05 | Completed | Completed | Completed | Completed
ZWP-21 | Report / Documents | MM-ZTK-1F-GEN-STR-MR-0003 | MATERIAL REQUISITION FOR BARGE BUMPER | 100% | 100% | 100% | 0% | 0.2 | 2026-05-01 | 2026-05-01 | 2026-04-30 | 2026-06-12 | 2026-06-12 | 2026-06-18 | 2026-07-24 | 2026-07-24 | 2026-06-29 | 2026-08-07 | 2026-08-07 | 2026-07-06 | Completed | Completed | Completed | Completed
ZWP-21 | Report / Documents | MM-ZTK-1F-GEN-STR-MR-0004 | MATERIAL REQUISITION FOR ANODE | 100% | 100% | 80% | -20% | 0.2 | 2026-05-01 | 2026-05-01 | 2026-04-30 | 2026-06-12 | 2026-06-12 | 2026-06-18 | 2026-07-24 | 2026-07-24 | 2026-08-20 | 2026-08-07 | 2026-08-07 |  | Completed | Completed | Completed | Overdue
ZWP-21 | Report / Documents | MM-ZTK-1F-GEN-STR-MR-0005 | MATERIAL REQUISITION FOR LAUNCH TIMBER | 100% | 100% | 100% | 0% | 0.2 | 2026-05-15 | 2026-05-15 | 2026-05-08 | 2026-06-26 | 2026-06-26 | 2026-06-18 | 2026-08-07 | 2026-08-07 | 2026-07-01 | 2026-08-21 | 2026-08-21 | 2026-07-20 | Completed | Completed | Completed | Completed
ZWP-21 | Report / Documents | MM-ZTK-1F-ZWP21-COR-CAL-0001 | ZWP21 CATHODIC PROTECTION DESIGN REPORT | 70% | 70% | 70% | 0% | 0.5 | 2026-06-12 | 2026-06-12 | 2026-05-29 | 2026-07-24 | 2026-07-24 | 2026-08-06 | 2026-09-04 | 2026-09-04 |  | 2026-09-18 | 2026-09-18 |  | Completed | Completed | Follow-This Week
ZWP-21 | Report / Documents | MM-ZTK-1F-ZWP21-STR-CAL-2801 | ZWP21 JACKET RISER CLAMP DESIGN | 0% | 0% | 0% | 0% |  | 2026-10-07 | 2026-10-07 |  | 2026-11-18 | 2026-11-18 |  | 2026-12-30 | 2026-12-30 |  | 2027-01-13 | 2027-01-13
ZWP-21 | Report / Documents | MM-ZTK-1F-ZWP21-WCR-CAL-2101 | ZWP21 WEIGHT CONTROL REPORT (AS-BUILT) | 0% | 0% | 0% | 0% | 0.2
ZWP-21 | Report / Documents | MM-ZTK-1F-ZWP21-STR-CAL-2101 | ZWP21 COMPUTER MODELLING AND LOAD FORMULATION REPORT (AS-BUILT) | 0% | 0% | 0% | 0% | 0.4
ZWP-21 | Report / Documents | MM-ZTK-1F-ZWP21-STR-CAL-2150 | ZWP21 CONSTRUCTION MODEL REPORT (AS-BUILT) | 0% | 0% | 0% | 0% | 0.4
ZWP-23 | Report / Documents | MM-ZTK-1F-GEN-ZTR-SPE-2001 | SPECIFICATION FOR GROUT SEALS AND DIAPHRAGM | 100% | 100% | 100% | 0% | 0.2 | 2026-04-03 | 2026-04-03 | 2026-04-03 | 2026-05-15 | 2026-05-15 | 2026-06-18 | 2026-06-26 | 2026-06-26 | 2026-07-16 | 2026-07-10 | 2026-07-10 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-23 | Report / Documents | MM-ZTK-1F-GEN-ZTR-SPE-2002 | SPECIFICATION FOR STAINLESS STEEL BUNDLES | 100% | 100% | 100% | 0% | 0.2 | 2026-04-03 | 2026-04-03 | 2026-04-03 | 2026-05-15 | 2026-05-15 | 2026-05-29 | 2026-06-26 | 2026-06-26 | 2026-06-26 | 2026-07-10 | 2026-07-10 | 2026-07-01 | Completed | Completed | Completed | Completed
ZWP-23 | Report / Documents | MM-ZTK-1F-GEN-ZTR-SPE-2003 | SPECIFICATIONS FOR GRIPPER PERFORMANCE | 100% | 100% | 100% | 0% | 0.2 | 2026-04-03 | 2026-04-03 | 2026-04-03 | 2026-05-15 | 2026-05-15 | 2026-05-29 | 2026-06-26 | 2026-06-26 | 2026-07-16 | 2026-07-10 | 2026-07-10 | 2026-07-30 | Completed | Completed | Completed | Completed
ZWP-23 | Report / Documents | MM-ZTK-1F-GEN-ZTR-SPE-2004 | SPECIFICATION FOR GROUTING AND INSTALLATION | 100% | 100% | 70% | -30% | 0.2 | 2026-04-03 | 2026-04-03 | 2026-04-03 | 2026-05-15 | 2026-05-15 | 2026-05-29 | 2026-06-26 | 2026-06-26 |  | 2026-07-10 | 2026-07-10 |  | Completed | Completed | Overdue | Overdue
ZWP-23 | Report / Documents | MM-ZTK-1F-GEN-ZTK-SPE-2005 | SPECIFICATION FOR HYDRAULIC DRIVEN FLOODING SYSTEMS | 100% | 100% | 100% | 0% | 0.2 | 2026-04-03 | 2026-04-03 | 2026-04-03 | 2026-05-15 | 2026-05-15 | 2026-06-26 | 2026-06-26 | 2026-06-26 | 2026-07-01 | 2026-07-10 | 2026-07-10 | 2026-07-10 | Completed | Completed | Completed | Completed
ZWP-23 | Report / Documents | MM-ZTK-1F-ZWP23-STR-CAL-2001 | ZWP23 JACKET COMPUTER MODELING AND LOAD FORMULATION - SUPERSEDED | 100% | 100% | 100% | 0% | 0.25 | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-06-19 | 2026-06-19 | 2026-07-17 | 2026-07-31 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-14 | 2026-08-07 | Completed | Completed | Completed | Completed
ZWP-23 | Report / Documents | MM-ZTK-1F-ZWP23-STR-CAL-2001 | ZWP23 JACKET COMPUTER MODELING AND LOAD FORMULATION - NEW WATER DEPTH | 70% | 70% | 70% | 0% | 0.25 | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-06-19 | 2026-06-19 | 2026-07-17 | 2026-09-12 | 2026-09-12 |  | 2026-09-26 | 2026-09-26 |  | Completed | Completed | Follow-Next Week
ZWP-23 | Report / Documents | MM-ZTK-1F-ZWP23-STR-CAL-2011 | ZWP23 JACKET IN-PLACE ANALYSIS | 100% | 100% | 70% | -30% | 0.5 | 2026-05-22 | 2026-05-22 | 2026-06-05 | 2026-07-03 | 2026-07-03 | 2026-07-24 | 2026-08-14 | 2026-08-14 |  | 2026-08-28 | 2026-08-28 |  | Completed | Completed | Overdue | Overdue
ZWP-23 | Report / Documents | MM-ZTK-1F-ZWP23-STR-CAL-2012 | ZWP23 JACKET DYNAMIC ANALYSIS | 80% | 80% | 70% | -10% | 0.5 | 2026-05-29 | 2026-05-29 | 2026-05-19 | 2026-07-10 | 2026-07-10 | 2026-07-20 | 2026-08-21 | 2026-08-21 |  | 2026-09-04 | 2026-09-04 |  | Completed | Completed | Overdue | Follow-This Week
ZWP-23 | Report / Documents | MM-ZTK-1F-ZWP23-STR-CAL-2014 | ZWP23 JACKET LOADOUT ANALYSIS | 80% | 80% | 70% | -10% | 0.5 | 2026-06-05 | 2026-06-05 | 2026-05-08 | 2026-07-17 | 2026-07-17 | 2026-07-27 | 2026-08-28 | 2026-08-28 |  | 2026-09-11 | 2026-09-11 |  | Completed | Completed | Overdue | Follow-Next Week
ZWP-23 | Report / Documents | MM-ZTK-1F-ZWP23-STR-CAL-2015 | ZWP23 JACKET TRANSPORTATION ANALYSIS | 70% | 70% | 70% | 0% | 0.5 | 2026-06-19 | 2026-06-19 | 2026-05-13 | 2026-07-31 | 2026-07-31 | 2026-07-27 | 2026-09-11 | 2026-09-11 |  | 2026-09-25 | 2026-09-25 |  | Completed | Completed | Follow-Next Week
ZWP-23 | Report / Documents | MM-ZTK-1F-ZWP23-STR-CAL-2016 | ZWP23 JACKET TRANSPORTATION FATIGUE | 70% | 70% | 70% | 0% | 0.5 | 2026-07-03 | 2026-07-03 | 2026-06-12 | 2026-08-14 | 2026-08-14 | 2026-08-07 | 2026-09-25 | 2026-09-25 |  | 2026-10-09 | 2026-10-09 |  | Completed | Completed
ZWP-23 | Report / Documents | MM-ZTK-1F-ZWP23-STR-CAL-2017 | ZWP23 JACKET BOAT IMPACT ANALYSIS | 70% | 70% | 70% | 0% | 0.5 | 2026-07-17 | 2026-07-17 | 2026-07-20 | 2026-08-28 | 2026-08-28 | 2026-08-14 | 2026-10-09 | 2026-10-09 |  | 2026-10-23 | 2026-10-23 |  | Completed | Completed
ZWP-23 | Report / Documents | MM-ZTK-1F-ZWP23-STR-CAL-2018 | ZWP23 JACKET ON-BOTTOM STABILITY ANALYSIS | 70% | 70% | 70% | 0% | 0.5 | 2026-06-12 | 2026-06-12 | 2026-06-08 | 2026-07-24 | 2026-07-24 | 2026-07-24 | 2026-09-04 | 2026-09-04 |  | 2026-09-18 | 2026-09-18 |  | Completed | Completed | Follow-This Week
ZWP-23 | Report / Documents | MM-ZTK-1F-ZWP23-STR-CAL-2019 | ZWP23 JACKET MISCELLANEOUS DESIGN | 70% | 70% | 50% | -20% | 0.75 | 2026-07-13 | 2026-07-13 | 2026-07-16 | 2026-08-17 | 2026-08-17 |  | 2026-09-28 | 2026-09-28 |  | 2026-10-12 | 2026-10-12 |  | Completed | Overdue
ZWP-23 | Report / Documents | MM-ZTK-1F-ZWP23-STR-CAL-2020 | ZWP23 JACKET LEVELLING ANALYSIS | 50% | 50% | 70% | 20% | 0.5 | 2026-07-31 | 2026-07-31 | 2026-07-15 | 2026-09-11 | 2026-09-11 | 2026-08-14 | 2026-10-23 | 2026-10-23 |  | 2026-11-06 | 2026-11-06 |  | Completed | Completed
ZWP-23 | Report / Documents | MM-ZTK-1F-ZWP23-STR-CAL-2021 | ZWP23 JACKET PILE HANDLING AND STICK-UP ANALYSIS - SUPERSEDED | 80% | 80% | 100% | 20% | 0.25 | 2026-06-05 | 2026-06-05 | 2026-07-15 | 2026-07-17 | 2026-07-17 | 2026-07-31 | 2026-08-28 | 2026-08-28 | 2026-07-31 | 2026-09-11 | 2026-09-11 | 2026-07-31 | Completed | Completed | Completed | Completed
ZWP-23 | Report / Documents | MM-ZTK-1F-ZWP23-STR-CAL-2021 | ZWP23 JACKET PILE HANDLING AND STICK-UP ANALYSIS - UPDATED ISO19901 STANDARD | 70% | 70% | 70% | 0% | 0.25 | 2026-06-12 | 2026-06-12 | 2026-07-15 | 2026-08-07 | 2026-08-07 | 2026-08-14 | 2026-09-18 | 2026-09-18 |  | 2026-10-02 | 2026-10-02 |  | Completed | Completed
ZWP-23 | Report / Documents | MM-ZTK-1F-ZWP23-STR-CAL-2022 | ZWP23 PILE DRIVEABILITY AND PILE FATIGUE ANALYSIS | 70% | 70% | 70% | 0% | 0.5 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-07-24 | 2026-07-24 | 2026-07-22 | 2026-09-04 | 2026-09-04 |  | 2026-09-18 | 2026-09-18 |  | Completed | Completed | Follow-This Week
ZWP-23 | Report / Documents | MM-ZTK-1F-ZWP23-STR-CAL-2023 | ZWP23 JACKET PILE CLUSTER AND SKIRT PILE SLEEVE DESIGN WITH FEA | 50% | 50% | 50% | 0% | 0.8 | 2026-08-21 | 2026-08-21 | 2026-08-14 | 2026-10-02 | 2026-10-02 |  | 2026-11-13 | 2026-11-13 |  | 2026-11-27 | 2026-11-27 |  | Completed
ZWP-23 | Report / Documents | MM-ZTK-1F-ZWP23-STR-CAL-2024 | ZWP23 PILE GROUP EFFECT ANALYSIS | 0% | 0% | 70% | 70% | 0.8 | 2026-09-04 | 2026-09-04 | 2026-06-29 | 2026-10-16 | 2026-10-16 | 2026-07-06 | 2026-11-27 | 2026-11-27 |  | 2026-12-11 | 2026-12-11 |  | Completed | Completed
ZWP-23 | Report / Documents | MM-ZTK-1F-ZWP23-STR-CAL-2025 | ZWP23 MUDMAT FEA ANALYSIS | 0% | 0% | 50% | 50% | 0.8 | 2026-09-12 | 2026-09-12 | 2026-08-14 | 2026-10-24 | 2026-10-24 |  | 2026-12-05 | 2026-12-05 |  | 2026-12-19 | 2026-12-19 |  | Completed
ZWP-23 | Report / Documents | MM-ZTK-1F-ZWP23-STR-CAL-2026 | ZWP23 JACKET PILE TRANSPORTATION FATIGUE | 0% | 0% | 0% | 0% | 0.5 | 2026-11-04 | 2026-11-04 |  | 2026-12-16 | 2026-12-16 |  | 2027-01-27 | 2027-01-27 |  | 2027-02-10 | 2027-02-10
ZWP-23 | Report / Documents | MM-ZTK-1F-ZWP23-STR-CAL-2041 | ZWP23 JACKET PUSHOVER ANALYSIS | 70% | 70% | 70% | 0% | 0.5 | 2026-06-26 | 2026-06-26 | 2026-06-19 | 2026-08-07 | 2026-08-07 | 2026-08-03 | 2026-09-18 | 2026-09-18 |  | 2026-10-02 | 2026-10-02 |  | Completed | Completed
ZWP-23 | Report / Documents | MM-ZTK-1F-ZWP23-STR-CAL-2050 | ZWP23 JACKET CONSTRUCTION MODEL REPORT | 50% | 50% | 70% | 20% | 0.5 | 2026-08-21 | 2026-08-21 | 2026-05-08 | 2026-10-02 | 2026-10-02 | 2026-07-17 | 2026-11-13 | 2026-11-13 |  | 2026-11-27 | 2026-11-27 |  | Completed | Completed
ZWP-23 | Report / Documents | MM-ZTK-1F-ZWP23-NVA-CAL-2011 | ZWP23 JACKET BARGE MOTION ANALYSIS | 70% | 70% | 70% | 0% | 0.55 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2026-07-31 | 2026-07-31 | 2026-07-24 | 2026-09-11 | 2026-09-11 |  | 2026-09-25 | 2026-09-25 |  | Completed | Completed | Follow-Next Week
ZWP-23 | Report / Documents | MM-ZTK-1F-ZWP23-NVA-CAL-2012 | ZWP23 JACKET LAUNCH ANALYSIS REPORT | 70% | 70% | 70% | 0% | 0.55 | 2026-06-26 | 2026-06-26 | 2026-05-13 | 2026-08-07 | 2026-08-07 | 2026-08-10 | 2026-09-18 | 2026-09-18 |  | 2026-10-02 | 2026-10-02 |  | Completed | Completed
ZWP-23 | Report / Documents | MM-ZTK-1F-ZWP23-NVA-CAL-2013 | ZWP23 JACKER FREE FLOATATION AND UPENDING ANALYSIS REPORT - SUPERSEDED | 70% | 70% | 100% | 30% | 0.375 | 2026-07-17 | 2026-07-17 | 2026-07-31 | 2026-08-28 | 2026-08-28 | 2026-07-31 | 2026-10-09 | 2026-10-09 | 2026-07-31 | 2026-10-23 | 2026-10-23 | 2026-07-31 | Completed | Completed | Completed | Completed
ZWP-23 | Report / Documents | MM-ZTK-1F-ZWP23-NVA-CAL-2013 | ZWP23 JACKET FREE FLOATATION AND UPENDING ANALYSIS REPORT - NEW WATER DEPTH | 70% | 70% | 70% | 0% | 0.375 | 2026-08-07 | 2026-08-07 | 2026-08-03 | 2026-08-28 | 2026-08-28 | 2026-08-18 | 2026-10-09 | 2026-10-09 |  | 2026-10-23 | 2026-10-23 |  | Completed | Completed
ZWP-23 | Report / Documents | MM-ZTK-1F-ZWP23-STR-WCR-2001 | ZWP23 JACKET WEIGHT CONTROL REPORT | 100% | 100% | 70% | -30% | 1 | 2026-05-01 | 2026-05-01 | 2026-04-10 | 2026-06-12 | 2026-06-12 | 2026-07-10 | 2026-07-24 | 2026-07-24 |  | 2026-08-07 | 2026-08-07 |  | Completed | Completed | Overdue | Overdue
ZWP-23 | Report / Documents | MM-ZTK-1F-ZWP23-STR-MTO-2001 | ZWP23 JACKET PRIMARY STEEL MTO REPORT | 70% | 70% | 70% | 0% | 0.5 | 2026-07-03 | 2026-07-03 | 2026-07-17 | 2026-08-14 | 2026-08-14 | 2026-08-18 | 2026-09-25 | 2026-09-25 |  | 2026-10-09 | 2026-10-09 |  | Completed | Completed
ZWP-23 | Report / Documents | MM-ZTK-1F-ZWP23-STR-MTO-2002 | ZWP23 JACKET SECONDARY STEEL MTO REPORT | 70% | 70% | 70% | 0% | 0.5 | 2026-07-10 | 2026-07-10 | 2026-07-17 | 2026-08-21 | 2026-08-21 | 2026-08-14 | 2026-10-02 | 2026-10-02 |  | 2026-10-16 | 2026-10-16 |  | Completed | Completed
ZWP-23 | Report / Documents | MM-ZTK-1F-ZWP23-STR-MR-2001 | MATERIAL REQUISITION FOR ZWP23 JACKET PRIMARY TUBULAR STEEL | 100% | 100% | 70% | -30% | 0.4 | 2026-04-10 | 2026-04-10 | 2026-04-03 | 2026-05-22 | 2026-05-22 | 2026-06-18 | 2026-07-03 | 2026-07-03 |  | 2026-07-17 | 2026-07-17 |  | Completed | Completed | Overdue | Overdue
ZWP-23 | Report / Documents | MM-ZTK-1F-ZWP23-STR-MR-2002 | MATERIAL REQUISITION FOR ZWP23 JACKET PRIMARY STEEL (PLATE) | 100% | 100% | 70% | -30% | 0.4 | 2026-04-17 | 2026-04-17 | 2026-04-30 | 2026-05-29 | 2026-05-29 | 2026-06-18 | 2026-07-10 | 2026-07-10 |  | 2026-07-24 | 2026-07-24 |  | Completed | Completed | Overdue | Overdue
ZWP-23 | Report / Documents | MM-ZTK-1F-ZWP23-STR-MR-2003 | MATERIAL REQUISITION FOR ZWP23 JACKET SECONDARY AND TERTIARY STEEL |  |  |  |  | 0.2 | 2026-04-30 | 2026-04-30 | 2026-08-14 | 2026-06-11 | 2026-06-11 | 2026-08-14 | 2026-07-23 | 2026-07-23 | 2026-08-14 | 2026-08-06 | 2026-08-06 | 2026-08-14 | Completed | Completed | Completed | Completed
ZWP-23 | Report / Documents | MM-ZTK-1F-ZWP23-STR-MR-2003 | MATERIAL REQUISITION FOR ZWP23 JACKET MISCELLANEOUS STEEL | 100% | 100% | 0% | -100% |  | 2026-04-30 | 2026-04-30 |  | 2026-06-11 | 2026-06-11 |  | 2026-07-23 | 2026-07-23 |  | 2026-08-06 | 2026-08-06 |  | Overdue | Overdue | Overdue | Overdue
ZWP-23 | Report / Documents | MM-ZTK-1F-GEN-STR-MR-0001 | MATERIAL REQUISITION FOR PILE GRIPPER WITH INTEGRAL DIAPHRAGM CLOSURE | 0% | 0% | 50% | 50% | 0.2 | 2026-05-15 | 2026-05-15 | 2026-05-08 | 2026-06-26 | 2026-06-26 | 2026-06-18 | 2026-08-07 | 2026-08-07 | 2026-07-24 | 2026-08-21 | 2026-08-21 | 2026-08-05 | Completed | Completed | Completed | Completed
ZWP-23 | Report / Documents | MM-ZTK-1F-GEN-STR-MR-0002 | MATERIAL REQUISITION FOR GROUT SEALS AND DIAPHRAGM CLOSURE | 0% | 0% | 50% | 50% | 0.2 | 2026-05-15 | 2026-05-15 | 2026-05-08 | 2026-06-26 | 2026-06-26 | 2026-06-18 | 2026-08-07 | 2026-08-07 | 2026-07-24 | 2026-08-21 | 2026-08-21 | 2026-08-05 | Completed | Completed | Completed | Completed
ZWP-23 | Report / Documents | MM-ZTK-1F-GEN-STR-MR-0003 | MATERIAL REQUISITION FOR BARGE BUMPER | 50% | 50% | 50% | 0% | 0.2 | 2026-05-01 | 2026-05-01 | 2026-04-30 | 2026-06-12 | 2026-06-12 | 2026-06-18 | 2026-07-24 | 2026-07-24 | 2026-06-29 | 2026-08-07 | 2026-08-07 | 2026-07-06 | Completed | Completed | Completed | Completed
ZWP-23 | Report / Documents | MM-ZTK-1F-GEN-STR-MR-0004 | MATERIAL REQUISITION FOR ANODE | 50% | 50% | 50% | 0% | 0.2 | 2026-05-01 | 2026-05-01 | 2026-04-30 | 2026-06-12 | 2026-06-12 | 2026-06-18 | 2026-07-24 | 2026-07-24 | 2026-08-20 | 2026-08-07 | 2026-08-07 |  | Completed | Completed | Completed | Overdue
ZWP-23 | Report / Documents | MM-ZTK-1F-GEN-STR-MR-0005 | MATERIAL REQUISITION FOR LAUNCH TIMBER | 0% | 0% | 50% | 50% | 0.2 | 2026-05-15 | 2026-05-15 | 2026-05-08 | 2026-06-26 | 2026-06-26 | 2026-06-18 | 2026-08-07 | 2026-08-07 | 2026-07-01 | 2026-08-21 | 2026-08-21 | 2026-07-20 | Completed | Completed | Completed | Completed
ZWP-23 | Report / Documents | MM-ZTK-1F-ZWP23-COR-CAL-0001 | ZWP23 CATHODIC PROTECTION DESIGN REPORT | 0% | 0% | 50% | 50% | 0.5 | 2026-07-10 | 2026-07-10 | 2026-05-29 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-10-02 | 2026-10-02 |  | 2026-10-16 | 2026-10-16 |  | Completed | Completed
ZWP-23 | Report / Documents | MM-ZTK-1F-ZWP23-STR-CAL-2801 | ZWP23 JACKET RISER CLAMP DESIGN | 0% | 0% | 50% | 50% |  | 2026-11-04 | 2026-11-04 |  | 2026-12-16 | 2026-12-16 |  | 2027-01-27 | 2027-01-27 |  | 2027-02-10 | 2027-02-10
ZWP-23 | Report / Documents | MM-ZTK-1F-ZWP23-WCR-CAL-2101 | ZWP23 WEIGHT CONTROL REPORT (AS-BUILT) | 0% | 0% | 0% | 0% | 0.2
ZWP-23 | Report / Documents | MM-ZTK-1F-ZWP23-STR-CAL-2101 | ZWP23 COMPUTER MODELLING AND LOAD FORMULATION REPORT (AS-BUILT) | 0% | 0% | 0% | 0% | 0.4
ZWP-23 | Report / Documents | MM-ZTK-1F-ZWP23-STR-CAL-2150 | ZWP23 CONSTRUCTION MODEL REPORT (AS-BUILT) | 0% | 0% | 0% | 0% | 0.4
ZWP-22 | Report / Documents | MM-ZTK-1F-GEN-ZTR-SPE-2001 | SPECIFICATION FOR GROUT SEALS AND DIAPHRAGM | 100% | 100% | 100% | 0% | 0.2 | 2026-04-03 | 2026-04-03 | 2026-04-03 | 2026-05-15 | 2026-05-15 | 2026-06-18 | 2026-06-26 | 2026-06-26 | 2026-07-16 | 2026-07-10 | 2026-07-10 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-22 | Report / Documents | MM-ZTK-1F-GEN-ZTR-SPE-2002 | SPECIFICATION FOR STAINLESS STEEL BUNDLES | 100% | 100% | 100% | 0% | 0.2 | 2026-04-03 | 2026-04-03 | 2026-04-03 | 2026-05-15 | 2026-05-15 | 2026-05-29 | 2026-06-26 | 2026-06-26 | 2026-06-26 | 2026-07-10 | 2026-07-10 | 2026-07-01 | Completed | Completed | Completed | Completed
ZWP-22 | Report / Documents | MM-ZTK-1F-GEN-ZTR-SPE-2003 | SPECIFICATIONS FOR GRIPPER PERFORMANCE | 100% | 100% | 100% | 0% | 0.2 | 2026-04-03 | 2026-04-03 | 2026-04-03 | 2026-05-15 | 2026-05-15 | 2026-05-29 | 2026-06-26 | 2026-06-26 | 2026-07-16 | 2026-07-10 | 2026-07-10 | 2026-07-30 | Completed | Completed | Completed | Completed
ZWP-22 | Report / Documents | MM-ZTK-1F-GEN-ZTR-SPE-2004 | SPECIFICATION FOR GROUTING AND INSTALLATION | 100% | 100% | 70% | -30% | 0.2 | 2026-04-03 | 2026-04-03 | 2026-04-03 | 2026-05-15 | 2026-05-15 | 2026-05-29 | 2026-06-26 | 2026-06-26 |  | 2026-07-10 | 2026-07-10 |  | Completed | Completed | Overdue | Overdue
ZWP-22 | Report / Documents | MM-ZTK-1F-GEN-ZTK-SPE-2005 | SPECIFICATION FOR HYDRAULIC DRIVEN FLOODING SYSTEMS | 100% | 100% | 100% | 0% | 0.2 | 2026-04-03 | 2026-04-03 | 2026-04-03 | 2026-05-15 | 2026-05-15 | 2026-06-26 | 2026-06-26 | 2026-06-26 | 2026-07-01 | 2026-07-10 | 2026-07-10 | 2026-07-10 | Completed | Completed | Completed | Completed
ZWP-22 | Report / Documents | MM-ZTK-1F-ZWP22-STR-CAL-2001 | ZWP22 JACKET COMPUTER MODELING AND LOAD FORMULATION | 80% | 80% | 70% | -10% | 0.5 | 2026-06-05 | 2026-06-05 | 2026-05-19 | 2026-07-17 | 2026-07-17 | 2026-08-28 | 2026-08-28 | 2026-08-28 |  | 2026-09-11 | 2026-09-11 |  | Completed | Completed | Overdue | Follow-Next Week
ZWP-22 | Report / Documents | MM-ZTK-1F-ZWP22-STR-CAL-2011 | ZWP22 JACKET IN-PLACE ANALYSIS | 70% | 70% | 70% | 0% | 0.5 | 2026-06-19 | 2026-06-19 | 2026-06-29 | 2026-07-31 | 2026-07-31 | 2026-08-14 | 2026-09-11 | 2026-09-11 |  | 2026-09-25 | 2026-09-25 |  | Completed | Completed | Follow-Next Week
ZWP-22 | Report / Documents | MM-ZTK-1F-ZWP22-STR-CAL-2012 | ZWP22 JACKET DYNAMIC ANALYSIS | 70% | 70% | 70% | 0% | 0.5 | 2026-06-26 | 2026-06-26 | 2026-06-02 | 2026-08-07 | 2026-08-07 | 2026-08-07 | 2026-09-18 | 2026-09-18 |  | 2026-10-02 | 2026-10-02 |  | Completed | Completed
ZWP-22 | Report / Documents | MM-ZTK-1F-ZWP22-STR-CAL-2014 | ZWP22 JACKET LOADOUT ANALYSIS | 70% | 70% | 70% | 0% | 0.5 | 2026-07-03 | 2026-07-03 | 2026-05-19 | 2026-08-14 | 2026-08-14 | 2026-08-07 | 2026-09-25 | 2026-09-25 |  | 2026-10-09 | 2026-10-09 |  | Completed | Completed
ZWP-22 | Report / Documents | MM-ZTK-1F-ZWP22-STR-CAL-2015 | ZWP22 JACKET TRANSPORTATION ANALYSIS | 70% | 70% | 70% | 0% | 0.5 | 2026-07-17 | 2026-07-17 | 2026-05-19 | 2026-08-28 | 2026-08-28 | 2026-08-18 | 2026-10-09 | 2026-10-09 |  | 2026-10-23 | 2026-10-23 |  | Completed | Completed
ZWP-22 | Report / Documents | MM-ZTK-1F-ZWP22-STR-CAL-2016 | ZWP22 JACKET TRANSPORTATION FATIGUE | 50% | 50% | 70% | 20% | 0.5 | 2026-07-31 | 2026-07-31 | 2026-08-03 | 2026-09-11 | 2026-09-11 | 2026-08-21 | 2026-10-23 | 2026-10-23 |  | 2026-11-06 | 2026-11-06 |  | Completed | Completed
ZWP-22 | Report / Documents | MM-ZTK-1F-ZWP22-STR-CAL-2017 | ZWP22 JACKET BOAT IMPACT ANALYSIS | 50% | 50% | 70% | 20% | 0.5 | 2026-08-14 | 2026-08-14 | 2026-07-24 | 2026-09-25 | 2026-09-25 | 2026-08-14 | 2026-11-06 | 2026-11-06 |  | 2026-11-20 | 2026-11-20 |  | Completed | Completed
ZWP-22 | Report / Documents | MM-ZTK-1F-ZWP22-STR-CAL-2018 | ZWP22 JACKET ON-BOTTOM STABILITY ANALYSIS | 70% | 70% | 70% | 0% | 0.5 | 2026-07-10 | 2026-07-10 | 2026-08-03 | 2026-08-21 | 2026-08-21 | 2026-08-14 | 2026-10-02 | 2026-10-02 |  | 2026-10-16 | 2026-10-16 |  | Completed | Completed
ZWP-22 | Report / Documents | MM-ZTK-1F-ZWP22-STR-CAL-2019 | ZWP22 JACKET MISCELLANEOUS DESIGN | 50% | 50% | 50% | 0% | 0.75 | 2026-08-10 | 2026-08-10 | 2026-07-23 | 2026-09-21 | 2026-09-21 |  | 2026-11-02 | 2026-11-02 |  | 2026-11-16 | 2026-11-16 |  | Completed
ZWP-22 | Report / Documents | MM-ZTK-1F-ZWP22-STR-CAL-2020 | ZWP22 JACKET LEVELLING ANALYSIS | 50% | 50% | 0% | -50% | 0.5 | 2026-08-28 | 2026-08-28 |  | 2026-10-09 | 2026-10-09 |  | 2026-11-20 | 2026-11-20 |  | 2026-12-04 | 2026-12-04 |  | Overdue
ZWP-22 | Report / Documents | MM-ZTK-1F-ZWP22-STR-CAL-2021 | ZWP22 JACKET PILE HANDLING AND STICK-UP ANALYSIS | 70% | 70% | 50% | -20% | 0.5 | 2026-07-03 | 2026-07-03 | 2026-08-21 | 2026-08-14 | 2026-08-14 |  | 2026-09-25 | 2026-09-25 |  | 2026-10-09 | 2026-10-09 |  | Completed | Overdue
ZWP-22 | Report / Documents | MM-ZTK-1F-ZWP22-STR-CAL-2022 | ZWP22 PILE DRIVEABILITY AND PILE FATIGUE ANALYSIS | 70% | 70% | 50% | -20% | 0.5 | 2026-07-10 | 2026-07-10 | 2026-08-14 | 2026-08-21 | 2026-08-21 |  | 2026-10-02 | 2026-10-02 |  | 2026-10-16 | 2026-10-16 |  | Completed | Overdue
ZWP-22 | Report / Documents | MM-ZTK-1F-ZWP22-STR-CAL-2023 | ZWP22 JACKET PILE CLUSTER AND SKIRT PILE SLEEVE DESIGN WITH FEA | 0% | 0% | 50% | 50% | 0.8 | 2026-09-18 | 2026-09-18 | 2026-08-28 | 2026-10-30 | 2026-10-30 |  | 2026-12-11 | 2026-12-11 |  | 2026-12-25 | 2026-12-25 |  | Completed
ZWP-22 | Report / Documents | MM-ZTK-1F-ZWP22-STR-CAL-2024 | ZWP22 PILE GROUP EFFECT ANALYSIS | 0% | 0% | 70% | 70% | 0.8 | 2026-10-02 | 2026-10-02 | 2026-07-23 | 2026-11-13 | 2026-11-13 | 2026-08-14 | 2026-12-25 | 2026-12-25 |  | 2027-01-08 | 2027-01-08 |  | Completed | Completed
ZWP-22 | Report / Documents | MM-ZTK-1F-ZWP22-STR-CAL-2025 | ZWP22 MUDMAT FEA ANALYSIS | 0% | 0% | 0% | 0% | 0.8 | 2026-10-10 | 2026-10-10 |  | 2026-11-21 | 2026-11-21 |  | 2027-01-02 | 2027-01-02 |  | 2027-01-16 | 2027-01-16
ZWP-22 | Report / Documents | MM-ZTK-1F-ZWP22-STR-CAL-2026 | ZWP23 JACKET PILE TRANSPORTATION FATIGUE | 0% | 0% | 0% | 0% | 0.5 | 2026-12-02 | 2026-12-02 |  | 2027-01-13 | 2027-01-13 |  | 2027-02-24 | 2027-02-24 |  | 2027-03-10 | 2027-03-10
ZWP-22 | Report / Documents | MM-ZTK-1F-ZWP22-STR-CAL-2041 | ZWP22 JACKET PUSHOVER ANALYSIS | 50% | 50% | 0% | -50% | 0.5 | 2026-07-24 | 2026-07-24 |  | 2026-09-04 | 2026-09-04 |  | 2026-10-16 | 2026-10-16 |  | 2026-10-30 | 2026-10-30 |  | Overdue | Follow-This Week
ZWP-22 | Report / Documents | MM-ZTK-1F-ZWP22-STR-CAL-2050 | ZWP22 JACKET CONSTRUCTION MODEL REPORT | 0% | 0% | 70% | 70% | 0.5 | 2026-09-18 | 2026-09-18 | 2026-05-19 | 2026-10-30 | 2026-10-30 | 2026-08-28 | 2026-12-11 | 2026-12-11 |  | 2026-12-25 | 2026-12-25 |  | Completed | Completed
ZWP-22 | Report / Documents | MM-ZTK-1F-ZWP22-NVA-CAL-2011 | ZWP22 JACKET BARGE MOTION ANALYSIS | 70% | 70% | 50% | -20% | 0.55 | 2026-07-17 | 2026-07-17 | 2026-08-21 | 2026-08-28 | 2026-08-28 |  | 2026-10-09 | 2026-10-09 |  | 2026-10-23 | 2026-10-23 |  | Completed | Overdue
ZWP-22 | Report / Documents | MM-ZTK-1F-ZWP22-NVA-CAL-2012 | ZWP22 JACKET LAUNCH ANALYSIS REPORT | 50% | 50% | 70% | 20% | 0.55 | 2026-07-24 | 2026-07-24 | 2026-06-02 | 2026-09-04 | 2026-09-04 | 2026-08-21 | 2026-10-16 | 2026-10-16 |  | 2026-10-30 | 2026-10-30 |  | Completed | Completed
ZWP-22 | Report / Documents | MM-ZTK-1F-ZWP22-NVA-CAL-2013 | ZWP22 JACKER FREE FLOATATION AND UPENDING ANALYSIS REPORT | 50% | 50% | 70% | 20% | 0.75 | 2026-08-14 | 2026-08-14 | 2026-08-14 | 2026-09-25 | 2026-09-25 | 2026-08-18 | 2026-11-06 | 2026-11-06 |  | 2026-11-20 | 2026-11-20 |  | Completed | Completed
ZWP-22 | Report / Documents | MM-ZTK-1F-ZWP22-STR-WCR-2001 | ZWP22 JACKET WEIGHT CONTROL REPORT | 80% | 80% | 70% | -10% | 1 | 2026-05-29 | 2026-05-29 | 2026-04-18 | 2026-07-10 | 2026-07-10 | 2026-07-27 | 2026-08-21 | 2026-08-21 |  | 2026-09-04 | 2026-09-04 |  | Completed | Completed | Overdue | Follow-This Week
ZWP-22 | Report / Documents | MM-ZTK-1F-ZWP22-STR-MTO-2001 | ZWP22 JACKET PRIMARY STEEL MTO REPORT | 50% | 50% | 70% | 20% | 0.5 | 2026-07-31 | 2026-07-31 | 2026-07-27 | 2026-09-11 | 2026-09-11 | 2026-08-14 | 2026-10-23 | 2026-10-23 |  | 2026-11-06 | 2026-11-06 |  | Completed | Completed
ZWP-22 | Report / Documents | MM-ZTK-1F-ZWP22-STR-MTO-2002 | ZWP22 JACKET SECONDARY STEEL MTO REPORT | 50% | 50% | 70% | 20% | 0.5 | 2026-08-07 | 2026-08-07 | 2026-07-27 | 2026-09-18 | 2026-09-18 | 2026-08-14 | 2026-10-30 | 2026-10-30 |  | 2026-11-13 | 2026-11-13 |  | Completed | Completed
ZWP-22 | Report / Documents | MM-ZTK-1F-ZWP22-STR-MR-2001 | MATERIAL REQUISITION FOR ZWP22 JACKET PRIMARY TUBULAR STEEL | 100% | 100% | 70% | -30% | 0.4 | 2026-04-10 | 2026-04-10 | 2026-04-03 | 2026-05-22 | 2026-05-22 | 2026-06-18 | 2026-07-03 | 2026-07-03 |  | 2026-07-17 | 2026-07-17 |  | Completed | Completed | Overdue | Overdue
ZWP-22 | Report / Documents | MM-ZTK-1F-ZWP22-STR-MR-2002 | MATERIAL REQUISITION FOR ZWP22 JACKET PRIMARY STEEL (PLATE) | 100% | 100% | 70% | -30% | 0.4 | 2026-04-17 | 2026-04-17 | 2026-04-30 | 2026-05-29 | 2026-05-29 | 2026-06-18 | 2026-07-10 | 2026-07-10 |  | 2026-07-24 | 2026-07-24 |  | Completed | Completed | Overdue | Overdue
ZWP-22 | Report / Documents | MM-ZTK-1F-ZWP22-STR-MR-2003 | MATERIAL REQUISITION FOR ZWP22 JACKET SECONDARY AND TERTIARY STEEL |  |  |  |  | 0.2 | 2026-04-30 | 2026-04-30 | 2026-08-14 | 2026-06-11 | 2026-06-11 | 2026-08-14 | 2026-07-23 | 2026-07-23 | 2026-08-14 | 2026-08-06 | 2026-08-06 | 2026-08-14 | Completed | Completed | Completed | Completed
ZWP-22 | Report / Documents | MM-ZTK-1F-ZWP22-STR-MR-2003 | MATERIAL REQUISITION FOR ZWP22 JACKET MISCELLANEOUS STEEL | 100% | 100% | 0% | -100% |  | 2026-04-30 | 2026-04-30 |  | 2026-06-11 | 2026-06-11 |  | 2026-07-23 | 2026-07-23 |  | 2026-08-06 | 2026-08-06 |  | Overdue | Overdue | Overdue | Overdue
ZWP-22 | Report / Documents | MM-ZTK-1F-GEN-STR-MR-0001 | MATERIAL REQUISITION FOR PILE GRIPPER WITH INTEGRAL DIAPHRAGM CLOSURE | 0% | 0% | 50% | 50% | 0.2 | 2026-05-15 | 2026-05-15 | 2026-05-08 | 2026-06-26 | 2026-06-26 | 2026-06-18 | 2026-08-07 | 2026-08-07 | 2026-07-24 | 2026-08-21 | 2026-08-21 | 2026-08-05 | Completed | Completed | Completed | Completed
ZWP-22 | Report / Documents | MM-ZTK-1F-GEN-STR-MR-0002 | MATERIAL REQUISITION FOR GROUT SEALS AND DIAPHRAGM CLOSURE | 0% | 0% | 50% | 50% | 0.2 | 2026-05-15 | 2026-05-15 | 2026-05-08 | 2026-06-26 | 2026-06-26 | 2026-06-18 | 2026-08-07 | 2026-08-07 | 2026-07-24 | 2026-08-21 | 2026-08-21 | 2026-08-05 | Completed | Completed | Completed | Completed
ZWP-22 | Report / Documents | MM-ZTK-1F-GEN-STR-MR-0003 | MATERIAL REQUISITION FOR BARGE BUMPER | 50% | 50% | 50% | 0% | 0.2 | 2026-05-01 | 2026-05-01 | 2026-04-30 | 2026-06-12 | 2026-06-12 | 2026-06-18 | 2026-07-24 | 2026-07-24 | 2026-06-29 | 2026-08-07 | 2026-08-07 | 2026-07-06 | Completed | Completed | Completed | Completed
ZWP-22 | Report / Documents | MM-ZTK-1F-GEN-STR-MR-0004 | MATERIAL REQUISITION FOR ANODE | 50% | 50% | 50% | 0% | 0.2 | 2026-05-01 | 2026-05-01 | 2026-04-30 | 2026-06-12 | 2026-06-12 | 2026-06-18 | 2026-07-24 | 2026-07-24 | 2026-08-20 | 2026-08-07 | 2026-08-07 |  | Completed | Completed | Completed | Overdue
ZWP-22 | Report / Documents | MM-ZTK-1F-GEN-STR-MR-0005 | MATERIAL REQUISITION FOR LAUNCH TIMBER | 0% | 0% | 50% | 50% | 0.2 | 2026-05-15 | 2026-05-15 | 2026-05-08 | 2026-06-26 | 2026-06-26 | 2026-06-18 | 2026-08-07 | 2026-08-07 | 2026-07-01 | 2026-08-21 | 2026-08-21 | 2026-07-20 | Completed | Completed | Completed | Completed
ZWP-22 | Report / Documents | MM-ZTK-1F-ZWP22-COR-CAL-0001 | ZWP22 CATHODIC PROTECTION DESIGN REPORT | 0% | 0% | 50% | 50% | 0.5 | 2026-08-07 | 2026-08-07 | 2026-05-29 | 2026-09-18 | 2026-09-18 | 2026-08-28 | 2026-10-30 | 2026-10-30 |  | 2026-11-13 | 2026-11-13 |  | Completed | Completed
ZWP-22 | Report / Documents | MM-ZTK-1F-ZWP22-STR-CAL-2801 | ZWP22 JACKET RISER CLAMP DESIGN | 0% | 0% | 50% | 50% |  | 2026-12-02 | 2026-12-02 |  | 2027-01-13 | 2027-01-13 |  | 2027-02-24 | 2027-01-27 |  | 2027-03-10 | 2027-02-10
ZWP-22 | Report / Documents | MM-ZTK-1F-ZWP22-WCR-CAL-2101 | ZWP22 WEIGHT CONTROL REPORT (AS-BUILT) | 0% | 0% | 0% | 0% | 0.2
ZWP-22 | Report / Documents | MM-ZTK-1F-ZWP22-STR-CAL-2101 | ZWP22 COMPUTER MODELLING AND LOAD FORMULATION REPORT (AS-BUILT) | 0% | 0% | 0% | 0% | 0.4
ZWP-22 | Report / Documents | MM-ZTK-1F-ZWP22-STR-CAL-2150 | ZWP22 CONSTRUCTION MODEL REPORT (AS-BUILT) | 0% | 0% | 0% | 0% | 0.4
ZWP-20 | Report / Documents | MM-ZTK-1F-GEN-ZTR-SPE-2001 | SPECIFICATION FOR GROUT SEALS AND DIAPHRAGM | 100% | 100% | 100% | 0% | 0.2 | 2026-04-03 | 2026-04-03 | 2026-04-03 | 2026-05-15 | 2026-05-15 | 2026-06-18 | 2026-06-26 | 2026-06-26 | 2026-07-16 | 2026-07-10 | 2026-07-10 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-20 | Report / Documents | MM-ZTK-1F-GEN-ZTR-SPE-2002 | SPECIFICATION FOR STAINLESS STEEL BUNDLES | 100% | 100% | 100% | 0% | 0.2 | 2026-04-03 | 2026-04-03 | 2026-04-03 | 2026-05-15 | 2026-05-15 | 2026-05-29 | 2026-06-26 | 2026-06-26 | 2026-06-26 | 2026-07-10 | 2026-07-10 | 2026-07-01 | Completed | Completed | Completed | Completed
ZWP-20 | Report / Documents | MM-ZTK-1F-GEN-ZTR-SPE-2003 | SPECIFICATIONS FOR GRIPPER PERFORMANCE | 100% | 100% | 100% | 0% | 0.2 | 2026-04-03 | 2026-04-03 | 2026-04-03 | 2026-05-15 | 2026-05-15 | 2026-05-29 | 2026-06-26 | 2026-06-26 | 2026-07-16 | 2026-07-10 | 2026-07-10 | 2026-07-30 | Completed | Completed | Completed | Completed
ZWP-20 | Report / Documents | MM-ZTK-1F-GEN-ZTR-SPE-2004 | SPECIFICATION FOR GROUTING AND INSTALLATION | 100% | 100% | 70% | -30% | 0.2 | 2026-04-03 | 2026-04-03 | 2026-04-03 | 2026-05-15 | 2026-05-15 | 2026-05-29 | 2026-06-26 | 2026-06-26 |  | 2026-07-10 | 2026-07-10 |  | Completed | Completed | Overdue | Overdue
ZWP-20 | Report / Documents | MM-ZTK-1F-GEN-ZTK-SPE-2005 | SPECIFICATION FOR HYDRAULIC DRIVEN FLOODING SYSTEMS | 100% | 100% | 100% | 0% | 0.2 | 2026-04-03 | 2026-04-03 | 2026-04-03 | 2026-05-15 | 2026-05-15 | 2026-06-26 | 2026-06-26 | 2026-06-26 | 2026-07-01 | 2026-07-10 | 2026-07-10 | 2026-07-10 | Completed | Completed | Completed | Completed
ZWP-20 | Report / Documents | MM-ZTK-1F-ZWP20-STR-CAL-2001 | ZWP20 JACKET COMPUTER MODELING AND LOAD FORMULATION | 70% | 70% | 50% | -20% | 0.5 | 2026-07-03 | 2026-07-03 | 2026-05-20 | 2026-08-14 | 2026-08-14 |  | 2026-09-25 | 2026-09-25 |  | 2026-10-09 | 2026-10-09 |  | Completed | Overdue
ZWP-20 | Report / Documents | MM-ZTK-1F-ZWP20-STR-CAL-2011 | ZWP20 JACKET IN-PLACE ANALYSIS | 70% | 70% | 50% | -20% | 0.5 | 2026-07-17 | 2026-07-17 | 2026-08-03 | 2026-08-28 | 2026-08-28 |  | 2026-10-09 | 2026-10-09 |  | 2026-10-23 | 2026-10-23 |  | Completed | Overdue
ZWP-20 | Report / Documents | MM-ZTK-1F-ZWP20-STR-CAL-2012 | ZWP20 JACKET DYNAMIC ANALYSIS | 50% | 50% | 70% | 20% | 0.5 | 2026-07-24 | 2026-07-24 | 2026-06-02 | 2026-09-04 | 2026-09-04 | 2026-08-28 | 2026-10-16 | 2026-10-16 |  | 2026-10-30 | 2026-10-30 |  | Completed | Completed
ZWP-20 | Report / Documents | MM-ZTK-1F-ZWP20-STR-CAL-2014 | ZWP20 JACKET LOADOUT ANALYSIS | 50% | 50% | 50% | 0% | 0.5 | 2026-07-31 | 2026-07-31 | 2026-06-02 | 2026-09-11 | 2026-09-11 |  | 2026-10-23 | 2026-10-23 |  | 2026-11-06 | 2026-11-06 |  | Completed | Follow-Next Week
ZWP-20 | Report / Documents | MM-ZTK-1F-ZWP20-STR-CAL-2015 | ZWP20 JACKET TRANSPORTATION ANALYSIS | 50% | 50% | 50% | 0% | 0.5 | 2026-08-14 | 2026-08-14 | 2026-05-20 | 2026-09-25 | 2026-09-25 |  | 2026-11-06 | 2026-11-06 |  | 2026-11-20 | 2026-11-20 |  | Completed
ZWP-20 | Report / Documents | MM-ZTK-1F-ZWP20-STR-CAL-2016 | ZWP20 JACKET TRANSPORTATION FATIGUE | 50% | 50% | 50% | 0% | 0.5 | 2026-08-28 | 2026-08-28 | 2026-08-20 | 2026-10-09 | 2026-10-09 |  | 2026-11-20 | 2026-11-20 |  | 2026-12-04 | 2026-12-04 |  | Completed
ZWP-20 | Report / Documents | MM-ZTK-1F-ZWP20-STR-CAL-2017 | ZWP20 JACKET BOAT IMPACT ANALYSIS | 0% | 0% | 50% | 50% | 0.5 | 2026-09-11 | 2026-09-11 | 2026-08-21 | 2026-10-23 | 2026-10-23 |  | 2026-12-04 | 2026-12-04 |  | 2026-12-18 | 2026-12-18 |  | Completed
ZWP-20 | Report / Documents | MM-ZTK-1F-ZWP20-STR-CAL-2018 | ZWP20 JACKET ON-BOTTOM STABILITY ANALYSIS | 50% | 50% | 70% | 20% | 0.5 | 2026-08-07 | 2026-08-07 | 2026-08-07 | 2026-09-18 | 2026-09-18 | 2026-08-14 | 2026-10-30 | 2026-10-30 |  | 2026-11-13 | 2026-11-13 |  | Completed | Completed
ZWP-20 | Report / Documents | MM-ZTK-1F-ZWP20-STR-CAL-2019 | ZWP20 JACKET MISCELLANEOUS DESIGN | 0% | 0% | 50% | 50% | 0.75 | 2026-09-07 | 2026-09-07 | 2026-08-07 | 2026-10-12 | 2026-10-12 |  | 2026-11-23 | 2026-11-23 |  | 2026-12-07 | 2026-12-07 |  | Completed
ZWP-20 | Report / Documents | MM-ZTK-1F-ZWP20-STR-CAL-2020 | ZWP20 JACKET LEVELLING ANALYSIS | 0% | 0% | 0% | 0% | 0.5 | 2026-09-25 | 2026-09-25 |  | 2026-11-06 | 2026-11-06 |  | 2026-12-18 | 2026-12-18 |  | 2027-01-01 | 2027-01-01
ZWP-20 | Report / Documents | MM-ZTK-1F-ZWP20-STR-CAL-2021 | ZWP20 JACKET PILE HANDLING AND STICK-UP ANALYSIS | 50% | 50% | 50% | 0% | 0.5 | 2026-07-31 | 2026-07-31 | 2026-08-21 | 2026-09-11 | 2026-09-11 |  | 2026-10-23 | 2026-10-23 |  | 2026-11-06 | 2026-11-06 |  | Completed | Follow-Next Week
ZWP-20 | Report / Documents | MM-ZTK-1F-ZWP20-STR-CAL-2022 | ZWP20 PILE DRIVEABILITY AND PILE FATIGUE ANALYSIS | 50% | 50% | 50% | 0% | 0.5 | 2026-08-07 | 2026-08-07 | 2026-08-21 | 2026-09-18 | 2026-09-18 |  | 2026-10-30 | 2026-10-30 |  | 2026-11-13 | 2026-11-13 |  | Completed
ZWP-20 | Report / Documents | MM-ZTK-1F-ZWP20-STR-CAL-2023 | ZWP20 JACKET PILE CLUSTER AND SKIRT PILE SLEEVE DESIGN WITH FEA | 0% | 0% | 0% | 0% | 0.8 | 2026-10-16 | 2026-10-16 |  | 2026-11-27 | 2026-11-27 |  | 2027-01-08 | 2027-01-08 |  | 2027-01-22 | 2027-01-22
ZWP-20 | Report / Documents | MM-ZTK-1F-ZWP20-STR-CAL-2024 | ZWP20 PILE GROUP EFFECT ANALYSIS | 0% | 0% | 50% | 50% | 0.8 | 2026-10-30 | 2026-10-30 | 2026-08-20 | 2026-12-11 | 2026-12-11 |  | 2027-01-22 | 2027-01-22 |  | 2027-02-05 | 2027-02-05 |  | Completed
ZWP-20 | Report / Documents | MM-ZTK-1F-ZWP20-STR-CAL-2025 | ZWP20 MUDMAT FEA ANALYSIS | 0% | 0% | 0% | 0% | 0.8 | 2026-11-07 | 2026-11-07 |  | 2026-12-19 | 2026-12-19 |  | 2027-01-30 | 2027-01-30 |  | 2027-02-13 | 2027-02-13
ZWP-20 | Report / Documents | MM-ZTK-1F-ZWP20-STR-CAL-2026 | ZWP20 JACKET PILE TRANSPORTATION FATIGUE | 0% | 0% | 0% | 0% | 0.5 | 2026-12-30 | 2026-12-30 |  | 2027-02-10 | 2027-02-10 |  | 2027-03-24 | 2027-03-24 |  | 2027-04-07 | 2027-04-07
ZWP-20 | Report / Documents | MM-ZTK-1F-ZWP20-STR-CAL-2041 | ZWP20 JACKET PUSHOVER ANALYSIS | 50% | 50% | 0% | -50% | 0.5 | 2026-08-21 | 2026-08-21 |  | 2026-10-02 | 2026-10-02 |  | 2026-11-13 | 2026-11-13 |  | 2026-11-27 | 2026-11-27 |  | Overdue
ZWP-20 | Report / Documents | MM-ZTK-1F-ZWP20-STR-CAL-2050 | ZWP20 JACKET CONSTRUCTION MODEL REPORT | 0% | 0% | 50% | 50% | 0.5 | 2026-10-16 | 2026-10-16 | 2026-05-20 | 2026-11-27 | 2026-11-27 |  | 2027-01-08 | 2027-01-08 |  | 2027-01-22 | 2027-01-22 |  | Completed
ZWP-20 | Report / Documents | MM-ZTK-1F-ZWP20-NVA-CAL-2011 | ZWP20 JACKET BARGE MOTION ANALYSIS | 50% | 50% | 0% | -50% | 0.55 | 2026-08-14 | 2026-08-14 |  | 2026-09-25 | 2026-09-25 |  | 2026-11-06 | 2026-11-06 |  | 2026-11-20 | 2026-11-20 |  | Overdue
ZWP-20 | Report / Documents | MM-ZTK-1F-ZWP20-NVA-CAL-2012 | ZWP20 JACKET LAUNCH ANALYSIS REPORT | 50% | 50% | 50% | 0% | 0.55 | 2026-08-21 | 2026-08-21 | 2026-06-15 | 2026-10-02 | 2026-10-02 |  | 2026-11-13 | 2026-11-13 |  | 2026-11-27 | 2026-11-27 |  | Completed
ZWP-20 | Report / Documents | MM-ZTK-1F-ZWP20-NVA-CAL-2013 | ZWP20 JACKER FREE FLOATATION AND UPENDING ANALYSIS REPORT | 0% | 0% | 0% | 0% | 0.75 | 2026-09-11 | 2026-09-11 |  | 2026-10-23 | 2026-10-23 |  | 2026-12-04 | 2026-12-04 |  | 2026-12-18 | 2026-12-18 |  | Follow-Next Week
ZWP-20 | Report / Documents | MM-ZTK-1F-ZWP20-STR-WCR-2001 | ZWP20 JACKET WEIGHT CONTROL REPORT | 70% | 70% | 70% | 0% | 1 | 2026-06-26 | 2026-06-26 | 2026-04-18 | 2026-08-07 | 2026-08-07 | 2026-08-21 | 2026-09-18 | 2026-09-18 |  | 2026-10-02 | 2026-10-02 |  | Completed | Completed
ZWP-20 | Report / Documents | MM-ZTK-1F-ZWP20-STR-MTO-2001 | ZWP20 JACKET PRIMARY STEEL MTO REPORT | 50% | 50% | 50% | 0% | 0.5 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-10-09 | 2026-10-09 |  | 2026-11-20 | 2026-11-20 |  | 2026-12-04 | 2026-12-04 |  | Completed
ZWP-20 | Report / Documents | MM-ZTK-1F-ZWP20-STR-MTO-2002 | ZWP20 JACKET SECONDARY STEEL MTO REPORT | 0% | 0% | 50% | 50% | 0.5 | 2026-09-04 | 2026-09-04 | 2026-08-28 | 2026-10-16 | 2026-10-16 |  | 2026-11-27 | 2026-11-27 |  | 2026-12-11 | 2026-12-11 |  | Completed
ZWP-20 | Report / Documents | MM-ZTK-1F-ZWP20-STR-MR-2001 | MATERIAL REQUISITION FOR ZWP20 JACKET PRIMARY TUBULAR STEEL | 100% | 100% | 50% | -50% | 0.4 | 2026-04-10 | 2026-04-10 | 2026-04-03 | 2026-05-22 | 2026-05-22 |  | 2026-07-03 | 2026-07-03 |  | 2026-07-17 | 2026-07-17 |  | Completed | Overdue | Overdue | Overdue
ZWP-20 | Report / Documents | MM-ZTK-1F-ZWP20-STR-MR-2002 | MATERIAL REQUISITION FOR ZWP20 JACKET PRIMARY STEEL (PLATE) | 100% | 100% | 70% | -30% | 0.4 | 2026-04-17 | 2026-04-17 | 2026-04-30 | 2026-05-29 | 2026-05-29 | 2026-06-18 | 2026-07-10 | 2026-07-10 |  | 2026-07-24 | 2026-07-24 |  | Completed | Completed | Overdue | Overdue
ZWP-20 | Report / Documents | MM-ZTK-1F-ZWP20-STR-MR-2003 | MATERIAL REQUISITION FOR ZWP20 JACKET SECONDARY AND TERTIARY STEEL |  |  |  |  | 0.2 | 2026-04-30 | 2026-04-30 | 2026-08-14 | 2026-06-11 | 2026-06-11 | 2026-08-14 | 2026-07-23 | 2026-07-23 | 2026-08-14 | 2026-08-06 | 2026-08-06 | 2026-08-14 | Completed | Completed | Completed | Completed
ZWP-20 | Report / Documents | MM-ZTK-1F-ZWP20-STR-MR-2003 | MATERIAL REQUISITION FOR ZWP20 JACKETMISCELLANEOUS STEEL | 100% | 100% | 0% | -100% |  | 2026-04-30 | 2026-04-30 |  | 2026-06-11 | 2026-06-11 |  | 2026-07-23 | 2026-07-23 |  | 2026-08-06 | 2026-08-06 |  | Overdue | Overdue | Overdue | Overdue
ZWP-20 | Report / Documents | MM-ZTK-1F-GEN-STR-MR-0001 | MATERIAL REQUISITION FOR PILE GRIPPER WITH INTEGRAL DIAPHRAGM CLOSURE | 0% | 0% | 50% | 50% | 0.2 | 2026-05-15 | 2026-05-15 | 2026-05-08 | 2026-06-26 | 2026-06-26 | 2026-06-18 | 2026-08-07 | 2026-08-07 | 2026-07-24 | 2026-08-21 | 2026-08-21 | 2026-08-05 | Completed | Completed | Completed | Completed
ZWP-20 | Report / Documents | MM-ZTK-1F-GEN-STR-MR-0002 | MATERIAL REQUISITION FOR GROUT SEALS AND DIAPHRAGM CLOSURE | 0% | 0% | 50% | 50% | 0.2 | 2026-05-15 | 2026-05-15 | 2026-05-08 | 2026-06-26 | 2026-06-26 | 2026-06-18 | 2026-08-07 | 2026-08-07 | 2026-07-24 | 2026-08-21 | 2026-08-21 | 2026-08-05 | Completed | Completed | Completed | Completed
ZWP-20 | Report / Documents | MM-ZTK-1F-GEN-STR-MR-0003 | MATERIAL REQUISITION FOR BARGE BUMPER | 50% | 50% | 50% | 0% | 0.2 | 2026-05-01 | 2026-05-01 | 2026-04-30 | 2026-06-12 | 2026-06-12 | 2026-06-18 | 2026-07-24 | 2026-07-24 | 2026-06-29 | 2026-08-07 | 2026-08-07 | 2026-07-06 | Completed | Completed | Completed | Completed
ZWP-20 | Report / Documents | MM-ZTK-1F-GEN-STR-MR-0004 | MATERIAL REQUISITION FOR ANODE | 50% | 50% | 50% | 0% | 0.2 | 2026-05-01 | 2026-05-01 | 2026-04-30 | 2026-06-12 | 2026-06-12 | 2026-06-18 | 2026-07-24 | 2026-07-24 | 2026-08-20 | 2026-08-07 | 2026-08-07 |  | Completed | Completed | Completed | Overdue
ZWP-20 | Report / Documents | MM-ZTK-1F-GEN-STR-MR-0005 | MATERIAL REQUISITION FOR LAUNCH TIMBER | 0% | 0% | 50% | 50% | 0.2 | 2026-05-15 | 2026-05-15 | 2026-05-08 | 2026-06-26 | 2026-06-26 | 2026-06-18 | 2026-08-07 | 2026-08-07 | 2026-07-01 | 2026-08-21 | 2026-08-21 | 2026-07-20 | Completed | Completed | Completed | Completed
ZWP-20 | Report / Documents | MM-ZTK-1F-ZWP20-COR-CAL-0001 | ZWP20 CATHODIC PROTECTION DESIGN REPORT | 0% | 0% | 50% | 50% | 0.5 | 2026-09-04 | 2026-09-04 | 2026-05-29 | 2026-10-16 | 2026-10-16 | 2026-08-28 | 2026-11-27 | 2026-11-27 |  | 2026-12-11 | 2026-12-11 |  | Completed | Completed
ZWP-20 | Report / Documents | MM-ZTK-1F-ZWP20-STR-CAL-2801 | ZWP20 JACKET RISER CLAMP DESIGN | 0% | 0% | 50% | 50% |  | 2026-12-30 | 2026-12-30 |  | 2027-02-10 | 2027-02-10 |  | 2027-03-24 | 2027-03-24 |  | 2027-04-07 | 2027-04-07
ZWP-20 | Report / Documents | MM-ZTK-1F-ZWP20-WCR-CAL-2101 | ZWP20 WEIGHT CONTROL REPORT (AS-BUILT) | 0% | 0% | 0% | 0% | 0.2
ZWP-20 | Report / Documents | MM-ZTK-1F-ZWP20-STR-CAL-2101 | ZWP20 COMPUTER MODELLING AND LOAD FORMULATION REPORT (AS-BUILT) | 0% | 0% | 0% | 0% | 0.4
ZWP-20 | Report / Documents | MM-ZTK-1F-ZWP20-STR-CAL-2150 | ZWP20 CONSTRUCTION MODEL REPORT (AS-BUILT) | 0% | 0% | 0% | 0% | 0.4
ZWP-21 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-0051 | JACKET - GENERAL NOTES - SHEET 1 | 100% | 100% | 100% | 0% | 0.009 | 2026-05-08 | 2026-05-08 | 2026-06-02 | 2026-06-19 | 2026-06-19 | 2026-06-18 | 2026-07-31 | 2026-07-31 | 2026-08-11 | 2026-08-14 | 2026-08-14 | 2026-08-21 | Completed | Completed | Completed | Completed
ZWP-21 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-0052 | JACKET - GENERAL NOTES - SHEET 2 | 100% | 100% | 100% | 0% | 0.009 | 2026-05-08 | 2026-05-08 | 2026-06-02 | 2026-06-19 | 2026-06-19 | 2026-06-18 | 2026-07-31 | 2026-07-31 | 2026-08-11 | 2026-08-14 | 2026-08-14 | 2026-08-21 | Completed | Completed | Completed | Completed
ZWP-21 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-0061 | JACKET - STANDARD DETAILS WELD PROFILE - SHEET 1 | 100% | 100% | 100% | 0% | 0.047 | 2026-05-08 | 2026-05-08 | 2026-06-02 | 2026-06-19 | 2026-06-19 | 2026-06-18 | 2026-07-31 | 2026-07-31 | 2026-08-11 | 2026-08-14 | 2026-08-14 | 2026-08-21 | Completed | Completed | Completed | Completed
ZWP-21 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-0062 | JACKET - STANDARD DETAILS WELD PROFILE - SHEET 2 | 100% | 100% | 100% | 0% | 0.047 | 2026-05-08 | 2026-05-08 | 2026-06-02 | 2026-06-19 | 2026-06-19 | 2026-06-18 | 2026-07-31 | 2026-07-31 | 2026-08-11 | 2026-08-14 | 2026-08-14 | 2026-08-21 | Completed | Completed | Completed | Completed
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2001 | ZWP21 JACKET - DRAWING INDEX - SHEET 1 | 100% | 100% | 100% | 0% | 0.047 | 2026-05-08 | 2026-05-08 | 2026-06-26 | 2026-06-19 | 2026-06-19 | 2026-06-26 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-08-14 | 2026-08-14 | 2026-08-14 | Completed | Completed | Completed | Completed
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2002 | ZWP21 JACKET - DRAWING INDEX - SHEET 2 | 100% | 100% | 100% | 0% | 0.047 | 2026-05-08 | 2026-05-08 | 2026-06-26 | 2026-06-19 | 2026-06-19 | 2026-06-26 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-08-14 | 2026-08-14 | 2026-08-14 | Completed | Completed | Completed | Completed
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2100 | ZWP21 JACKET - VERTICAL FRAMING ROW 'A' | 100% | 100% | 80% | -20% | 0.047 | 2026-05-08 | 2026-05-08 | 2026-04-18 | 2026-06-19 | 2026-06-19 | 2026-06-25 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-08-14 | 2026-08-14 |  | Completed | Completed | Completed | Overdue
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2101 | ZWP21 JACKET - VERTICAL FRAMING ROW 'B' | 100% | 100% | 80% | -20% | 0.047 | 2026-05-08 | 2026-05-08 | 2026-04-18 | 2026-06-19 | 2026-06-19 | 2026-06-25 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-08-14 | 2026-08-14 |  | Completed | Completed | Completed | Overdue
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2102 | ZWP21 JACKET - VERTICAL FRAMING ROW '1' & '1.1' | 100% | 100% | 80% | -20% | 0.047 | 2026-05-08 | 2026-05-08 | 2026-04-18 | 2026-06-19 | 2026-06-19 | 2026-06-25 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-08-14 | 2026-08-14 |  | Completed | Completed | Completed | Overdue
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2103 | ZWP21 JACKET - VERTICAL FRAMING ROW '2' | 100% | 100% | 80% | -20% | 0.047 | 2026-05-08 | 2026-05-08 | 2026-04-18 | 2026-06-19 | 2026-06-19 | 2026-06-25 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-08-14 | 2026-08-14 |  | Completed | Completed | Completed | Overdue
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2104 | ZWP21 JACKET - VERTICAL FRAMING LAUNCH TRUSS ROW 'Aa' | 100% | 100% | 80% | -20% | 0.047 | 2026-05-08 | 2026-05-08 | 2026-04-18 | 2026-06-19 | 2026-06-19 | 2026-06-25 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-08-14 | 2026-08-14 |  | Completed | Completed | Completed | Overdue
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2105 | ZWP21 JACKET - VERTICAL FRAMING LAUNCH TRUSS ROW 'Bb' | 100% | 100% | 80% | -20% | 0.047 | 2026-05-08 | 2026-05-08 | 2026-04-18 | 2026-06-19 | 2026-06-19 | 2026-06-25 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-08-14 | 2026-08-14 |  | Completed | Completed | Completed | Overdue
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2110 | ZWP21 JACKET - HORIZONTAL FRAMING PLAN AT EL(+) 8000 | 100% | 100% | 80% | -20% | 0.047 | 2026-05-08 | 2026-05-08 | 2026-04-18 | 2026-06-19 | 2026-06-19 | 2026-06-25 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-08-14 | 2026-08-14 |  | Completed | Completed | Completed | Overdue
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2111 | ZWP21 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 3000 | 100% | 100% | 80% | -20% | 0.047 | 2026-05-08 | 2026-05-08 | 2026-04-18 | 2026-06-19 | 2026-06-19 | 2026-06-25 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-08-14 | 2026-08-14 |  | Completed | Completed | Completed | Overdue
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2112 | ZWP21 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 14000 | 100% | 100% | 80% | -20% | 0.047 | 2026-05-08 | 2026-05-08 | 2026-04-18 | 2026-06-19 | 2026-06-19 | 2026-06-25 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-08-14 | 2026-08-14 |  | Completed | Completed | Completed | Overdue
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2113 | ZWP21 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 26000 | 100% | 100% | 80% | -20% | 0.047 | 2026-05-08 | 2026-05-08 | 2026-04-18 | 2026-06-19 | 2026-06-19 | 2026-06-25 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-08-14 | 2026-08-14 |  | Completed | Completed | Completed | Overdue
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2114 | ZWP21 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 38000 | 100% | 100% | 80% | -20% | 0.047 | 2026-05-08 | 2026-05-08 | 2026-04-18 | 2026-06-19 | 2026-06-19 | 2026-06-25 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-08-14 | 2026-08-14 |  | Completed | Completed | Completed | Overdue
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2115 | ZWP21 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 52000 | 100% | 100% | 80% | -20% | 0.047 | 2026-05-08 | 2026-05-08 | 2026-04-18 | 2026-06-19 | 2026-06-19 | 2026-06-25 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-08-14 | 2026-08-14 |  | Completed | Completed | Completed | Overdue
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2116 | ZWP21 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 66000 | 100% | 100% | 80% | -20% | 0.047 | 2026-05-08 | 2026-05-08 | 2026-04-18 | 2026-06-19 | 2026-06-19 | 2026-06-25 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-08-14 | 2026-08-14 |  | Completed | Completed | Completed | Overdue
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2117 | ZWP21 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 79500 | 100% | 100% | 80% | -20% | 0.047 | 2026-05-08 | 2026-05-08 | 2026-04-18 | 2026-06-19 | 2026-06-19 | 2026-06-25 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-08-14 | 2026-08-14 |  | Completed | Completed | Completed | Overdue
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2118 | ZWP21 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 93000 | 100% | 100% | 80% | -20% | 0.047 | 2026-05-08 | 2026-05-08 | 2026-04-18 | 2026-06-19 | 2026-06-19 | 2026-06-25 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-08-14 | 2026-08-14 |  | Completed | Completed | Completed | Overdue
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2119 | ZWP21 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 107000 | 100% | 100% | 80% | -20% | 0.047 | 2026-05-08 | 2026-05-08 | 2026-04-18 | 2026-06-19 | 2026-06-19 | 2026-06-25 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-08-14 | 2026-08-14 |  | Completed | Completed | Completed | Overdue
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2120 | ZWP21 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 121000 | 100% | 100% | 80% | -20% | 0.047 | 2026-05-08 | 2026-05-08 | 2026-04-18 | 2026-06-19 | 2026-06-19 | 2026-06-25 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-08-14 | 2026-08-14 |  | Completed | Completed | Completed | Overdue
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2121 | ZWP21 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 135000 | 100% | 100% | 80% | -20% | 0.047 | 2026-05-08 | 2026-05-08 | 2026-04-18 | 2026-06-19 | 2026-06-19 | 2026-06-25 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-08-14 | 2026-08-14 |  | Completed | Completed | Completed | Overdue
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2122 | ZWP21 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 147900 | 100% | 100% | 100% | 0% | 0.047 | 2026-05-08 | 2026-05-08 | 2026-04-18 | 2026-06-19 | 2026-06-19 | 2026-06-25 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-08-14 | 2026-08-14 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2123 | ZWP21 JACKET - FRAMING SECTIONS | 100% | 100% | 100% | 0% | 0.047 | 2026-05-08 | 2026-05-08 | 2026-04-18 | 2026-06-19 | 2026-06-19 | 2026-07-20 | 2026-07-31 | 2026-07-31 | 2026-08-13 | 2026-08-14 | 2026-08-14 | 2026-08-21 | Completed | Completed | Completed | Completed
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2130 | ZWP21 JACKET - LAUNCH CRADLE GENERAL ARRANGEMENT | 100% | 100% | 100% | 0% | 0.047 | 2026-05-08 | 2026-05-08 | 2026-04-30 | 2026-06-19 | 2026-06-19 | 2026-06-26 | 2026-07-31 | 2026-07-31 | 2026-08-13 | 2026-08-14 | 2026-08-14 | 2026-08-21 | Completed | Completed | Completed | Completed
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2131 | ZWP21 JACKET - LAUNCH CRADLE DETAILS - SHEET 1 | 100% | 100% | 100% | 0% | 0.047 | 2026-05-08 | 2026-05-08 | 2026-04-30 | 2026-06-19 | 2026-06-19 | 2026-06-26 | 2026-07-31 | 2026-07-31 | 2026-08-13 | 2026-08-14 | 2026-08-14 | 2026-08-21 | Completed | Completed | Completed | Completed
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2132 | ZWP21 JACKET - LAUNCH CRADLE DETAILS - SHEET 2 | 100% | 100% | 80% | -20% | 0.047 | 2026-05-08 | 2026-05-08 | 2026-04-30 | 2026-06-19 | 2026-06-19 | 2026-06-26 | 2026-07-31 | 2026-07-31 | 2026-08-13 | 2026-08-14 | 2026-08-14 |  | Completed | Completed | Completed | Overdue
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2133 | ZWP21 JACKET - LAUNCH CRADLE AND VERTICAL FRAMING INTERNAL RING STIFFENER DETAILS - SHEET 1 | 100% | 100% | 80% | -20% | 0.047 | 2026-05-08 | 2026-05-08 | 2026-04-30 | 2026-06-19 | 2026-06-19 | 2026-06-12 | 2026-07-31 | 2026-07-31 | 2026-08-13 | 2026-08-14 | 2026-08-14 |  | Completed | Completed | Completed | Overdue
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2134 | ZWP21 JACKET - LAUNCH CRADLE AND VERTICAL FRAMING INTERNAL RING STIFFENER DETAILS - SHEET 2 | 100% | 100% | 80% | -20% | 0.047 | 2026-05-08 | 2026-05-08 | 2026-04-30 | 2026-06-19 | 2026-06-19 | 2026-06-12 | 2026-07-31 | 2026-07-31 | 2026-08-13 | 2026-08-14 | 2026-08-14 |  | Completed | Completed | Completed | Overdue
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2135 | ZWP21 JACKET - LAUNCH CRADLE AND VERTICAL FRAMING INTERNAL RING STIFFENER DETAILS - SHEET 3 | 100% | 100% | 80% | -20% | 0.047 | 2026-05-08 | 2026-05-08 | 2026-04-30 | 2026-06-19 | 2026-06-19 | 2026-06-12 | 2026-07-31 | 2026-07-31 | 2026-08-13 | 2026-08-14 | 2026-08-14 |  | Completed | Completed | Completed | Overdue
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2136 | ZWP21 JACKET - LAUNCH CRADLE AND VERTICAL FRAMING INTERNAL RING STIFFENER DETAILS - SHEET 4 | 100% | 100% | 80% | -20% | 0.047 | 2026-05-08 | 2026-05-08 | 2026-04-30 | 2026-06-19 | 2026-06-19 | 2026-06-12 | 2026-07-31 | 2026-07-31 | 2026-08-13 | 2026-08-14 | 2026-08-14 |  | Completed | Completed | Completed | Overdue
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2141 | ZWP21 JACKET - PILE CLUSTER ARRANGEMENT | 80% | 80% | 70% | -10% | 0.047 | 2026-05-29 | 2026-05-29 | 2026-05-14 | 2026-07-10 | 2026-07-10 | 2026-08-14 | 2026-08-21 | 2026-08-21 |  | 2026-09-04 | 2026-09-04 |  | Completed | Completed | Overdue | Follow-This Week
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2142 | ZWP21 JACKET - PILE SLEEVE DETAILS | 80% | 80% | 70% | -10% | 0.047 | 2026-05-29 | 2026-05-29 | 2026-05-14 | 2026-07-10 | 2026-07-10 | 2026-08-14 | 2026-08-21 | 2026-08-21 |  | 2026-09-04 | 2026-09-04 |  | Completed | Completed | Overdue | Follow-This Week
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2143 | ZWP21 JACKET - SKIRT SLEEVE MARKING | 80% | 80% | 100% | 20% | 0.047 | 2026-05-29 | 2026-05-29 | 2026-05-14 | 2026-07-10 | 2026-07-10 | 2026-06-18 | 2026-08-21 | 2026-08-21 | 2026-08-15 | 2026-09-04 | 2026-09-04 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2144 | ZWP21 JACKET - PILE MAKE-UP | 100% | 100% | 70% | -30% | 0.047 | 2026-05-22 | 2026-05-22 | 2026-04-30 | 2026-07-03 | 2026-07-03 | 2026-08-14 | 2026-08-14 | 2026-08-14 |  | 2026-08-28 | 2026-08-28 |  | Completed | Completed | Overdue | Overdue
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2145 | ZWP21 JACKET - PILE MARKING | 80% | 80% | 70% | -10% | 0.047 | 2026-05-29 | 2026-05-29 | 2026-08-14 | 2026-07-10 | 2026-07-10 | 2026-08-28 | 2026-08-21 | 2026-08-21 |  | 2026-09-04 | 2026-09-04 |  | Completed | Completed | Overdue | Follow-This Week
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2200 | ZWP21 JACKET - HYDROSTATIC RING DETAILS - SHEET 1 | 100% | 100% | 80% | -20% | 0.047 | 2026-05-22 | 2026-05-22 | 2026-05-14 | 2026-07-03 | 2026-07-03 | 2026-06-12 | 2026-08-14 | 2026-08-14 | 2026-08-15 | 2026-08-28 | 2026-08-28 |  | Completed | Completed | Completed | Overdue
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2201 | ZWP21 JACKET - HYDROSTATIC RING DETAILS - SHEET 2 | 100% | 100% | 80% | -20% | 0.047 | 2026-05-22 | 2026-05-22 | 2026-05-14 | 2026-07-03 | 2026-07-03 | 2026-06-12 | 2026-08-14 | 2026-08-14 | 2026-08-15 | 2026-08-28 | 2026-08-28 |  | Completed | Completed | Completed | Overdue
ZWP-21 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-2221 | JACKET - JACKET ACCESS LAYOUT AND DETAILS - SHEET 1 | 80% | 80% | 100% | 20% | 0.047 | 2026-06-05 | 2026-06-05 | 2026-06-09 | 2026-07-17 | 2026-07-17 | 2026-06-18 | 2026-08-28 | 2026-08-28 | 2026-08-18 | 2026-09-11 | 2026-09-11 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-21 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-2222 | JACKET - JACKET ACCESS LAYOUT AND DETAILS - SHEET 2 | 80% | 80% | 100% | 20% | 0.047 | 2026-06-05 | 2026-06-05 | 2026-06-09 | 2026-07-17 | 2026-07-17 | 2026-06-18 | 2026-08-28 | 2026-08-28 | 2026-08-18 | 2026-09-11 | 2026-09-11 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-21 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-2223 | JACKET - JACKET ACCESS LAYOUT AND DETAILS - SHEET 3 | 80% | 80% | 100% | 20% | 0.047 | 2026-06-05 | 2026-06-05 | 2026-06-09 | 2026-07-17 | 2026-07-17 | 2026-06-18 | 2026-08-28 | 2026-08-28 | 2026-08-18 | 2026-09-11 | 2026-09-11 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-21 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-2224 | JACKET - JACKET WALKWAY STAIR No 8 LANDING PLANS, SECTION & DETAILS | 80% | 80% | 100% | 20% | 0.047 | 2026-06-05 | 2026-06-05 | 2026-06-09 | 2026-07-17 | 2026-07-17 | 2026-06-18 | 2026-08-28 | 2026-08-28 | 2026-08-18 | 2026-09-11 | 2026-09-11 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-21 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-2225 | JACKET - STAIR No 9 PLANS, SECTIONS & DETAILS | 80% | 80% | 100% | 20% | 0.047 | 2026-06-05 | 2026-06-05 | 2026-06-09 | 2026-07-17 | 2026-07-17 | 2026-06-18 | 2026-08-28 | 2026-08-28 | 2026-08-18 | 2026-09-11 | 2026-09-11 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-21 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-2231 | JACKET - BOATLANDING ARRANGEMENT | 80% | 80% | 100% | 20% | 0.047 | 2026-06-05 | 2026-06-05 | 2026-05-20 | 2026-07-17 | 2026-07-17 | 2026-06-18 | 2026-08-28 | 2026-08-28 | 2026-08-18 | 2026-09-11 | 2026-09-11 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-21 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-2232 | JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 1 | 80% | 80% | 100% | 20% | 0.047 | 2026-06-05 | 2026-06-05 | 2026-05-20 | 2026-07-17 | 2026-07-17 | 2026-06-18 | 2026-08-28 | 2026-08-28 | 2026-08-18 | 2026-09-11 | 2026-09-11 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-21 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-2233 | JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 2 | 80% | 80% | 100% | 20% | 0.047 | 2026-06-05 | 2026-06-05 | 2026-05-20 | 2026-07-17 | 2026-07-17 | 2026-06-18 | 2026-08-28 | 2026-08-28 | 2026-08-18 | 2026-09-11 | 2026-09-11 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-21 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-2234 | JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 3 | 80% | 80% | 100% | 20% | 0.047 | 2026-06-05 | 2026-06-05 | 2026-05-20 | 2026-07-17 | 2026-07-17 | 2026-06-18 | 2026-08-28 | 2026-08-28 | 2026-08-18 | 2026-09-11 | 2026-09-11 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-21 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-2235 | JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 4 | 80% | 80% | 100% | 20% | 0.047 | 2026-06-05 | 2026-06-05 | 2026-05-20 | 2026-07-17 | 2026-07-17 | 2026-06-18 | 2026-08-28 | 2026-08-28 | 2026-08-18 | 2026-09-11 | 2026-09-11 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-21 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-2236 | JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 5 | 80% | 80% | 100% | 20% | 0.047 | 2026-06-05 | 2026-06-05 | 2026-05-20 | 2026-07-17 | 2026-07-17 | 2026-06-18 | 2026-08-28 | 2026-08-28 | 2026-08-18 | 2026-09-11 | 2026-09-11 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-21 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-2237 | JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 6 | 80% | 80% | 100% | 20% | 0.047 | 2026-06-05 | 2026-06-05 | 2026-05-20 | 2026-07-17 | 2026-07-17 | 2026-06-18 | 2026-08-28 | 2026-08-28 | 2026-08-18 | 2026-09-11 | 2026-09-11 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-21 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-2238 | JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 7 | 80% | 80% | 100% | 20% | 0.047 | 2026-06-05 | 2026-06-05 | 2026-05-20 | 2026-07-17 | 2026-07-17 | 2026-06-18 | 2026-08-28 | 2026-08-28 | 2026-08-18 | 2026-09-11 | 2026-09-11 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2241 | ZWP21 JACKET - RISER PROTECTOR | 100% | 100% | 80% | -20% | 0.047 | 2026-05-22 | 2026-05-22 | 2026-06-11 | 2026-07-03 | 2026-07-03 | 2026-06-19 | 2026-08-14 | 2026-08-14 | 2026-08-20 | 2026-08-28 | 2026-08-28 |  | Completed | Completed | Completed | Overdue
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2242 | ZWP21 JACKET - RISER PROTECTOR (OPTION) - CANCELLED |  |  |  |  | 0.047 | 2026-05-22 | 2026-05-22 | 2026-06-11 | 2026-07-03 | 2026-07-03 | 2026-06-19 | 2026-08-14 | 2026-08-14 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2300 | ZWP21 JACKET - CASING GUIDE ARRANGEMENT | 100% | 100% | 80% | -20% | 0.047 | 2026-05-22 | 2026-05-22 | 2026-06-11 | 2026-07-03 | 2026-07-03 | 2026-06-19 | 2026-08-14 | 2026-08-14 | 2026-08-20 | 2026-08-28 | 2026-08-28 |  | Completed | Completed | Completed | Overdue
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2301 | ZWP21 JACKET - CASING GUIDE DETAILS | 100% | 100% | 80% | -20% | 0.047 | 2026-05-22 | 2026-05-22 | 2026-06-11 | 2026-07-03 | 2026-07-03 | 2026-06-19 | 2026-08-14 | 2026-08-14 | 2026-08-20 | 2026-08-28 | 2026-08-28 |  | Completed | Completed | Completed | Overdue
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2311 | ZWP21 JACKET - ANODE STRUCTURE AND INSTALLATION | 70% | 70% | 70% | 0% | 0.047 | 2026-06-12 | 2026-06-12 | 2026-04-24 | 2026-07-24 | 2026-07-24 | 2026-08-06 | 2026-09-04 | 2026-09-04 |  | 2026-09-18 | 2026-09-18 |  | Completed | Completed | Follow-This Week
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2312 | ZWP21 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING ROW 'A' | 70% | 70% | 70% | 0% | 0.047 | 2026-06-12 | 2026-06-12 | 2026-04-24 | 2026-07-24 | 2026-07-24 | 2026-08-06 | 2026-09-04 | 2026-09-04 |  | 2026-09-18 | 2026-09-18 |  | Completed | Completed | Follow-This Week
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2313 | ZWP21 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING ROW 'B' | 70% | 70% | 70% | 0% | 0.047 | 2026-06-12 | 2026-06-12 | 2026-04-24 | 2026-07-24 | 2026-07-24 | 2026-08-06 | 2026-09-04 | 2026-09-04 |  | 2026-09-18 | 2026-09-18 |  | Completed | Completed | Follow-This Week
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2314 | ZWP21 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING ROW '1' & '1.1' | 70% | 70% | 70% | 0% | 0.047 | 2026-06-12 | 2026-06-12 | 2026-04-24 | 2026-07-24 | 2026-07-24 | 2026-08-06 | 2026-09-04 | 2026-09-04 |  | 2026-09-18 | 2026-09-18 |  | Completed | Completed | Follow-This Week
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2315 | ZWP21 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING ROW '2' | 70% | 70% | 70% | 0% | 0.047 | 2026-06-12 | 2026-06-12 | 2026-04-24 | 2026-07-24 | 2026-07-24 | 2026-08-06 | 2026-09-04 | 2026-09-04 |  | 2026-09-18 | 2026-09-18 |  | Completed | Completed | Follow-This Week
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2316 | ZWP21 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING LAUNCH TRUSS ROW 'Aa' | 70% | 70% | 70% | 0% | 0.047 | 2026-06-12 | 2026-06-12 | 2026-04-24 | 2026-07-24 | 2026-07-24 | 2026-08-06 | 2026-09-04 | 2026-09-04 |  | 2026-09-18 | 2026-09-18 |  | Completed | Completed | Follow-This Week
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2317 | ZWP21 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING LAUNCH TRUSS ROW 'Bb' | 70% | 70% | 70% | 0% | 0.047 | 2026-06-12 | 2026-06-12 | 2026-04-24 | 2026-07-24 | 2026-07-24 | 2026-08-06 | 2026-09-04 | 2026-09-04 |  | 2026-09-18 | 2026-09-18 |  | Completed | Completed | Follow-This Week
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2321 | ZWP21 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 14000 | 70% | 70% | 70% | 0% | 0.047 | 2026-06-12 | 2026-06-12 | 2026-04-24 | 2026-07-24 | 2026-07-24 | 2026-08-06 | 2026-09-04 | 2026-09-04 |  | 2026-09-18 | 2026-09-18 |  | Completed | Completed | Follow-This Week
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2322 | ZWP21 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 26000 | 70% | 70% | 70% | 0% | 0.047 | 2026-06-12 | 2026-06-12 | 2026-04-24 | 2026-07-24 | 2026-07-24 | 2026-08-06 | 2026-09-04 | 2026-09-04 |  | 2026-09-18 | 2026-09-18 |  | Completed | Completed | Follow-This Week
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2323 | ZWP21 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 38000 | 70% | 70% | 70% | 0% | 0.047 | 2026-06-12 | 2026-06-12 | 2026-04-24 | 2026-07-24 | 2026-07-24 | 2026-08-06 | 2026-09-04 | 2026-09-04 |  | 2026-09-18 | 2026-09-18 |  | Completed | Completed | Follow-This Week
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2324 | ZWP21 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 52000 | 70% | 70% | 70% | 0% | 0.047 | 2026-06-12 | 2026-06-12 | 2026-04-24 | 2026-07-24 | 2026-07-24 | 2026-08-06 | 2026-09-04 | 2026-09-04 |  | 2026-09-18 | 2026-09-18 |  | Completed | Completed | Follow-This Week
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2325 | ZWP21 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 66000 | 70% | 70% | 70% | 0% | 0.047 | 2026-06-12 | 2026-06-12 | 2026-04-24 | 2026-07-24 | 2026-07-24 | 2026-08-06 | 2026-09-04 | 2026-09-04 |  | 2026-09-18 | 2026-09-18 |  | Completed | Completed | Follow-This Week
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2326 | ZWP21 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 79500 | 70% | 70% | 70% | 0% | 0.047 | 2026-06-12 | 2026-06-12 | 2026-04-24 | 2026-07-24 | 2026-07-24 | 2026-08-06 | 2026-09-04 | 2026-09-04 |  | 2026-09-18 | 2026-09-18 |  | Completed | Completed | Follow-This Week
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2327 | ZWP21 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 93000 | 70% | 70% | 70% | 0% | 0.047 | 2026-06-12 | 2026-06-12 | 2026-04-24 | 2026-07-24 | 2026-07-24 | 2026-08-06 | 2026-09-04 | 2026-09-04 |  | 2026-09-18 | 2026-09-18 |  | Completed | Completed | Follow-This Week
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2328 | ZWP21 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 107000 | 70% | 70% | 70% | 0% | 0.047 | 2026-06-12 | 2026-06-12 | 2026-04-24 | 2026-07-24 | 2026-07-24 | 2026-08-06 | 2026-09-04 | 2026-09-04 |  | 2026-09-18 | 2026-09-18 |  | Completed | Completed | Follow-This Week
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2329 | ZWP21 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 121000 | 70% | 70% | 70% | 0% | 0.047 | 2026-06-12 | 2026-06-12 | 2026-04-24 | 2026-07-24 | 2026-07-24 | 2026-08-06 | 2026-09-04 | 2026-09-04 |  | 2026-09-18 | 2026-09-18 |  | Completed | Completed | Follow-This Week
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2330 | ZWP21 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 135000 | 70% | 70% | 70% | 0% | 0.047 | 2026-06-12 | 2026-06-12 | 2026-04-24 | 2026-07-24 | 2026-07-24 | 2026-08-06 | 2026-09-04 | 2026-09-04 |  | 2026-09-18 | 2026-09-18 |  | Completed | Completed | Follow-This Week
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2331 | ZWP21 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 147900 | 70% | 70% | 70% | 0% | 0.047 | 2026-06-12 | 2026-06-12 | 2026-04-24 | 2026-07-24 | 2026-07-24 | 2026-08-06 | 2026-09-04 | 2026-09-04 |  | 2026-09-18 | 2026-09-18 |  | Completed | Completed | Follow-This Week
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2332 | ZWP21 JACKET - ANODE DISTRIBUTION OF PILE CLUSTER | 70% | 70% | 70% | 0% | 0.047 | 2026-06-12 | 2026-06-12 | 2026-04-24 | 2026-07-24 | 2026-07-24 | 2026-08-06 | 2026-09-04 | 2026-09-04 |  | 2026-09-18 | 2026-09-18 |  | Completed | Completed | Follow-This Week
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2411 | ZWP21 JACKET - INSTALLATION PROCEDURE |  |  |  |  | 0.047 | 2026-06-19 | 2026-06-19 | 2026-06-26 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-25 | 2026-09-25 | 2026-09-25 | Completed | Completed | Completed | Completed
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2421 | ZWP21 JACKET - INSTALLATION AID CLASH CHECK |  |  |  |  | 0.047 | 2026-06-19 | 2026-06-19 | 2026-06-26 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-25 | 2026-09-25 | 2026-09-25 | Completed | Completed | Completed | Completed
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-XXXX | ZWP21 JACKET - INSTALLATION PROCEDURE (TBC FROM T&I) | 0% | 0% | 0% | 0% |  | 2026-10-09 | 2026-10-09 |  | 2026-11-20 | 2026-11-20 |  | 2027-01-01 | 2027-01-01 |  | 2027-01-15 | 2027-01-15
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-XXXX | ZWP21 JACKET - INSTALLATION AID CLASH CHECK (TBC FROM T&I) | 0% | 0% | 0% | 0% |  | 2026-10-09 | 2026-10-09 |  | 2026-11-20 | 2026-11-20 |  | 2027-01-01 | 2027-01-01 |  | 2027-01-15 | 2027-01-15
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2801 | ZWP21 JACKET - RISER SUPPORT LOCATION | 70% | 70% | 70% | 0% |  | 2026-06-26 | 2026-06-26 | 2026-06-17 | 2026-08-07 | 2026-08-07 | 2026-08-21 | 2026-09-18 | 2026-09-18 |  | 2026-10-02 | 2026-10-02 |  | Completed | Completed
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2802 | ZWP21 JACKET - RISER CLAMP DETAILS SHEET 1 | 0% | 0% | 50% | 50% |  | 2026-08-31 | 2026-08-31 | 2026-08-21 | 2026-10-12 | 2026-10-12 |  | 2026-11-23 | 2026-11-23 |  | 2026-12-07 | 2026-12-07 |  | Completed
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2803 | ZWP21 JACKET - RISER CLAMP DETAILS SHEET 2 | 0% | 0% | 50% | 50% |  | 2026-08-31 | 2026-08-31 | 2026-08-21 | 2026-10-12 | 2026-10-12 |  | 2026-11-23 | 2026-11-23 |  | 2026-12-07 | 2026-12-07 |  | Completed
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2804 | ZWP21 JACKET - RISER CLAMP DETAILS SHEET 3 | 0% | 0% | 50% | 50% |  | 2026-08-31 | 2026-08-31 | 2026-08-21 | 2026-10-12 | 2026-10-12 |  | 2026-11-23 | 2026-11-23 |  | 2026-12-07 | 2026-12-07 |  | Completed
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2805 | ZWP21 JACKET - RISER CLAMP DETAILS SHEET 4 | 0% | 0% | 50% | 50% |  | 2026-08-31 | 2026-08-31 | 2026-08-21 | 2026-10-12 | 2026-10-12 |  | 2026-11-23 | 2026-11-23 |  | 2026-12-07 | 2026-12-07 |  | Completed
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2806 | ZWP21 JACKET - RISER CLAMP DETAILS SHEET 5 | 0% | 0% | 50% | 50% |  | 2026-08-31 | 2026-08-31 | 2026-08-21 | 2026-10-12 | 2026-10-12 |  | 2026-11-23 | 2026-11-23 |  | 2026-12-07 | 2026-12-07 |  | Completed
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2807 | ZWP21 JACKET - RISER CLAMP DETAILS SHEET 6 | 0% | 0% | 50% | 50% |  | 2026-08-31 | 2026-08-31 | 2026-08-21 | 2026-10-12 | 2026-10-12 |  | 2026-11-23 | 2026-11-23 |  | 2026-12-07 | 2026-12-07 |  | Completed
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2808 | ZWP21 JACKET - RISER CLAMP DETAILS SHEET 7 | 0% | 0% | 50% | 50% |  | 2026-08-31 | 2026-08-31 | 2026-08-21 | 2026-10-12 | 2026-10-12 |  | 2026-11-23 | 2026-11-23 |  | 2026-12-07 | 2026-12-07 |  | Completed
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2809 | ZWP21 JACKET - RISER CLAMP DETAILS SHEET 8 | 0% | 0% | 50% | 50% |  | 2026-08-31 | 2026-08-31 | 2026-08-21 | 2026-10-12 | 2026-10-12 |  | 2026-11-23 | 2026-11-23 |  | 2026-12-07 | 2026-12-07 |  | Completed
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2810 | ZWP21 JACKET - RISER CLAMP DETAILS SHEET 9 | 0% | 0% | 0% | 0% |  | 2026-08-31 | 2026-08-31 |  | 2026-10-12 | 2026-10-12 |  | 2026-11-23 | 2026-11-23 |  | 2026-12-07 | 2026-12-07 |  | Follow-This Week
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2811 | ZWP21 JACKET - RISER CLAMP DETAILS SHEET 10 | 0% | 0% | 0% | 0% |  | 2026-08-31 | 2026-08-31 |  | 2026-10-12 | 2026-10-12 |  | 2026-11-23 | 2026-11-23 |  | 2026-12-07 | 2026-12-07 |  | Follow-This Week
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2900 | ZWP21 JACKET - CLOSURE PLATE DETAILS - SHEET 1 | 70% | 70% | 50% | -20% | 0.047 | 2026-06-19 | 2026-06-19 | 2026-06-11 | 2026-07-31 | 2026-07-31 |  | 2026-09-11 | 2026-09-11 |  | 2026-09-25 | 2026-09-25 |  | Completed | Overdue | Follow-Next Week
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2901 | ZWP21 JACKET - CLOSURE PLATE DETAILS - SHEET 2 | 70% | 70% | 50% | -20% | 0.047 | 2026-06-19 | 2026-06-19 | 2026-06-11 | 2026-07-31 | 2026-07-31 |  | 2026-09-11 | 2026-09-11 |  | 2026-09-25 | 2026-09-25 |  | Completed | Overdue | Follow-Next Week
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2902 | ZWP21 JACKET - LEG PARTITION DETAILS | 70% | 70% | 50% | -20% | 0.047 | 2026-06-19 | 2026-06-19 | 2026-05-19 | 2026-07-31 | 2026-07-31 |  | 2026-09-11 | 2026-09-11 |  | 2026-09-25 | 2026-09-25 |  | Completed | Overdue | Follow-Next Week
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2911 | ZWP21 JACKET - UPENDING ARRANGEMENT AND DETAILS | 70% | 70% | 50% | -20% | 0.047 | 2026-06-19 | 2026-06-19 | 2026-06-11 | 2026-07-31 | 2026-07-31 |  | 2026-09-11 | 2026-09-11 |  | 2026-09-25 | 2026-09-25 |  | Completed | Overdue | Follow-Next Week
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2931 | ZWP21 JACKET - BALLAST / DEBASSAST SCHEMATIC | 70% | 70% | 70% | 0% | 0.047 | 2026-06-26 | 2026-06-26 | 2026-04-30 | 2026-08-07 | 2026-08-07 | 2026-08-21 | 2026-09-18 | 2026-09-18 |  | 2026-10-02 | 2026-10-02 |  | Completed | Completed
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2932 | ZWP21 JACKET - GROUTING SCHEMATIC | 70% | 70% | 70% | 0% | 0.047 | 2026-06-26 | 2026-06-26 | 2026-04-30 | 2026-08-07 | 2026-08-07 | 2026-08-21 | 2026-09-18 | 2026-09-18 |  | 2026-10-02 | 2026-10-02 |  | Completed | Completed
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2933 | ZWP21 JACKET - BALLAST SYSTEM AND GROUTING LINE ROUTING AT ROW A ELEVATION | 70% | 70% | 50% | -20% | 0.047 | 2026-06-26 | 2026-06-26 | 2026-06-18 | 2026-08-07 | 2026-08-07 |  | 2026-09-18 | 2026-09-18 |  | 2026-10-02 | 2026-10-02 |  | Completed | Overdue
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2934 | ZWP21 JACKET - BALLAST SYSTEM AND GROUTING LINE ROUTING AT ROW B ELEVATION | 70% | 70% | 50% | -20% | 0.047 | 2026-06-26 | 2026-06-26 | 2026-06-18 | 2026-08-07 | 2026-08-07 |  | 2026-09-18 | 2026-09-18 |  | 2026-10-02 | 2026-10-02 |  | Completed | Overdue
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2935 | ZWP21 JACKET - BALLAST AND GROUTING SYSTEM SUPPORT DETAILS SHEET 1 | 70% | 70% | 50% | -20% | 0.047 | 2026-06-26 | 2026-06-26 | 2026-06-18 | 2026-08-07 | 2026-08-07 |  | 2026-09-18 | 2026-09-18 |  | 2026-10-02 | 2026-10-02 |  | Completed | Overdue
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2936 | ZWP21 JACKET - BALLAST AND GROUTING SYSTEM SUPPORT DETAILS SHEET 2 | 70% | 70% | 50% | -20% | 0.047 | 2026-06-26 | 2026-06-26 | 2026-06-18 | 2026-08-07 | 2026-08-07 |  | 2026-09-18 | 2026-09-18 |  | 2026-10-02 | 2026-10-02 |  | Completed | Overdue
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2937 | ZWP21 JACKET - BALLAST SYSTEM VALVE DETAILS | 70% | 70% | 50% | -20% | 0.047 | 2026-06-26 | 2026-06-26 | 2026-06-18 | 2026-08-07 | 2026-08-07 |  | 2026-09-18 | 2026-09-18 |  | 2026-10-02 | 2026-10-02 |  | Completed | Overdue
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2938 | ZWP21 JACKET -GROUT, SKIRT SLEEVE VENT AND FLOODING DETAILS AT SKIRT PILE SLEEVE SHEET 1 | 70% | 70% | 50% | -20% | 0.047 | 2026-06-26 | 2026-06-26 | 2026-06-18 | 2026-08-07 | 2026-08-07 |  | 2026-09-18 | 2026-09-18 |  | 2026-10-02 | 2026-10-02 |  | Completed | Overdue
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2939 | ZWP21 JACKET -GROUT, SKIRT SLEEVE VENT AND FLOODING DETAILS AT SKIRT PILE SLEEVE SHEET 2 | 70% | 70% | 50% | -20% | 0.047 | 2026-06-26 | 2026-06-26 | 2026-06-18 | 2026-08-07 | 2026-08-07 |  | 2026-09-18 | 2026-09-18 |  | 2026-10-02 | 2026-10-02 |  | Completed | Overdue
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2940 | ZWP21 JACKET - BALLAST SYSTEM AND GROUTING LINE ROUTING AT EL(+) 8000 | 70% | 70% | 50% | -20% | 0.047 | 2026-06-26 | 2026-06-26 | 2026-06-18 | 2026-08-07 | 2026-08-07 |  | 2026-09-18 | 2026-09-18 |  | 2026-10-02 | 2026-10-02 |  | Completed | Overdue
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2941 | ZWP21 JACKET - GROUT SYSTEM DETAILS | 70% | 70% | 50% | -20% | 0.047 | 2026-06-26 | 2026-06-26 | 2026-06-18 | 2026-08-07 | 2026-08-07 |  | 2026-09-18 | 2026-09-18 |  | 2026-10-02 | 2026-10-02 |  | Completed | Overdue
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2950 | ZWP21 JACKET - LAUNCHING SEQUENCE | 70% | 70% | 0% | -70% | 0.047 | 2026-07-03 | 2026-07-03 |  | 2026-08-14 | 2026-08-14 |  | 2026-09-25 | 2026-09-25 |  | 2026-10-09 | 2026-10-09 |  | Overdue | Overdue
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2951 | ZWP21 JACKET - UPENDING & LOWERING SEQUENCE | 70% | 70% | 0% | -70% | 0.047 | 2026-07-03 | 2026-07-03 |  | 2026-08-14 | 2026-08-14 |  | 2026-09-25 | 2026-09-25 |  | 2026-10-09 | 2026-10-09 |  | Overdue | Overdue
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2961 | ZWP21 JACKET - PILE LIFTING & UPENDING | 70% | 70% | 0% | -70% | 0.047 | 2026-07-03 | 2026-07-03 |  | 2026-08-14 | 2026-08-14 |  | 2026-09-25 | 2026-09-25 |  | 2026-10-09 | 2026-10-09 |  | Overdue | Overdue
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2971 | ZWP21 JACKET - WELD PROFILE CONTROL SHEET 1 | 70% | 70% | 70% | 0% | 0.047 | 2026-07-03 | 2026-07-03 | 2026-06-17 | 2026-08-14 | 2026-08-14 | 2026-08-13 | 2026-09-25 | 2026-09-25 |  | 2026-10-09 | 2026-10-09 |  | Completed | Completed
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2972 | ZWP21 JACKET - WELD PROFILE CONTROL SHEET 2 | 70% | 70% | 70% | 0% | 0.047 | 2026-07-03 | 2026-07-03 | 2026-06-17 | 2026-08-14 | 2026-08-14 | 2026-08-13 | 2026-09-25 | 2026-09-25 |  | 2026-10-09 | 2026-10-09 |  | Completed | Completed
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2973 | ZWP21 JACKET - WELD PROFILE CONTROL SHEET 3 | 70% | 70% | 70% | 0% | 0.047 | 2026-07-03 | 2026-07-03 | 2026-06-17 | 2026-08-14 | 2026-08-14 | 2026-08-13 | 2026-09-25 | 2026-09-25 |  | 2026-10-09 | 2026-10-09 |  | Completed | Completed
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2974 | ZWP21 JACKET - WELD PROFILE CONTROL SHEET 4 | 70% | 70% | 70% | 0% | 0.047 | 2026-07-03 | 2026-07-03 | 2026-06-17 | 2026-08-14 | 2026-08-14 | 2026-08-13 | 2026-09-25 | 2026-09-25 |  | 2026-10-09 | 2026-10-09 |  | Completed | Completed
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2975 | ZWP21 JACKET - WELD PROFILE CONTROL SHEET 5 | 70% | 70% | 70% | 0% | 0.047 | 2026-07-03 | 2026-07-03 | 2026-06-17 | 2026-08-14 | 2026-08-14 | 2026-08-13 | 2026-09-25 | 2026-09-25 |  | 2026-10-09 | 2026-10-09 |  | Completed | Completed
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2976 | ZWP21 JACKET - WELD PROFILE CONTROL SHEET 6 | 70% | 70% | 70% | 0% | 0.047 | 2026-07-03 | 2026-07-03 | 2026-06-17 | 2026-08-14 | 2026-08-14 | 2026-08-13 | 2026-09-25 | 2026-09-25 |  | 2026-10-09 | 2026-10-09 |  | Completed | Completed
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2981 | ZWP21 JACKET - LEG PAINT MARKING DETAILS - SHEET 1 | 70% | 70% | 80% | 10% | 0.047 | 2026-07-03 | 2026-07-03 | 2026-07-17 | 2026-08-14 | 2026-08-14 | 2026-07-30 | 2026-09-25 | 2026-09-25 | 2026-08-20 | 2026-10-09 | 2026-10-09 |  | Completed | Completed | Completed
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2982 | ZWP21 JACKET - LEG PAINT MARKING DETAILS - SHEET 2 | 70% | 70% | 80% | 10% | 0.047 | 2026-07-03 | 2026-07-03 | 2026-07-17 | 2026-08-14 | 2026-08-14 | 2026-07-30 | 2026-09-25 | 2026-09-25 | 2026-08-20 | 2026-10-09 | 2026-10-09 |  | Completed | Completed | Completed
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2984 | ZWP21 JACKET - PULLING LUG DETAILS (CANCELLED) |  |  |  |  | 0.047 | 2026-07-03 | 2026-07-03 | 2026-07-24 | 2026-08-14 | 2026-08-14 | 2026-07-24 | 2026-09-25 | 2026-09-25 | 2026-07-24 | 2026-10-09 | 2026-10-09 | 2026-07-24
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2991 | ZWP21 JACKET - JACKET TRANSPORTATION ARRANGEMENT | 70% | 70% | 80% | 10% | 0.047 | 2026-07-03 | 2026-07-03 | 2026-07-17 | 2026-08-14 | 2026-08-14 | 2026-07-30 | 2026-09-25 | 2026-09-25 | 2026-08-20 | 2026-10-09 | 2026-10-09 |  | Completed | Completed | Completed
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2994 | ZWP21 JACKET - VORTEX SHEDDING PREVENTION - SHEET 1 | 70% | 70% | 70% | 0% | 0.047 | 2026-07-03 | 2026-07-03 | 2026-08-14 | 2026-08-14 | 2026-08-14 | 2026-08-21 | 2026-09-25 | 2026-09-25 |  | 2026-10-09 | 2026-10-09 |  | Completed | Completed
ZWP-21 | Drawing | MM-ZTK-1F-ZWP21-STR-DWG-2995 | ZWP21 JACKET - VORTEX SHEDDING PREVENTION - SHEET 2 | 70% | 70% | 70% | 0% | 0.047 | 2026-07-03 | 2026-07-03 | 2026-08-14 | 2026-08-14 | 2026-08-14 | 2026-08-21 | 2026-09-25 | 2026-09-25 |  | 2026-10-09 | 2026-10-09 |  | Completed | Completed
ZWP-21 | Drawing | AS-BUILT DRAWINGS (TO BE CONFIRMED) | ZWP21 AS-BUILT DRAWINGS | 0% | 0% | 0% | 0% | 1.5
ZWP-23 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-0051 | JACKET - GENERAL NOTES - SHEET 1 | 80% | 80% | 100% | 20% | 0.009 | 2026-06-05 | 2026-06-05 | 2026-06-02 | 2026-07-17 | 2026-07-17 | 2026-06-18 | 2026-08-28 | 2026-08-28 | 2026-08-11 | 2026-09-11 | 2026-09-11 | 2026-08-21 | Completed | Completed | Completed | Completed
ZWP-23 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-0052 | JACKET - GENERAL NOTES - SHEET 2 | 80% | 80% | 100% | 20% | 0.009 | 2026-06-05 | 2026-06-05 | 2026-06-02 | 2026-07-17 | 2026-07-17 | 2026-06-18 | 2026-08-28 | 2026-08-28 | 2026-08-11 | 2026-09-11 | 2026-09-11 | 2026-08-21 | Completed | Completed | Completed | Completed
ZWP-23 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-0061 | JACKET - STANDARD DETAILS WELD PROFILE - SHEET 1 | 80% | 80% | 100% | 20% | 0.047 | 2026-06-05 | 2026-06-05 | 2026-06-02 | 2026-07-17 | 2026-07-17 | 2026-06-18 | 2026-08-28 | 2026-08-28 | 2026-08-11 | 2026-09-11 | 2026-09-11 | 2026-08-21 | Completed | Completed | Completed | Completed
ZWP-23 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-0062 | JACKET - STANDARD DETAILS WELD PROFILE - SHEET 2 | 80% | 80% | 100% | 20% | 0.047 | 2026-06-05 | 2026-06-05 | 2026-06-02 | 2026-07-17 | 2026-07-17 | 2026-06-18 | 2026-08-28 | 2026-08-28 | 2026-08-11 | 2026-09-11 | 2026-09-11 | 2026-08-21 | Completed | Completed | Completed | Completed
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2001 | ZWP23 JACKET - DRAWING INDEX - SHEET 1 | 80% | 80% | 0% | -80% | 0.047 | 2026-06-05 | 2026-06-05 |  | 2026-07-17 | 2026-07-17 |  | 2026-08-28 | 2026-08-28 |  | 2026-09-11 | 2026-09-11 |  | Overdue | Overdue | Overdue | Follow-Next Week
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2002 | ZWP23 JACKET - DRAWING INDEX - SHEET 2 | 80% | 80% | 0% | -80% | 0.047 | 2026-06-05 | 2026-06-05 |  | 2026-07-17 | 2026-07-17 |  | 2026-08-28 | 2026-08-28 |  | 2026-09-11 | 2026-09-11 |  | Overdue | Overdue | Overdue | Follow-Next Week
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2100 | ZWP23 JACKET - VERTICAL FRAMING ROW 'A' | 80% | 80% | 70% | -10% | 0.047 | 2026-06-05 | 2026-06-05 | 2026-04-18 | 2026-07-17 | 2026-07-17 | 2026-07-14 | 2026-08-24 | 2026-08-24 |  | 2026-09-07 | 2026-09-07 |  | Completed | Completed | Overdue | Follow-Next Week
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2101 | ZWP23 JACKET - VERTICAL FRAMING ROW 'B' | 80% | 80% | 70% | -10% | 0.047 | 2026-06-05 | 2026-06-05 | 2026-04-18 | 2026-07-17 | 2026-07-17 | 2026-07-14 | 2026-08-24 | 2026-08-24 |  | 2026-09-07 | 2026-09-07 |  | Completed | Completed | Overdue | Follow-Next Week
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2102 | ZWP23 JACKET - VERTICAL FRAMING ROW '1' & '1.1' | 80% | 80% | 70% | -10% | 0.047 | 2026-06-05 | 2026-06-05 | 2026-04-18 | 2026-07-17 | 2026-07-17 | 2026-07-14 | 2026-08-24 | 2026-08-24 |  | 2026-09-07 | 2026-09-07 |  | Completed | Completed | Overdue | Follow-Next Week
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2103 | ZWP23 JACKET - VERTICAL FRAMING ROW '2' | 80% | 80% | 70% | -10% | 0.047 | 2026-06-05 | 2026-06-05 | 2026-04-18 | 2026-07-17 | 2026-07-17 | 2026-07-14 | 2026-08-24 | 2026-08-24 |  | 2026-09-07 | 2026-09-07 |  | Completed | Completed | Overdue | Follow-Next Week
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2104 | ZWP23 JACKET - VERTICAL FRAMING LAUNCH TRUSS ROW 'Aa' | 80% | 80% | 70% | -10% | 0.047 | 2026-06-05 | 2026-06-05 | 2026-04-18 | 2026-07-17 | 2026-07-17 | 2026-07-14 | 2026-08-24 | 2026-08-24 |  | 2026-09-07 | 2026-09-07 |  | Completed | Completed | Overdue | Follow-Next Week
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2105 | ZWP23 JACKET - VERTICAL FRAMING LAUNCH TRUSS ROW 'Bb' | 80% | 80% | 70% | -10% | 0.047 | 2026-06-05 | 2026-06-05 | 2026-04-18 | 2026-07-17 | 2026-07-17 | 2026-07-14 | 2026-08-24 | 2026-08-24 |  | 2026-09-07 | 2026-09-07 |  | Completed | Completed | Overdue | Follow-Next Week
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2110 | ZWP23 JACKET - HORIZONTAL FRAMING PLAN AT EL(+) 8000 | 80% | 80% | 70% | -10% | 0.047 | 2026-06-05 | 2026-06-05 | 2026-04-18 | 2026-07-17 | 2026-07-17 | 2026-07-14 | 2026-08-24 | 2026-08-24 |  | 2026-09-07 | 2026-09-07 |  | Completed | Completed | Overdue | Follow-Next Week
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2111 | ZWP23 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 3000 | 80% | 80% | 70% | -10% | 0.047 | 2026-06-05 | 2026-06-05 | 2026-04-18 | 2026-07-17 | 2026-07-17 | 2026-07-14 | 2026-08-24 | 2026-08-24 |  | 2026-09-07 | 2026-09-07 |  | Completed | Completed | Overdue | Follow-Next Week
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2112 | ZWP23 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 14000 | 80% | 80% | 70% | -10% | 0.047 | 2026-06-05 | 2026-06-05 | 2026-04-18 | 2026-07-17 | 2026-07-17 | 2026-07-14 | 2026-08-24 | 2026-08-24 |  | 2026-09-07 | 2026-09-07 |  | Completed | Completed | Overdue | Follow-Next Week
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2113 | ZWP23 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 26000 | 80% | 80% | 70% | -10% | 0.047 | 2026-06-05 | 2026-06-05 | 2026-04-18 | 2026-07-17 | 2026-07-17 | 2026-07-14 | 2026-08-24 | 2026-08-24 |  | 2026-09-07 | 2026-09-07 |  | Completed | Completed | Overdue | Follow-Next Week
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2114 | ZWP23 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 38000 | 80% | 80% | 70% | -10% | 0.047 | 2026-06-05 | 2026-06-05 | 2026-04-18 | 2026-07-17 | 2026-07-17 | 2026-07-14 | 2026-08-24 | 2026-08-24 |  | 2026-09-07 | 2026-09-07 |  | Completed | Completed | Overdue | Follow-Next Week
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2115 | ZWP23 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 52000 | 80% | 80% | 70% | -10% | 0.047 | 2026-06-05 | 2026-06-05 | 2026-04-18 | 2026-07-17 | 2026-07-17 | 2026-07-14 | 2026-08-24 | 2026-08-24 |  | 2026-09-07 | 2026-09-07 |  | Completed | Completed | Overdue | Follow-Next Week
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2116 | ZWP23 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 66000 | 80% | 80% | 70% | -10% | 0.047 | 2026-06-05 | 2026-06-05 | 2026-04-18 | 2026-07-17 | 2026-07-17 | 2026-07-14 | 2026-08-24 | 2026-08-24 |  | 2026-09-07 | 2026-09-07 |  | Completed | Completed | Overdue | Follow-Next Week
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2117 | ZWP23 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 79500 | 80% | 80% | 70% | -10% | 0.047 | 2026-06-05 | 2026-06-05 | 2026-04-18 | 2026-07-17 | 2026-07-17 | 2026-07-14 | 2026-08-24 | 2026-08-24 |  | 2026-09-07 | 2026-09-07 |  | Completed | Completed | Overdue | Follow-Next Week
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2118 | ZWP23 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 93000 | 80% | 80% | 70% | -10% | 0.047 | 2026-06-05 | 2026-06-05 | 2026-04-18 | 2026-07-17 | 2026-07-17 | 2026-07-14 | 2026-08-24 | 2026-08-24 |  | 2026-09-07 | 2026-09-07 |  | Completed | Completed | Overdue | Follow-Next Week
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2119 | ZWP23 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 107000 | 80% | 80% | 70% | -10% | 0.047 | 2026-06-05 | 2026-06-05 | 2026-04-18 | 2026-07-17 | 2026-07-17 | 2026-07-14 | 2026-08-24 | 2026-08-24 |  | 2026-09-07 | 2026-09-07 |  | Completed | Completed | Overdue | Follow-Next Week
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2120 | ZWP23 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 121000 | 80% | 80% | 70% | -10% | 0.047 | 2026-06-05 | 2026-06-05 | 2026-04-18 | 2026-07-17 | 2026-07-17 | 2026-07-14 | 2026-08-24 | 2026-08-24 |  | 2026-09-07 | 2026-09-07 |  | Completed | Completed | Overdue | Follow-Next Week
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2121 | ZWP23 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 133000 | 80% | 80% | 70% | -10% | 0.047 | 2026-06-05 | 2026-06-05 | 2026-04-18 | 2026-07-17 | 2026-07-17 | 2026-07-14 | 2026-08-24 | 2026-08-24 |  | 2026-09-07 | 2026-09-07 |  | Completed | Completed | Overdue | Follow-Next Week
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2122 | ZWP23 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 144100 | 80% | 80% | 70% | -10% | 0.047 | 2026-06-05 | 2026-06-05 | 2026-04-18 | 2026-07-17 | 2026-07-17 | 2026-07-14 | 2026-08-24 | 2026-08-24 |  | 2026-09-07 | 2026-09-07 |  | Completed | Completed | Overdue | Follow-Next Week
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2123 | ZWP23 JACKET - FRAMING SECTIONS | 80% | 80% | 70% | -10% | 0.047 | 2026-06-05 | 2026-06-05 | 2026-04-18 | 2026-07-17 | 2026-07-17 | 2026-07-21 | 2026-08-24 | 2026-08-24 |  | 2026-09-07 | 2026-09-07 |  | Completed | Completed | Overdue | Follow-Next Week
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2130 | ZWP23 JACKET - LAUNCH CRADLE GENERAL ARRANGEMENT | 80% | 80% | 70% | -10% | 0.047 | 2026-06-05 | 2026-06-05 | 2026-05-08 | 2026-07-17 | 2026-07-17 | 2026-07-02 | 2026-08-24 | 2026-08-24 |  | 2026-09-07 | 2026-09-07 |  | Completed | Completed | Overdue | Follow-Next Week
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2131 | ZWP23 JACKET - LAUNCH CRADLE DETAILS - SHEET 1 | 80% | 80% | 70% | -10% | 0.047 | 2026-06-05 | 2026-06-05 | 2026-05-08 | 2026-07-17 | 2026-07-17 | 2026-07-02 | 2026-08-24 | 2026-08-24 |  | 2026-09-07 | 2026-09-07 |  | Completed | Completed | Overdue | Follow-Next Week
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2132 | ZWP23 JACKET - LAUNCH CRADLE DETAILS - SHEET 2 | 80% | 80% | 100% | 20% | 0.047 | 2026-06-05 | 2026-06-05 | 2026-05-08 | 2026-07-17 | 2026-07-17 | 2026-07-02 | 2026-08-24 | 2026-08-24 | 2026-08-14 | 2026-09-07 | 2026-09-07 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2133 | ZWP23 JACKET - LAUNCH CRADLE AND VERTICAL FRAMING INTERNAL RING STIFFENER DETAILS - SHEET 1 | 80% | 80% | 70% | -10% | 0.047 | 2026-06-05 | 2026-06-05 | 2026-05-15 | 2026-07-17 | 2026-07-17 | 2026-06-17 | 2026-08-24 | 2026-08-24 |  | 2026-09-07 | 2026-09-07 |  | Completed | Completed | Overdue | Follow-Next Week
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2134 | ZWP23 JACKET - LAUNCH CRADLE AND VERTICAL FRAMING INTERNAL RING STIFFENER DETAILS - SHEET 2 | 80% | 80% | 70% | -10% | 0.047 | 2026-06-05 | 2026-06-05 | 2026-05-15 | 2026-07-17 | 2026-07-17 | 2026-06-17 | 2026-08-24 | 2026-08-24 |  | 2026-09-07 | 2026-09-07 |  | Completed | Completed | Overdue | Follow-Next Week
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2135 | ZWP23 JACKET - LAUNCH CRADLE AND VERTICAL FRAMING INTERNAL RING STIFFENER DETAILS - SHEET 3 | 80% | 80% | 70% | -10% | 0.047 | 2026-06-05 | 2026-06-05 | 2026-05-15 | 2026-07-17 | 2026-07-17 | 2026-06-17 | 2026-08-24 | 2026-08-24 |  | 2026-09-07 | 2026-09-07 |  | Completed | Completed | Overdue | Follow-Next Week
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2136 | ZWP23 JACKET - LAUNCH CRADLE AND VERTICAL FRAMING INTERNAL RING STIFFENER DETAILS - SHEET 4 | 80% | 80% | 70% | -10% | 0.047 | 2026-06-05 | 2026-06-05 | 2026-05-15 | 2026-07-17 | 2026-07-17 | 2026-06-17 | 2026-08-24 | 2026-08-24 |  | 2026-09-07 | 2026-09-07 |  | Completed | Completed | Overdue | Follow-Next Week
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2141 | ZWP23 JACKET - PILE CLUSTER ARRANGEMENT | 70% | 70% | 50% | -20% | 0.047 | 2026-06-26 | 2026-06-26 | 2026-05-14 | 2026-08-07 | 2026-08-07 |  | 2026-09-18 | 2026-09-18 |  | 2026-10-02 | 2026-10-02 |  | Completed | Overdue
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2142 | ZWP23 JACKET - PILE SLEEVE DETAILS | 70% | 70% | 50% | -20% | 0.047 | 2026-06-26 | 2026-06-26 | 2026-05-14 | 2026-08-07 | 2026-08-07 |  | 2026-09-18 | 2026-09-18 |  | 2026-10-02 | 2026-10-02 |  | Completed | Overdue
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2143 | ZWP23 JACKET - SKIRT SLEEVE MARKING | 70% | 70% | 70% | 0% | 0.047 | 2026-06-26 | 2026-06-26 | 2026-05-14 | 2026-08-07 | 2026-08-07 | 2026-06-18 | 2026-09-18 | 2026-09-18 |  | 2026-10-02 | 2026-10-02 |  | Completed | Completed
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2144 | ZWP23 JACKET - PILE MAKE-UP | 70% | 70% | 50% | -20% | 0.047 | 2026-06-19 | 2026-06-19 | 2026-06-05 | 2026-07-31 | 2026-07-31 |  | 2026-09-11 | 2026-09-11 |  | 2026-09-25 | 2026-09-25 |  | Completed | Overdue | Follow-Next Week
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2145 | ZWP23 JACKET - PILE MARKING | 70% | 70% | 0% | -70% | 0.047 | 2026-06-26 | 2026-06-26 |  | 2026-08-07 | 2026-08-07 |  | 2026-09-18 | 2026-09-18 |  | 2026-10-02 | 2026-10-02 |  | Overdue | Overdue
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2200 | ZWP23 JACKET - HYDROSTATIC RING DETAILS - SHEET 1 | 70% | 70% | 50% | -20% | 0.047 | 2026-06-19 | 2026-06-19 | 2026-06-18 | 2026-07-31 | 2026-07-31 |  | 2026-09-11 | 2026-09-11 |  | 2026-09-25 | 2026-09-25 |  | Completed | Overdue | Follow-Next Week
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2201 | ZWP23 JACKET - HYDROSTATIC RING DETAILS - SHEET 2 | 70% | 70% | 50% | -20% | 0.047 | 2026-06-19 | 2026-06-19 | 2026-06-18 | 2026-07-31 | 2026-07-31 |  | 2026-09-11 | 2026-09-11 |  | 2026-09-25 | 2026-09-25 |  | Completed | Overdue | Follow-Next Week
ZWP-23 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-2221 | JACKET - JACKET ACCESS LAYOUT AND DETAILS - SHEET 1 | 70% | 70% | 100% | 30% | 0.047 | 2026-07-03 | 2026-07-03 | 2026-06-09 | 2026-08-14 | 2026-08-14 | 2026-06-18 | 2026-09-25 | 2026-09-25 | 2026-08-18 | 2026-10-09 | 2026-10-09 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-23 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-2222 | JACKET - JACKET ACCESS LAYOUT AND DETAILS - SHEET 2 | 70% | 70% | 100% | 30% | 0.047 | 2026-07-03 | 2026-07-03 | 2026-06-09 | 2026-08-14 | 2026-08-14 | 2026-06-18 | 2026-09-25 | 2026-09-25 | 2026-08-18 | 2026-10-09 | 2026-10-09 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-23 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-2223 | JACKET - JACKET ACCESS LAYOUT AND DETAILS - SHEET 3 | 70% | 70% | 100% | 30% | 0.047 | 2026-07-03 | 2026-07-03 | 2026-06-09 | 2026-08-14 | 2026-08-14 | 2026-06-18 | 2026-09-25 | 2026-09-25 | 2026-08-18 | 2026-10-09 | 2026-10-09 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-23 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-2224 | JACKET - JACKET WALKWAY STAIR No 8 LANDING PLANS, SECTION & DETAILS | 70% | 70% | 100% | 30% | 0.047 | 2026-07-03 | 2026-07-03 | 2026-06-09 | 2026-08-14 | 2026-08-14 | 2026-06-18 | 2026-09-25 | 2026-09-25 | 2026-08-18 | 2026-10-09 | 2026-10-09 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-23 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-2225 | JACKET - STAIR No 9 PLANS, SECTIONS & DETAILS | 70% | 70% | 100% | 30% | 0.047 | 2026-07-03 | 2026-07-03 | 2026-06-09 | 2026-08-14 | 2026-08-14 | 2026-06-18 | 2026-09-25 | 2026-09-25 | 2026-08-18 | 2026-10-09 | 2026-10-09 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-23 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-2231 | JACKET - BOATLANDING ARRANGEMENT | 70% | 70% | 100% | 30% | 0.047 | 2026-07-03 | 2026-07-03 | 2026-05-20 | 2026-08-14 | 2026-08-14 | 2026-06-18 | 2026-09-25 | 2026-09-25 | 2026-08-18 | 2026-10-09 | 2026-10-09 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-23 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-2232 | JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 1 | 70% | 70% | 100% | 30% | 0.047 | 2026-07-03 | 2026-07-03 | 2026-05-20 | 2026-08-14 | 2026-08-14 | 2026-06-18 | 2026-09-25 | 2026-09-25 | 2026-08-18 | 2026-10-09 | 2026-10-09 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-23 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-2233 | JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 2 | 70% | 70% | 100% | 30% | 0.047 | 2026-07-03 | 2026-07-03 | 2026-05-20 | 2026-08-14 | 2026-08-14 | 2026-06-18 | 2026-09-25 | 2026-09-25 | 2026-08-18 | 2026-10-09 | 2026-10-09 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-23 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-2234 | JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 3 | 70% | 70% | 100% | 30% | 0.047 | 2026-07-03 | 2026-07-03 | 2026-05-20 | 2026-08-14 | 2026-08-14 | 2026-06-18 | 2026-09-25 | 2026-09-25 | 2026-08-18 | 2026-10-09 | 2026-10-09 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-23 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-2235 | JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 4 | 70% | 70% | 100% | 30% | 0.047 | 2026-07-03 | 2026-07-03 | 2026-05-20 | 2026-08-14 | 2026-08-14 | 2026-06-18 | 2026-09-25 | 2026-09-25 | 2026-08-18 | 2026-10-09 | 2026-10-09 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-23 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-2236 | JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 5 | 70% | 70% | 100% | 30% | 0.047 | 2026-07-03 | 2026-07-03 | 2026-05-20 | 2026-08-14 | 2026-08-14 | 2026-06-18 | 2026-09-25 | 2026-09-25 | 2026-08-18 | 2026-10-09 | 2026-10-09 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-23 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-2237 | JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 6 | 70% | 70% | 100% | 30% | 0.047 | 2026-07-03 | 2026-07-03 | 2026-05-20 | 2026-08-14 | 2026-08-14 | 2026-06-18 | 2026-09-25 | 2026-09-25 | 2026-08-18 | 2026-10-09 | 2026-10-09 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-23 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-2238 | JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 7 | 70% | 70% | 100% | 30% | 0.047 | 2026-07-03 | 2026-07-03 | 2026-05-20 | 2026-08-14 | 2026-08-14 | 2026-06-18 | 2026-09-25 | 2026-09-25 | 2026-08-18 | 2026-10-09 | 2026-10-09 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2241 | ZWP23 JACKET - RISER PROTECTOR | 70% | 70% | 70% | 0% | 0.047 | 2026-06-19 | 2026-06-19 | 2026-06-11 | 2026-07-31 | 2026-07-31 | 2026-07-10 | 2026-09-11 | 2026-09-11 |  | 2026-09-25 | 2026-09-25 |  | Completed | Completed | Follow-Next Week
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2242 | ZWP23 JACKET - RISER PROTECTOR (OPTION) - CANCELLED |  |  | 100% |  | 0.047 | 2026-06-19 | 2026-06-19 | 2026-06-11 | 2026-07-31 | 2026-07-31 | 2026-07-10 | 2026-09-11 | 2026-09-11 | 2026-08-28 | 2026-09-25 | 2026-09-25 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2300 | ZWP23 JACKET - CASING GUIDE ARRANGEMENT | 70% | 70% | 0% | -70% | 0.047 | 2026-06-19 | 2026-06-19 |  | 2026-07-31 | 2026-07-31 |  | 2026-09-11 | 2026-09-11 |  | 2026-09-25 | 2026-09-25 |  | Overdue | Overdue | Follow-Next Week
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2301 | ZWP23 JACKET - CASING GUIDE DETAILS | 70% | 70% | 0% | -70% | 0.047 | 2026-06-19 | 2026-06-19 |  | 2026-07-31 | 2026-07-31 |  | 2026-09-11 | 2026-09-11 |  | 2026-09-25 | 2026-09-25 |  | Overdue | Overdue | Follow-Next Week
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2311 | ZWP23 JACKET - ANODE STRUCTURE AND INSTALLATION | 70% | 70% | 50% | -20% | 0.047 | 2026-07-10 | 2026-07-10 | 2026-04-30 | 2026-08-21 | 2026-08-21 |  | 2026-10-02 | 2026-10-02 |  | 2026-10-16 | 2026-10-16 |  | Completed | Overdue
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2312 | ZWP23 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING ROW 'A' | 70% | 70% | 50% | -20% | 0.047 | 2026-07-10 | 2026-07-10 | 2026-04-30 | 2026-08-21 | 2026-08-21 |  | 2026-10-02 | 2026-10-02 |  | 2026-10-16 | 2026-10-16 |  | Completed | Overdue
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2313 | ZWP23 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING ROW 'B' | 70% | 70% | 50% | -20% | 0.047 | 2026-07-10 | 2026-07-10 | 2026-04-30 | 2026-08-21 | 2026-08-21 |  | 2026-10-02 | 2026-10-02 |  | 2026-10-16 | 2026-10-16 |  | Completed | Overdue
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2314 | ZWP23 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING ROW '1' & '1.1' | 70% | 70% | 50% | -20% | 0.047 | 2026-07-10 | 2026-07-10 | 2026-04-30 | 2026-08-21 | 2026-08-21 |  | 2026-10-02 | 2026-10-02 |  | 2026-10-16 | 2026-10-16 |  | Completed | Overdue
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2315 | ZWP23 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING ROW '2' | 70% | 70% | 50% | -20% | 0.047 | 2026-07-10 | 2026-07-10 | 2026-04-30 | 2026-08-21 | 2026-08-21 |  | 2026-10-02 | 2026-10-02 |  | 2026-10-16 | 2026-10-16 |  | Completed | Overdue
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2316 | ZWP23 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING LAUNCH TRUSS ROW 'Aa' | 70% | 70% | 50% | -20% | 0.047 | 2026-07-10 | 2026-07-10 | 2026-04-30 | 2026-08-21 | 2026-08-21 |  | 2026-10-02 | 2026-10-02 |  | 2026-10-16 | 2026-10-16 |  | Completed | Overdue
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2317 | ZWP23 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING LAUNCH TRUSS ROW 'Bb' | 70% | 70% | 50% | -20% | 0.047 | 2026-07-10 | 2026-07-10 | 2026-04-30 | 2026-08-21 | 2026-08-21 |  | 2026-10-02 | 2026-10-02 |  | 2026-10-16 | 2026-10-16 |  | Completed | Overdue
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2321 | ZWP23 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 14000 | 70% | 70% | 50% | -20% | 0.047 | 2026-07-10 | 2026-07-10 | 2026-04-30 | 2026-08-21 | 2026-08-21 |  | 2026-10-02 | 2026-10-02 |  | 2026-10-16 | 2026-10-16 |  | Completed | Overdue
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2322 | ZWP23 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 26000 | 70% | 70% | 50% | -20% | 0.047 | 2026-07-10 | 2026-07-10 | 2026-04-30 | 2026-08-21 | 2026-08-21 |  | 2026-10-02 | 2026-10-02 |  | 2026-10-16 | 2026-10-16 |  | Completed | Overdue
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2323 | ZWP23 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 38000 | 70% | 70% | 50% | -20% | 0.047 | 2026-07-10 | 2026-07-10 | 2026-04-30 | 2026-08-21 | 2026-08-21 |  | 2026-10-02 | 2026-10-02 |  | 2026-10-16 | 2026-10-16 |  | Completed | Overdue
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2324 | ZWP23 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 52000 | 70% | 70% | 50% | -20% | 0.047 | 2026-07-10 | 2026-07-10 | 2026-04-30 | 2026-08-21 | 2026-08-21 |  | 2026-10-02 | 2026-10-02 |  | 2026-10-16 | 2026-10-16 |  | Completed | Overdue
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2325 | ZWP23 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 66000 | 70% | 70% | 50% | -20% | 0.047 | 2026-07-10 | 2026-07-10 | 2026-04-30 | 2026-08-21 | 2026-08-21 |  | 2026-10-02 | 2026-10-02 |  | 2026-10-16 | 2026-10-16 |  | Completed | Overdue
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2326 | ZWP23 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 79500 | 70% | 70% | 50% | -20% | 0.047 | 2026-07-10 | 2026-07-10 | 2026-04-30 | 2026-08-21 | 2026-08-21 |  | 2026-10-02 | 2026-10-02 |  | 2026-10-16 | 2026-10-16 |  | Completed | Overdue
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2327 | ZWP23 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 93000 | 70% | 70% | 50% | -20% | 0.047 | 2026-07-10 | 2026-07-10 | 2026-04-30 | 2026-08-21 | 2026-08-21 |  | 2026-10-02 | 2026-10-02 |  | 2026-10-16 | 2026-10-16 |  | Completed | Overdue
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2328 | ZWP23 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 107000 | 70% | 70% | 50% | -20% | 0.047 | 2026-07-10 | 2026-07-10 | 2026-04-30 | 2026-08-21 | 2026-08-21 |  | 2026-10-02 | 2026-10-02 |  | 2026-10-16 | 2026-10-16 |  | Completed | Overdue
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2329 | ZWP23 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 121000 | 70% | 70% | 50% | -20% | 0.047 | 2026-07-10 | 2026-07-10 | 2026-04-30 | 2026-08-21 | 2026-08-21 |  | 2026-10-02 | 2026-10-02 |  | 2026-10-16 | 2026-10-16 |  | Completed | Overdue
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2330 | ZWP23 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 133000 | 70% | 70% | 50% | -20% | 0.047 | 2026-07-10 | 2026-07-10 | 2026-04-30 | 2026-08-21 | 2026-08-21 |  | 2026-10-02 | 2026-10-02 |  | 2026-10-16 | 2026-10-16 |  | Completed | Overdue
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2331 | ZWP23 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 144100 | 70% | 70% | 50% | -20% | 0.047 | 2026-07-10 | 2026-07-10 | 2026-04-30 | 2026-08-21 | 2026-08-21 |  | 2026-10-02 | 2026-10-02 |  | 2026-10-16 | 2026-10-16 |  | Completed | Overdue
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2332 | ZWP23 JACKET - ANODE DISTRIBUTION OF PILE CLUSTER | 70% | 70% | 50% | -20% | 0.047 | 2026-07-10 | 2026-07-10 | 2026-04-30 | 2026-08-21 | 2026-08-21 |  | 2026-10-02 | 2026-10-02 |  | 2026-10-16 | 2026-10-16 |  | Completed | Overdue
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2411 | ZWP23 JACKET - INSTALLATION PROCEDURE - CANCELLED |  |  |  |  | 0.047 | 2026-07-17 | 2026-07-17 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-10-09 | 2026-10-09 | 2026-08-28 | 2026-10-23 | 2026-10-23 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2421 | ZWP23 JACKET - INSTALLATION AID CLASH CHECK - CANCELLED\ |  |  |  |  | 0.047 | 2026-07-17 | 2026-07-17 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-10-09 | 2026-10-09 | 2026-08-28 | 2026-10-23 | 2026-10-23 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-XXXX | ZWP23 JACKET - INSTALLATION PROCEDURE - T&I ITEM | 0% | 0% | 0% | 0% |  | 2026-11-06 | 2026-11-06 |  | 2026-12-18 | 2026-12-18 |  | 2027-01-29 | 2027-01-29 |  | 2027-02-12 | 2027-02-12
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-XXXX | ZWP23 JACKET - INSTALLATION AID CLASH CHECK - T&I ITEM | 0% | 0% | 0% | 0% |  | 2026-11-06 | 2026-11-06 |  | 2026-12-18 | 2026-12-18 |  | 2027-01-29 | 2027-01-29 |  | 2027-02-12 | 2027-02-12
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2801 | ZWP23 JACKET - RISER SUPPORT LOCATION | 50% | 50% | 50% | 0% |  | 2026-07-24 | 2026-07-24 | 2026-06-17 | 2026-09-04 | 2026-09-04 |  | 2026-10-16 | 2026-10-16 |  | 2026-10-30 | 2026-10-30 |  | Completed | Follow-This Week
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2802 | ZWP23 JACKET - RISER CLAMP DETAILS SHEET 1 | 0% | 0% | 0% | 0% |  | 2026-09-28 | 2026-09-28 |  | 2026-11-09 | 2026-11-09 |  | 2026-12-21 | 2026-12-21 |  | 2027-01-04 | 2027-01-04
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2803 | ZWP23 JACKET - RISER CLAMP DETAILS SHEET 2 | 0% | 0% | 0% | 0% |  | 2026-09-28 | 2026-09-28 |  | 2026-11-09 | 2026-11-09 |  | 2026-12-21 | 2026-12-21 |  | 2027-01-04 | 2027-01-04
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2804 | ZWP23 JACKET - RISER CLAMP DETAILS SHEET 3 | 0% | 0% | 0% | 0% |  | 2026-09-28 | 2026-09-28 |  | 2026-11-09 | 2026-11-09 |  | 2026-12-21 | 2026-12-21 |  | 2027-01-04 | 2027-01-04
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2805 | ZWP23 JACKET - RISER CLAMP DETAILS SHEET 4 | 0% | 0% | 0% | 0% |  | 2026-09-28 | 2026-09-28 |  | 2026-11-09 | 2026-11-09 |  | 2026-12-21 | 2026-12-21 |  | 2027-01-04 | 2027-01-04
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2900 | ZWP23 JACKET - CLOSURE PLATE DETAILS - SHEET 1 | 70% | 70% | 50% | -20% | 0.047 | 2026-07-17 | 2026-07-17 | 2026-06-11 | 2026-08-28 | 2026-08-28 |  | 2026-10-09 | 2026-10-09 |  | 2026-10-23 | 2026-10-23 |  | Completed | Overdue
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2901 | ZWP23 JACKET - CLOSURE PLATE DETAILS - SHEET 2 | 70% | 70% | 50% | -20% | 0.047 | 2026-07-17 | 2026-07-17 | 2026-06-11 | 2026-08-28 | 2026-08-28 |  | 2026-10-09 | 2026-10-09 |  | 2026-10-23 | 2026-10-23 |  | Completed | Overdue
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2902 | ZWP23 JACKET - LEG PARTITION DETAILS | 70% | 70% | 50% | -20% | 0.047 | 2026-07-17 | 2026-07-17 | 2026-06-11 | 2026-08-28 | 2026-08-28 |  | 2026-10-09 | 2026-10-09 |  | 2026-10-23 | 2026-10-23 |  | Completed | Overdue
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2911 | ZWP23 JACKET - UPENDING ARRANGEMENT AND DETAILS | 70% | 70% | 0% | -70% | 0.047 | 2026-07-17 | 2026-07-17 |  | 2026-08-28 | 2026-08-28 |  | 2026-10-09 | 2026-10-09 |  | 2026-10-23 | 2026-10-23 |  | Overdue | Overdue
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2931 | ZWP23 JACKET - BALLAST / DEBASSAST SCHEMATIC | 50% | 50% | 70% | 20% | 0.047 | 2026-07-24 | 2026-07-24 | 2026-04-30 | 2026-09-04 | 2026-09-04 | 2026-08-21 | 2026-10-16 | 2026-10-16 |  | 2026-10-30 | 2026-10-30 |  | Completed | Completed
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2932 | ZWP23 JACKET - GROUTING SCHEMATIC | 50% | 50% | 70% | 20% | 0.047 | 2026-07-24 | 2026-07-24 | 2026-04-30 | 2026-09-04 | 2026-09-04 | 2026-08-21 | 2026-10-16 | 2026-10-16 |  | 2026-10-30 | 2026-10-30 |  | Completed | Completed
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2933 | ZWP23 JACKET - BALLAST SYSTEM AND GROUTING LINE ROUTING AT ROW A ELEVATION | 50% | 50% | 70% | 20% | 0.047 | 2026-07-24 | 2026-07-24 | 2026-07-21 | 2026-09-04 | 2026-09-04 | 2026-07-30 | 2026-10-16 | 2026-10-16 |  | 2026-10-30 | 2026-10-30 |  | Completed | Completed
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2934 | ZWP23 JACKET - BALLAST SYSTEM AND GROUTING LINE ROUTING AT ROW B ELEVATION | 50% | 50% | 70% | 20% | 0.047 | 2026-07-24 | 2026-07-24 | 2026-07-21 | 2026-09-04 | 2026-09-04 | 2026-07-30 | 2026-10-16 | 2026-10-16 |  | 2026-10-30 | 2026-10-30 |  | Completed | Completed
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2935 | ZWP23 JACKET - BALLAST AND GROUTING SYSTEM SUPPORT DETAILS SHEET 1 | 50% | 50% | 50% | 0% | 0.047 | 2026-07-24 | 2026-07-24 | 2026-07-21 | 2026-09-04 | 2026-09-04 |  | 2026-10-16 | 2026-10-16 |  | 2026-10-30 | 2026-10-30 |  | Completed | Follow-This Week
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2936 | ZWP23 JACKET - BALLAST AND GROUTING SYSTEM SUPPORT DETAILS SHEET 2 | 50% | 50% | 50% | 0% | 0.047 | 2026-07-24 | 2026-07-24 | 2026-07-21 | 2026-09-04 | 2026-09-04 |  | 2026-10-16 | 2026-10-16 |  | 2026-10-30 | 2026-10-30 |  | Completed | Follow-This Week
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2937 | ZWP23 JACKET - BALLAST SYSTEM VALVE DETAILS | 50% | 50% | 50% | 0% | 0.047 | 2026-07-24 | 2026-07-24 | 2026-07-21 | 2026-09-04 | 2026-09-04 |  | 2026-10-16 | 2026-10-16 |  | 2026-10-30 | 2026-10-30 |  | Completed | Follow-This Week
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2938 | ZWP23 JACKET -GROUT, SKIRT SLEEVE VENT AND FLOODING DETAILS AT SKIRT PILE SLEEVE SHEET 1 | 50% | 50% | 50% | 0% | 0.047 | 2026-07-24 | 2026-07-24 | 2026-07-21 | 2026-09-04 | 2026-09-04 |  | 2026-10-16 | 2026-10-16 |  | 2026-10-30 | 2026-10-30 |  | Completed | Follow-This Week
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2939 | ZWP23 JACKET -GROUT, SKIRT SLEEVE VENT AND FLOODING DETAILS AT SKIRT PILE SLEEVE SHEET 2 | 50% | 50% | 50% | 0% | 0.047 | 2026-07-24 | 2026-07-24 | 2026-07-21 | 2026-09-04 | 2026-09-04 |  | 2026-10-16 | 2026-10-16 |  | 2026-10-30 | 2026-10-30 |  | Completed | Follow-This Week
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2940 | ZWP23 JACKET - BALLAST SYSTEM AND GROUTING LINE ROUTING AT EL(+) 8000 | 50% | 50% | 50% | 0% | 0.047 | 2026-07-24 | 2026-07-24 | 2026-07-21 | 2026-09-04 | 2026-09-04 |  | 2026-10-16 | 2026-10-16 |  | 2026-10-30 | 2026-10-30 |  | Completed | Follow-This Week
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2941 | ZWP23 JACKET - GROUT SYSTEM DETAILS | 50% | 50% | 50% | 0% | 0.047 | 2026-07-24 | 2026-07-24 | 2026-07-21 | 2026-09-04 | 2026-09-04 |  | 2026-10-16 | 2026-10-16 |  | 2026-10-30 | 2026-10-30 |  | Completed | Follow-This Week
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2950 | ZWP23 JACKET - LAUNCHING SEQUENCE | 50% | 50% | 0% | -50% | 0.047 | 2026-07-31 | 2026-07-31 |  | 2026-09-11 | 2026-09-11 |  | 2026-10-23 | 2026-10-23 |  | 2026-11-06 | 2026-11-06 |  | Overdue | Follow-Next Week
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2951 | ZWP23 JACKET - UPENDING & LOWERING SEQUENCE | 50% | 50% | 0% | -50% | 0.047 | 2026-07-31 | 2026-07-31 |  | 2026-09-11 | 2026-09-11 |  | 2026-10-23 | 2026-10-23 |  | 2026-11-06 | 2026-11-06 |  | Overdue | Follow-Next Week
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2961 | ZWP23 JACKET - PILE LIFTING & UPENDING | 50% | 50% | 0% | -50% | 0.047 | 2026-07-31 | 2026-07-31 |  | 2026-09-11 | 2026-09-11 |  | 2026-10-23 | 2026-10-23 |  | 2026-11-06 | 2026-11-06 |  | Overdue | Follow-Next Week
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2971 | ZWP23 JACKET - WELD PROFILE CONTROL SHEET 1 | 50% | 50% | 70% | 20% | 0.047 | 2026-07-31 | 2026-07-31 | 2026-08-13 | 2026-09-11 | 2026-09-11 | 2026-08-28 | 2026-10-23 | 2026-10-23 |  | 2026-11-06 | 2026-11-06 |  | Completed | Completed
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2972 | ZWP23 JACKET - WELD PROFILE CONTROL SHEET 2 | 50% | 50% | 70% | 20% | 0.047 | 2026-07-31 | 2026-07-31 | 2026-08-13 | 2026-09-11 | 2026-09-11 | 2026-08-28 | 2026-10-23 | 2026-10-23 |  | 2026-11-06 | 2026-11-06 |  | Completed | Completed
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2973 | ZWP23 JACKET - WELD PROFILE CONTROL SHEET 3 | 50% | 50% | 70% | 20% | 0.047 | 2026-07-31 | 2026-07-31 | 2026-08-13 | 2026-09-11 | 2026-09-11 | 2026-08-28 | 2026-10-23 | 2026-10-23 |  | 2026-11-06 | 2026-11-06 |  | Completed | Completed
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2974 | ZWP23 JACKET - WELD PROFILE CONTROL SHEET 4 | 50% | 50% | 70% | 20% | 0.047 | 2026-07-31 | 2026-07-31 | 2026-08-13 | 2026-09-11 | 2026-09-11 | 2026-08-28 | 2026-10-23 | 2026-10-23 |  | 2026-11-06 | 2026-11-06 |  | Completed | Completed
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2975 | ZWP23 JACKET - WELD PROFILE CONTROL SHEET 5 | 50% | 50% | 70% | 20% | 0.047 | 2026-07-31 | 2026-07-31 | 2026-08-13 | 2026-09-11 | 2026-09-11 | 2026-08-28 | 2026-10-23 | 2026-10-23 |  | 2026-11-06 | 2026-11-06 |  | Completed | Completed
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2976 | ZWP23 JACKET - WELD PROFILE CONTROL SHEET 6 | 50% | 50% | 70% | 20% | 0.047 | 2026-07-31 | 2026-07-31 | 2026-08-13 | 2026-09-11 | 2026-09-11 | 2026-08-28 | 2026-10-23 | 2026-10-23 |  | 2026-11-06 | 2026-11-06 |  | Completed | Completed
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2981 | ZWP23 JACKET - LEG PAINT MARKING DETAILS - SHEET 1 | 50% | 50% | 0% | -50% | 0.047 | 2026-07-31 | 2026-07-31 |  | 2026-09-11 | 2026-09-11 |  | 2026-10-23 | 2026-10-23 |  | 2026-11-06 | 2026-11-06 |  | Overdue | Follow-Next Week
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2982 | ZWP23 JACKET - LEG PAINT MARKING DETAILS - SHEET 2 | 50% | 50% | 0% | -50% | 0.047 | 2026-07-31 | 2026-07-31 |  | 2026-09-11 | 2026-09-11 |  | 2026-10-23 | 2026-10-23 |  | 2026-11-06 | 2026-11-06 |  | Overdue | Follow-Next Week
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2984 | ZWP23 JACKET - PULLING LUG DETAILS | 50% | 50% | 70% | 20% | 0.047 | 2026-07-31 | 2026-07-31 | 2026-07-17 | 2026-09-11 | 2026-09-11 | 2026-07-30 | 2026-10-23 | 2026-10-23 |  | 2026-11-06 | 2026-11-06 |  | Completed | Completed
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2991 | ZWP23 JACKET - JACKET TRANSPORTATION ARRANGEMENT | 50% | 50% | 0% | -50% | 0.047 | 2026-07-31 | 2026-07-31 |  | 2026-09-11 | 2026-09-11 |  | 2026-10-23 | 2026-10-23 |  | 2026-11-06 | 2026-11-06 |  | Overdue | Follow-Next Week
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2994 | ZWP23 JACKET - VORTEX SHEDDING PREVENTION - SHEET 1 | 50% | 50% | 0% | -50% | 0.047 | 2026-07-31 | 2026-07-31 |  | 2026-09-11 | 2026-09-11 |  | 2026-10-23 | 2026-10-23 |  | 2026-11-06 | 2026-11-06 |  | Overdue | Follow-Next Week
ZWP-23 | Drawing | MM-ZTK-1F-ZWP23-STR-DWG-2995 | ZWP23 JACKET - VORTEX SHEDDING PREVENTION - SHEET 2 | 50% | 50% | 0% | -50% | 0.047 | 2026-07-31 | 2026-07-31 |  | 2026-09-11 | 2026-09-11 |  | 2026-10-23 | 2026-10-23 |  | 2026-11-06 | 2026-11-06 |  | Overdue | Follow-Next Week
ZWP-23 | Drawing | AS-BUILT DRAWINGS (TO BE CONFIRMED) | ZWP23 AS-BUILT DRAWINGS | 0% | 0% | 0% | 0% | 1.5
ZWP-22 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-0051 | JACKET - GENERAL NOTES - SHEET 1 | 70% | 70% | 100% | 30% | 0.009 | 2026-07-03 | 2026-07-03 | 2026-06-02 | 2026-08-14 | 2026-08-14 | 2026-06-18 | 2026-09-25 | 2026-09-25 | 2026-08-11 | 2026-10-09 | 2026-10-09 | 2026-08-21 | Completed | Completed | Completed | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-0052 | JACKET - GENERAL NOTES - SHEET 2 | 70% | 70% | 100% | 30% | 0.009 | 2026-07-03 | 2026-07-03 | 2026-06-02 | 2026-08-14 | 2026-08-14 | 2026-06-18 | 2026-09-25 | 2026-09-25 | 2026-08-11 | 2026-10-09 | 2026-10-09 | 2026-08-21 | Completed | Completed | Completed | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-0061 | JACKET - STANDARD DETAILS WELD PROFILE - SHEET 1 | 70% | 70% | 100% | 30% | 0.047 | 2026-07-03 | 2026-07-03 | 2026-06-02 | 2026-08-14 | 2026-08-14 | 2026-06-18 | 2026-09-25 | 2026-09-25 | 2026-08-11 | 2026-10-09 | 2026-10-09 | 2026-08-21 | Completed | Completed | Completed | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-0062 | JACKET - STANDARD DETAILS WELD PROFILE - SHEET 2 | 70% | 70% | 100% | 30% | 0.047 | 2026-07-03 | 2026-07-03 | 2026-06-02 | 2026-08-14 | 2026-08-14 | 2026-06-18 | 2026-09-25 | 2026-09-25 | 2026-08-11 | 2026-10-09 | 2026-10-09 | 2026-08-21 | Completed | Completed | Completed | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2001 | ZWP22 JACKET - DRAWING INDEX - SHEET 1 | 70% | 70% | 0% | -70% | 0.047 | 2026-07-03 | 2026-07-03 |  | 2026-08-14 | 2026-08-14 |  | 2026-09-25 | 2026-09-25 |  | 2026-10-09 | 2026-10-09 |  | Overdue | Overdue
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2002 | ZWP22 JACKET - DRAWING INDEX - SHEET 2 | 70% | 70% | 0% | -70% | 0.047 | 2026-07-03 | 2026-07-03 |  | 2026-08-14 | 2026-08-14 |  | 2026-09-25 | 2026-09-25 |  | 2026-10-09 | 2026-10-09 |  | Overdue | Overdue
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2100 | ZWP22 JACKET - VERTICAL FRAMING ROW 'A' | 70% | 70% | 70% | 0% | 0.047 | 2026-07-03 | 2026-07-03 | 2026-04-18 | 2026-08-14 | 2026-08-14 | 2026-07-22 | 2026-09-21 | 2026-09-21 |  | 2026-10-05 | 2026-10-05 |  | Completed | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2101 | ZWP22 JACKET - VERTICAL FRAMING ROW 'B' | 70% | 70% | 70% | 0% | 0.047 | 2026-07-03 | 2026-07-03 | 2026-04-18 | 2026-08-14 | 2026-08-14 | 2026-07-22 | 2026-09-21 | 2026-09-21 |  | 2026-10-05 | 2026-10-05 |  | Completed | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2102 | ZWP22 JACKET - VERTICAL FRAMING ROW '1' & '1.1' | 70% | 70% | 70% | 0% | 0.047 | 2026-07-03 | 2026-07-03 | 2026-04-18 | 2026-08-14 | 2026-08-14 | 2026-07-22 | 2026-09-21 | 2026-09-21 |  | 2026-10-05 | 2026-10-05 |  | Completed | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2103 | ZWP22 JACKET - VERTICAL FRAMING ROW '2' | 70% | 70% | 70% | 0% | 0.047 | 2026-07-03 | 2026-07-03 | 2026-04-18 | 2026-08-14 | 2026-08-14 | 2026-07-22 | 2026-09-21 | 2026-09-21 |  | 2026-10-05 | 2026-10-05 |  | Completed | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2104 | ZWP22 JACKET - VERTICAL FRAMING LAUNCH TRUSS ROW 'Aa' | 70% | 70% | 70% | 0% | 0.047 | 2026-07-03 | 2026-07-03 | 2026-04-18 | 2026-08-14 | 2026-08-14 | 2026-07-22 | 2026-09-21 | 2026-09-21 |  | 2026-10-05 | 2026-10-05 |  | Completed | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2105 | ZWP22 JACKET - VERTICAL FRAMING LAUNCH TRUSS ROW 'Bb' | 70% | 70% | 70% | 0% | 0.047 | 2026-07-03 | 2026-07-03 | 2026-04-18 | 2026-08-14 | 2026-08-14 | 2026-07-22 | 2026-09-21 | 2026-09-21 |  | 2026-10-05 | 2026-10-05 |  | Completed | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2110 | ZWP22 JACKET - HORIZONTAL FRAMING PLAN AT EL(+) 8000 | 70% | 70% | 70% | 0% | 0.047 | 2026-07-03 | 2026-07-03 | 2026-04-18 | 2026-08-14 | 2026-08-14 | 2026-07-22 | 2026-09-21 | 2026-09-21 |  | 2026-10-05 | 2026-10-05 |  | Completed | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2111 | ZWP22 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 3000 | 70% | 70% | 70% | 0% | 0.047 | 2026-07-03 | 2026-07-03 | 2026-04-18 | 2026-08-14 | 2026-08-14 | 2026-07-22 | 2026-09-21 | 2026-09-21 |  | 2026-10-05 | 2026-10-05 |  | Completed | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2112 | ZWP22 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 14000 | 70% | 70% | 70% | 0% | 0.047 | 2026-07-03 | 2026-07-03 | 2026-04-18 | 2026-08-14 | 2026-08-14 | 2026-07-22 | 2026-09-21 | 2026-09-21 |  | 2026-10-05 | 2026-10-05 |  | Completed | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2113 | ZWP22 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 26000 | 70% | 70% | 70% | 0% | 0.047 | 2026-07-03 | 2026-07-03 | 2026-04-18 | 2026-08-14 | 2026-08-14 | 2026-07-22 | 2026-09-21 | 2026-09-21 |  | 2026-10-05 | 2026-10-05 |  | Completed | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2114 | ZWP22 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 38000 | 70% | 70% | 70% | 0% | 0.047 | 2026-07-03 | 2026-07-03 | 2026-04-18 | 2026-08-14 | 2026-08-14 | 2026-07-22 | 2026-09-21 | 2026-09-21 |  | 2026-10-05 | 2026-10-05 |  | Completed | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2115 | ZWP22 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 52000 | 70% | 70% | 70% | 0% | 0.047 | 2026-07-03 | 2026-07-03 | 2026-04-18 | 2026-08-14 | 2026-08-14 | 2026-07-22 | 2026-09-21 | 2026-09-21 |  | 2026-10-05 | 2026-10-05 |  | Completed | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2116 | ZWP22 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 66000 | 70% | 70% | 70% | 0% | 0.047 | 2026-07-03 | 2026-07-03 | 2026-04-18 | 2026-08-14 | 2026-08-14 | 2026-07-22 | 2026-09-21 | 2026-09-21 |  | 2026-10-05 | 2026-10-05 |  | Completed | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2117 | ZWP22 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 79500 | 70% | 70% | 70% | 0% | 0.047 | 2026-07-03 | 2026-07-03 | 2026-04-18 | 2026-08-14 | 2026-08-14 | 2026-07-22 | 2026-09-21 | 2026-09-21 |  | 2026-10-05 | 2026-10-05 |  | Completed | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2118 | ZWP22 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 93000 | 70% | 70% | 70% | 0% | 0.047 | 2026-07-03 | 2026-07-03 | 2026-04-18 | 2026-08-14 | 2026-08-14 | 2026-07-22 | 2026-09-21 | 2026-09-21 |  | 2026-10-05 | 2026-10-05 |  | Completed | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2119 | ZWP22 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 103000 | 70% | 70% | 70% | 0% | 0.047 | 2026-07-03 | 2026-07-03 | 2026-04-18 | 2026-08-14 | 2026-08-14 | 2026-07-22 | 2026-09-21 | 2026-09-21 |  | 2026-10-05 | 2026-10-05 |  | Completed | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2120 | ZWP22 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 113000 | 70% | 70% | 70% | 0% | 0.047 | 2026-07-03 | 2026-07-03 | 2026-04-18 | 2026-08-14 | 2026-08-14 | 2026-07-22 | 2026-09-21 | 2026-09-21 |  | 2026-10-05 | 2026-10-05 |  | Completed | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2121 | ZWP22 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 126500 | 70% | 70% | 70% | 0% | 0.047 | 2026-07-03 | 2026-07-03 | 2026-04-18 | 2026-08-14 | 2026-08-14 | 2026-07-22 | 2026-09-21 | 2026-09-21 |  | 2026-10-05 | 2026-10-05 |  | Completed | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2122 | ZWP22 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 137900 | 70% | 70% | 70% | 0% | 0.047 | 2026-07-03 | 2026-07-03 | 2026-04-18 | 2026-08-14 | 2026-08-14 | 2026-07-22 | 2026-09-21 | 2026-09-21 |  | 2026-10-05 | 2026-10-05 |  | Completed | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2123 | ZWP22 JACKET - FRAMING SECTIONS | 70% | 70% | 70% | 0% | 0.047 | 2026-07-03 | 2026-07-03 | 2026-04-18 | 2026-08-14 | 2026-08-14 | 2026-07-22 | 2026-09-21 | 2026-09-21 |  | 2026-10-05 | 2026-10-05 |  | Completed | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2130 | ZWP22 JACKET - LAUNCH CRADLE GENERAL ARRANGEMENT | 70% | 70% | 70% | 0% | 0.047 | 2026-07-03 | 2026-07-03 | 2026-05-08 | 2026-08-14 | 2026-08-14 | 2026-07-02 | 2026-09-21 | 2026-09-21 |  | 2026-10-05 | 2026-10-05 |  | Completed | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2131 | ZWP22 JACKET - LAUNCH CRADLE DETAILS - SHEET 1 | 70% | 70% | 70% | 0% | 0.047 | 2026-07-03 | 2026-07-03 | 2026-05-08 | 2026-08-14 | 2026-08-14 | 2026-07-02 | 2026-09-21 | 2026-09-21 |  | 2026-10-05 | 2026-10-05 |  | Completed | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2132 | ZWP22 JACKET - LAUNCH CRADLE DETAILS - SHEET 2 | 70% | 70% | 100% | 30% | 0.047 | 2026-07-03 | 2026-07-03 | 2026-05-08 | 2026-08-14 | 2026-08-14 | 2026-07-02 | 2026-09-21 | 2026-09-21 | 2026-08-14 | 2026-10-05 | 2026-10-05 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2133 | ZWP22 JACKET - LAUNCH CRADLE AND VERTICAL FRAMING INTERNAL RING STIFFENER DETAILS - SHEET 1 | 70% | 70% | 50% | -20% | 0.047 | 2026-07-03 | 2026-07-03 | 2026-05-15 | 2026-08-14 | 2026-08-14 |  | 2026-09-21 | 2026-09-21 |  | 2026-10-05 | 2026-10-05 |  | Completed | Overdue
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2134 | ZWP22 JACKET - LAUNCH CRADLE AND VERTICAL FRAMING INTERNAL RING STIFFENER DETAILS - SHEET 2 | 70% | 70% | 50% | -20% | 0.047 | 2026-07-03 | 2026-07-03 | 2026-05-15 | 2026-08-14 | 2026-08-14 |  | 2026-09-21 | 2026-09-21 |  | 2026-10-05 | 2026-10-05 |  | Completed | Overdue
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2135 | ZWP22 JACKET - LAUNCH CRADLE AND VERTICAL FRAMING INTERNAL RING STIFFENER DETAILS - SHEET 3 | 70% | 70% | 50% | -20% | 0.047 | 2026-07-03 | 2026-07-03 | 2026-05-15 | 2026-08-14 | 2026-08-14 |  | 2026-09-21 | 2026-09-21 |  | 2026-10-05 | 2026-10-05 |  | Completed | Overdue
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2136 | ZWP22 JACKET - LAUNCH CRADLE AND VERTICAL FRAMING INTERNAL RING STIFFENER DETAILS - SHEET 4 | 70% | 70% | 70% | 0% | 0.047 | 2026-07-03 | 2026-07-03 | 2026-05-15 | 2026-08-14 | 2026-08-14 | 2026-07-02 | 2026-09-21 | 2026-09-21 |  | 2026-10-05 | 2026-10-05 |  | Completed | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2141 | ZWP22 JACKET - PILE CLUSTER ARRANGEMENT | 50% | 50% | 50% | 0% | 0.047 | 2026-07-24 | 2026-07-24 | 2026-05-14 | 2026-09-04 | 2026-09-04 |  | 2026-10-16 | 2026-10-16 |  | 2026-10-30 | 2026-10-30 |  | Completed | Follow-This Week
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2142 | ZWP22 JACKET - PILE SLEEVE DETAILS | 50% | 50% | 50% | 0% | 0.047 | 2026-07-24 | 2026-07-24 | 2026-05-14 | 2026-09-04 | 2026-09-04 |  | 2026-10-16 | 2026-10-16 |  | 2026-10-30 | 2026-10-30 |  | Completed | Follow-This Week
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2143 | ZWP22 JACKET - SKIRT SLEEVE MARKING | 50% | 50% | 70% | 20% | 0.047 | 2026-07-24 | 2026-07-24 | 2026-05-14 | 2026-09-04 | 2026-09-04 | 2026-06-18 | 2026-10-16 | 2026-10-16 |  | 2026-10-30 | 2026-10-30 |  | Completed | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2144 | ZWP22 JACKET - PILE MAKE-UP | 70% | 70% | 50% | -20% | 0.047 | 2026-07-17 | 2026-07-17 | 2026-06-05 | 2026-08-28 | 2026-08-28 |  | 2026-10-09 | 2026-10-09 |  | 2026-10-23 | 2026-10-23 |  | Completed | Overdue
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2145 | ZWP22 JACKET - PILE MARKING | 50% | 50% | 0% | -50% | 0.047 | 2026-07-24 | 2026-07-24 |  | 2026-09-04 | 2026-09-04 |  | 2026-10-16 | 2026-10-16 |  | 2026-10-30 | 2026-10-30 |  | Overdue | Follow-This Week
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2200 | ZWP22 JACKET - HYDROSTATIC RING DETAILS - SHEET 1 | 70% | 70% | 50% | -20% | 0.047 | 2026-07-17 | 2026-07-17 | 2026-07-02 | 2026-08-28 | 2026-08-28 |  | 2026-10-09 | 2026-10-09 |  | 2026-10-23 | 2026-10-23 |  | Completed | Overdue
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2201 | ZWP22 JACKET - HYDROSTATIC RING DETAILS - SHEET 2 | 70% | 70% | 50% | -20% | 0.047 | 2026-07-17 | 2026-07-17 | 2026-07-02 | 2026-08-28 | 2026-08-28 |  | 2026-10-09 | 2026-10-09 |  | 2026-10-23 | 2026-10-23 |  | Completed | Overdue
ZWP-22 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-2221 | JACKET - JACKET ACCESS LAYOUT AND DETAILS - SHEET 1 | 50% | 50% | 100% | 50% | 0.047 | 2026-07-31 | 2026-07-31 | 2026-06-09 | 2026-09-11 | 2026-09-11 | 2026-06-18 | 2026-10-23 | 2026-10-23 | 2026-08-18 | 2026-11-06 | 2026-11-06 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-2222 | JACKET - JACKET ACCESS LAYOUT AND DETAILS - SHEET 2 | 50% | 50% | 100% | 50% | 0.047 | 2026-07-31 | 2026-07-31 | 2026-06-09 | 2026-09-11 | 2026-09-11 | 2026-06-18 | 2026-10-23 | 2026-10-23 | 2026-08-18 | 2026-11-06 | 2026-11-06 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-2223 | JACKET - JACKET ACCESS LAYOUT AND DETAILS - SHEET 3 | 50% | 50% | 100% | 50% | 0.047 | 2026-07-31 | 2026-07-31 | 2026-06-09 | 2026-09-11 | 2026-09-11 | 2026-06-18 | 2026-10-23 | 2026-10-23 | 2026-08-18 | 2026-11-06 | 2026-11-06 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-2224 | JACKET - JACKET WALKWAY STAIR No 8 LANDING PLANS, SECTION & DETAILS | 50% | 50% | 100% | 50% | 0.047 | 2026-07-31 | 2026-07-31 | 2026-06-09 | 2026-09-11 | 2026-09-11 | 2026-06-18 | 2026-10-23 | 2026-10-23 | 2026-08-18 | 2026-11-06 | 2026-11-06 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-2225 | JACKET - STAIR No 9 PLANS, SECTIONS & DETAILS | 50% | 50% | 100% | 50% | 0.047 | 2026-07-31 | 2026-07-31 | 2026-06-09 | 2026-09-11 | 2026-09-11 | 2026-06-18 | 2026-10-23 | 2026-10-23 | 2026-08-18 | 2026-11-06 | 2026-11-06 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-2231 | JACKET - BOATLANDING ARRANGEMENT | 50% | 50% | 100% | 50% | 0.047 | 2026-07-31 | 2026-07-31 | 2026-05-20 | 2026-09-11 | 2026-09-11 | 2026-06-18 | 2026-10-23 | 2026-10-23 | 2026-08-18 | 2026-11-06 | 2026-11-06 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-2232 | JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 1 | 50% | 50% | 100% | 50% | 0.047 | 2026-07-31 | 2026-07-31 | 2026-05-20 | 2026-09-11 | 2026-09-11 | 2026-06-18 | 2026-10-23 | 2026-10-23 | 2026-08-18 | 2026-11-06 | 2026-11-06 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-2233 | JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 2 | 50% | 50% | 100% | 50% | 0.047 | 2026-07-31 | 2026-07-31 | 2026-05-20 | 2026-09-11 | 2026-09-11 | 2026-06-18 | 2026-10-23 | 2026-10-23 | 2026-08-18 | 2026-11-06 | 2026-11-06 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-2234 | JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 3 | 50% | 50% | 100% | 50% | 0.047 | 2026-07-31 | 2026-07-31 | 2026-05-20 | 2026-09-11 | 2026-09-11 | 2026-06-18 | 2026-10-23 | 2026-10-23 | 2026-08-18 | 2026-11-06 | 2026-11-06 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-2235 | JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 4 | 50% | 50% | 100% | 50% | 0.047 | 2026-07-31 | 2026-07-31 | 2026-05-20 | 2026-09-11 | 2026-09-11 | 2026-06-18 | 2026-10-23 | 2026-10-23 | 2026-08-18 | 2026-11-06 | 2026-11-06 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-2236 | JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 5 | 50% | 50% | 100% | 50% | 0.047 | 2026-07-31 | 2026-07-31 | 2026-05-20 | 2026-09-11 | 2026-09-11 | 2026-06-18 | 2026-10-23 | 2026-10-23 | 2026-08-18 | 2026-11-06 | 2026-11-06 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-2237 | JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 6 | 50% | 50% | 100% | 50% | 0.047 | 2026-07-31 | 2026-07-31 | 2026-05-20 | 2026-09-11 | 2026-09-11 | 2026-06-18 | 2026-10-23 | 2026-10-23 | 2026-08-18 | 2026-11-06 | 2026-11-06 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-2238 | JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 7 | 50% | 50% | 100% | 50% | 0.047 | 2026-07-31 | 2026-07-31 | 2026-05-20 | 2026-09-11 | 2026-09-11 | 2026-06-18 | 2026-10-23 | 2026-10-23 | 2026-08-18 | 2026-11-06 | 2026-11-06 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2241 | ZWP22 JACKET - RISER PROTECTOR | 70% | 70% | 70% | 0% | 0.047 | 2026-07-17 | 2026-07-17 | 2026-06-11 | 2026-08-28 | 2026-08-28 | 2026-07-10 | 2026-10-09 | 2026-10-09 |  | 2026-10-23 | 2026-10-23 |  | Completed | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2242 | ZWP22 JACKET - RISER PROTECTOR (OPTION) - CANCELLED |  |  | 100% |  | 0.047 | 2026-07-17 | 2026-07-17 | 2026-06-11 | 2026-08-28 | 2026-08-28 | 2026-07-10 | 2026-10-09 | 2026-10-09 | 2026-08-28 | 2026-10-23 | 2026-10-23 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2300 | ZWP22 JACKET - CASING GUIDE ARRANGEMENT | 70% | 70% | 0% | -70% | 0.047 | 2026-07-17 | 2026-07-17 |  | 2026-08-28 | 2026-08-28 |  | 2026-10-09 | 2026-10-09 |  | 2026-10-23 | 2026-10-23 |  | Overdue | Overdue
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2301 | ZWP22 JACKET - CASING GUIDE DETAILS | 70% | 70% | 0% | -70% | 0.047 | 2026-07-17 | 2026-07-17 |  | 2026-08-28 | 2026-08-28 |  | 2026-10-09 | 2026-10-09 |  | 2026-10-23 | 2026-10-23 |  | Overdue | Overdue
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2311 | ZWP22 JACKET - ANODE STRUCTURE AND INSTALLATION | 50% | 50% | 50% | 0% | 0.047 | 2026-08-07 | 2026-08-07 | 2026-04-30 | 2026-09-18 | 2026-09-18 |  | 2026-10-30 | 2026-10-30 |  | 2026-11-13 | 2026-11-13 |  | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2312 | ZWP22 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING ROW 'A' | 50% | 50% | 50% | 0% | 0.047 | 2026-08-07 | 2026-08-07 | 2026-04-30 | 2026-09-18 | 2026-09-18 |  | 2026-10-30 | 2026-10-30 |  | 2026-11-13 | 2026-11-13 |  | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2313 | ZWP22 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING ROW 'B' | 50% | 50% | 50% | 0% | 0.047 | 2026-08-07 | 2026-08-07 | 2026-04-30 | 2026-09-18 | 2026-09-18 |  | 2026-10-30 | 2026-10-30 |  | 2026-11-13 | 2026-11-13 |  | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2314 | ZWP22 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING ROW '1' & '1.1' | 50% | 50% | 50% | 0% | 0.047 | 2026-08-07 | 2026-08-07 | 2026-04-30 | 2026-09-18 | 2026-09-18 |  | 2026-10-30 | 2026-10-30 |  | 2026-11-13 | 2026-11-13 |  | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2315 | ZWP22 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING ROW '2' | 50% | 50% | 50% | 0% | 0.047 | 2026-08-07 | 2026-08-07 | 2026-04-30 | 2026-09-18 | 2026-09-18 |  | 2026-10-30 | 2026-10-30 |  | 2026-11-13 | 2026-11-13 |  | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2316 | ZWP22 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING LAUNCH TRUSS ROW 'Aa' | 50% | 50% | 50% | 0% | 0.047 | 2026-08-07 | 2026-08-07 | 2026-04-30 | 2026-09-18 | 2026-09-18 |  | 2026-10-30 | 2026-10-30 |  | 2026-11-13 | 2026-11-13 |  | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2317 | ZWP22 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING LAUNCH TRUSS ROW 'Bb' | 50% | 50% | 50% | 0% | 0.047 | 2026-08-07 | 2026-08-07 | 2026-04-30 | 2026-09-18 | 2026-09-18 |  | 2026-10-30 | 2026-10-30 |  | 2026-11-13 | 2026-11-13 |  | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2321 | ZWP22 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 14000 | 50% | 50% | 50% | 0% | 0.047 | 2026-08-07 | 2026-08-07 | 2026-04-30 | 2026-09-18 | 2026-09-18 |  | 2026-10-30 | 2026-10-30 |  | 2026-11-13 | 2026-11-13 |  | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2322 | ZWP22 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 26000 | 50% | 50% | 50% | 0% | 0.047 | 2026-08-07 | 2026-08-07 | 2026-04-30 | 2026-09-18 | 2026-09-18 |  | 2026-10-30 | 2026-10-30 |  | 2026-11-13 | 2026-11-13 |  | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2323 | ZWP22 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 38000 | 50% | 50% | 50% | 0% | 0.047 | 2026-08-07 | 2026-08-07 | 2026-04-30 | 2026-09-18 | 2026-09-18 |  | 2026-10-30 | 2026-10-30 |  | 2026-11-13 | 2026-11-13 |  | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2324 | ZWP22 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 52000 | 50% | 50% | 50% | 0% | 0.047 | 2026-08-07 | 2026-08-07 | 2026-04-30 | 2026-09-18 | 2026-09-18 |  | 2026-10-30 | 2026-10-30 |  | 2026-11-13 | 2026-11-13 |  | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2325 | ZWP22 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 66000 | 50% | 50% | 50% | 0% | 0.047 | 2026-08-07 | 2026-08-07 | 2026-04-30 | 2026-09-18 | 2026-09-18 |  | 2026-10-30 | 2026-10-30 |  | 2026-11-13 | 2026-11-13 |  | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2326 | ZWP22 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 79500 | 50% | 50% | 50% | 0% | 0.047 | 2026-08-07 | 2026-08-07 | 2026-04-30 | 2026-09-18 | 2026-09-18 |  | 2026-10-30 | 2026-10-30 |  | 2026-11-13 | 2026-11-13 |  | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2327 | ZWP22 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 93000 | 50% | 50% | 50% | 0% | 0.047 | 2026-08-07 | 2026-08-07 | 2026-04-30 | 2026-09-18 | 2026-09-18 |  | 2026-10-30 | 2026-10-30 |  | 2026-11-13 | 2026-11-13 |  | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2328 | ZWP22 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 103000 | 50% | 50% | 50% | 0% | 0.047 | 2026-08-07 | 2026-08-07 | 2026-04-30 | 2026-09-18 | 2026-09-18 |  | 2026-10-30 | 2026-10-30 |  | 2026-11-13 | 2026-11-13 |  | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2329 | ZWP22 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 113000 | 50% | 50% | 50% | 0% | 0.047 | 2026-08-07 | 2026-08-07 | 2026-04-30 | 2026-09-18 | 2026-09-18 |  | 2026-10-30 | 2026-10-30 |  | 2026-11-13 | 2026-11-13 |  | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2330 | ZWP22 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 126500 | 50% | 50% | 50% | 0% | 0.047 | 2026-08-07 | 2026-08-07 | 2026-04-30 | 2026-09-18 | 2026-09-18 |  | 2026-10-30 | 2026-10-30 |  | 2026-11-13 | 2026-11-13 |  | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2331 | ZWP22 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 137900 | 50% | 50% | 50% | 0% | 0.047 | 2026-08-07 | 2026-08-07 | 2026-04-30 | 2026-09-18 | 2026-09-18 |  | 2026-10-30 | 2026-10-30 |  | 2026-11-13 | 2026-11-13 |  | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2332 | ZWP22 JACKET - ANODE DISTRIBUTION OF PILE CLUSTER | 50% | 50% | 50% | 0% | 0.047 | 2026-08-07 | 2026-08-07 | 2026-04-30 | 2026-09-18 | 2026-09-18 |  | 2026-10-30 | 2026-10-30 |  | 2026-11-13 | 2026-11-13 |  | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2411 | ZWP22 JACKET - INSTALLATION PROCEDURE CANCELLED | 50% | 50% | 100% | 50% | 0.047 | 2026-08-14 | 2026-08-14 | 2026-08-28 | 2026-09-25 | 2026-09-25 | 2026-08-28 | 2026-11-06 | 2026-11-06 | 2026-08-28 | 2026-11-20 | 2026-11-20 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2421 | ZWP22 JACKET - INSTALLATION AID CLASH CHECK - CANCELLED | 50% | 50% | 100% | 50% | 0.047 | 2026-08-14 | 2026-08-14 | 2026-08-28 | 2026-09-25 | 2026-09-25 | 2026-08-28 | 2026-11-06 | 2026-11-06 | 2026-08-28 | 2026-11-20 | 2026-11-20 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-XXXX | ZWP22 JACKET - INSTALLATION PROCEDURE - T&I ITEM | 0% | 0% | 0% | 0% |  | 2026-12-04 | 2026-12-04 |  | 2027-01-15 | 2027-01-15 |  | 2027-02-26 | 2027-02-26 |  | 2027-03-12 | 2027-03-12
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-XXXX | ZWP22 JACKET - INSTALLATION AID CLASH CHECK - T&I ITEM | 0% | 0% | 0% | 0% |  | 2026-12-04 | 2026-12-04 |  | 2027-01-15 | 2027-01-15 |  | 2027-02-26 | 2027-02-26 |  | 2027-03-12 | 2027-03-12
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2801 | ZWP22 JACKET - RISER SUPPORT LOCATION | 50% | 50% | 50% | 0% |  | 2026-08-21 | 2026-08-21 | 2026-06-17 | 2026-10-02 | 2026-10-02 |  | 2026-11-13 | 2026-11-13 |  | 2026-11-27 | 2026-11-27 |  | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2802 | ZWP22 JACKET - RISER CLAMP DETAILS SHEET 1 | 0% | 0% | 0% | 0% |  | 2026-10-26 | 2026-10-26 |  | 2026-12-07 | 2026-12-07 |  | 2027-01-18 | 2027-01-18 |  | 2027-02-01 | 2027-02-01
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2803 | ZWP22 JACKET - RISER CLAMP DETAILS SHEET 2 | 0% | 0% | 0% | 0% |  | 2026-10-26 | 2026-10-26 |  | 2026-12-07 | 2026-12-07 |  | 2027-01-18 | 2027-01-18 |  | 2027-02-01 | 2027-02-01
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2804 | ZWP22 JACKET - RISER CLAMP DETAILS SHEET 3 | 0% | 0% | 0% | 0% |  | 2026-10-26 | 2026-10-26 |  | 2026-12-07 | 2026-12-07 |  | 2027-01-18 | 2027-01-18 |  | 2027-02-01 | 2027-02-01
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2805 | ZWP22 JACKET - RISER CLAMP DETAILS SHEET 4 | 0% | 0% | 0% | 0% |  | 2026-10-26 | 2026-10-26 |  | 2026-12-07 | 2026-12-07 |  | 2027-01-18 | 2027-01-18 |  | 2027-02-01 | 2027-02-01
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2806 | ZWP22 JACKET - RISER CLAMP DETAILS SHEET 5 | 0% | 0% | 0% | 0% |  | 2026-10-26 | 2026-10-26 |  | 2026-12-07 | 2026-12-07 |  | 2027-01-18 | 2027-01-18 |  | 2027-02-01 | 2027-02-01
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2807 | ZWP22 JACKET - RISER CLAMP DETAILS SHEET 6 | 0% | 0% | 0% | 0% |  | 2026-10-26 | 2026-10-26 |  | 2026-12-07 | 2026-12-07 |  | 2027-01-18 | 2027-01-18 |  | 2027-02-01 | 2027-02-01
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2808 | ZWP22 JACKET - RISER CLAMP DETAILS SHEET 7 | 0% | 0% | 0% | 0% |  | 2026-10-26 | 2026-10-26 |  | 2026-12-07 | 2026-12-07 |  | 2027-01-18 | 2027-01-18 |  | 2027-02-01 | 2027-02-01
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2809 | ZWP22 JACKET - RISER CLAMP DETAILS SHEET 8 | 0% | 0% | 0% | 0% |  | 2026-10-26 | 2026-10-26 |  | 2026-12-07 | 2026-12-07 |  | 2027-01-18 | 2027-01-18 |  | 2027-02-01 | 2027-02-01
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2810 | ZWP22 JACKET - RISER CLAMP DETAILS SHEET 9 | 0% | 0% | 0% | 0% |  | 2026-10-26 | 2026-10-26 |  | 2026-12-07 | 2026-12-07 |  | 2027-01-18 | 2027-01-18 |  | 2027-02-01 | 2027-02-01
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2811 | ZWP22 JACKET - RISER CLAMP DETAILS SHEET 10 | 0% | 0% | 0% | 0% |  | 2026-10-26 | 2026-10-26 |  | 2026-12-07 | 2026-12-07 |  | 2027-01-18 | 2027-01-18 |  | 2027-02-01 | 2027-02-01
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2900 | ZWP22 JACKET - CLOSURE PLATE DETAILS - SHEET 1 | 50% | 50% | 50% | 0% | 0.047 | 2026-08-14 | 2026-08-14 | 2026-06-11 | 2026-09-25 | 2026-09-25 |  | 2026-11-06 | 2026-11-06 |  | 2026-11-20 | 2026-11-20 |  | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2901 | ZWP22 JACKET - CLOSURE PLATE DETAILS - SHEET 2 | 50% | 50% | 50% | 0% | 0.047 | 2026-08-14 | 2026-08-14 | 2026-06-11 | 2026-09-25 | 2026-09-25 |  | 2026-11-06 | 2026-11-06 |  | 2026-11-20 | 2026-11-20 |  | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2902 | ZWP22 JACKET - LEG PARTITION DETAILS | 50% | 50% | 50% | 0% | 0.047 | 2026-08-14 | 2026-08-14 | 2026-06-11 | 2026-09-25 | 2026-09-25 |  | 2026-11-06 | 2026-11-06 |  | 2026-11-20 | 2026-11-20 |  | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2911 | ZWP22 JACKET - UPENDING ARRANGEMENT AND DETAILS | 50% | 50% | 0% | -50% | 0.047 | 2026-08-14 | 2026-08-14 |  | 2026-09-25 | 2026-09-25 |  | 2026-11-06 | 2026-11-06 |  | 2026-11-20 | 2026-11-20 |  | Overdue
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2931 | ZWP22 JACKET - BALLAST / DEBASSAST SCHEMATIC | 50% | 50% | 70% | 20% | 0.047 | 2026-08-21 | 2026-08-21 | 2026-04-30 | 2026-10-02 | 2026-10-02 | 2026-08-21 | 2026-11-13 | 2026-11-13 |  | 2026-11-27 | 2026-11-27 |  | Completed | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2932 | ZWP22 JACKET - GROUTING SCHEMATIC | 50% | 50% | 70% | 20% | 0.047 | 2026-08-21 | 2026-08-21 | 2026-04-30 | 2026-10-02 | 2026-10-02 | 2026-08-21 | 2026-11-13 | 2026-11-13 |  | 2026-11-27 | 2026-11-27 |  | Completed | Completed
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2933 | ZWP22 JACKET - BALLAST SYSTEM AND GROUTING LINE ROUTING AT ROW A ELEVATION | 50% | 50% | 0% | -50% | 0.047 | 2026-08-21 | 2026-08-21 |  | 2026-10-02 | 2026-10-02 |  | 2026-11-13 | 2026-11-13 |  | 2026-11-27 | 2026-11-27 |  | Overdue
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2934 | ZWP22 JACKET - BALLAST SYSTEM AND GROUTING LINE ROUTING AT ROW B ELEVATION | 50% | 50% | 0% | -50% | 0.047 | 2026-08-21 | 2026-08-21 |  | 2026-10-02 | 2026-10-02 |  | 2026-11-13 | 2026-11-13 |  | 2026-11-27 | 2026-11-27 |  | Overdue
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2935 | ZWP22 JACKET - BALLAST AND GROUTING SYSTEM SUPPORT DETAILS SHEET 1 | 50% | 50% | 0% | -50% | 0.047 | 2026-08-21 | 2026-08-21 |  | 2026-10-02 | 2026-10-02 |  | 2026-11-13 | 2026-11-13 |  | 2026-11-27 | 2026-11-27 |  | Overdue
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2936 | ZWP22 JACKET - BALLAST AND GROUTING SYSTEM SUPPORT DETAILS SHEET 2 | 50% | 50% | 0% | -50% | 0.047 | 2026-08-21 | 2026-08-21 |  | 2026-10-02 | 2026-10-02 |  | 2026-11-13 | 2026-11-13 |  | 2026-11-27 | 2026-11-27 |  | Overdue
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2937 | ZWP22 JACKET - BALLAST SYSTEM VALVE DETAILS | 50% | 50% | 0% | -50% | 0.047 | 2026-08-21 | 2026-08-21 |  | 2026-10-02 | 2026-10-02 |  | 2026-11-13 | 2026-11-13 |  | 2026-11-27 | 2026-11-27 |  | Overdue
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2938 | ZWP22 JACKET -GROUT, SKIRT SLEEVE VENT AND FLOODING DETAILS AT SKIRT PILE SLEEVE SHEET 1 | 50% | 50% | 0% | -50% | 0.047 | 2026-08-21 | 2026-08-21 |  | 2026-10-02 | 2026-10-02 |  | 2026-11-13 | 2026-11-13 |  | 2026-11-27 | 2026-11-27 |  | Overdue
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2939 | ZWP22 JACKET -GROUT, SKIRT SLEEVE VENT AND FLOODING DETAILS AT SKIRT PILE SLEEVE SHEET 2 | 50% | 50% | 0% | -50% | 0.047 | 2026-08-21 | 2026-08-21 |  | 2026-10-02 | 2026-10-02 |  | 2026-11-13 | 2026-11-13 |  | 2026-11-27 | 2026-11-27 |  | Overdue
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2940 | ZWP22 JACKET - BALLAST SYSTEM AND GROUTING LINE ROUTING AT EL(+) 8000 | 50% | 50% | 0% | -50% | 0.047 | 2026-08-21 | 2026-08-21 |  | 2026-10-02 | 2026-10-02 |  | 2026-11-13 | 2026-11-13 |  | 2026-11-27 | 2026-11-27 |  | Overdue
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2941 | ZWP22 JACKET - GROUT SYSTEM DETAILS | 50% | 50% | 0% | -50% | 0.047 | 2026-08-21 | 2026-08-21 |  | 2026-10-02 | 2026-10-02 |  | 2026-11-13 | 2026-11-13 |  | 2026-11-27 | 2026-11-27 |  | Overdue
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2950 | ZWP22 JACKET - LAUNCHING SEQUENCE | 50% | 50% | 0% | -50% | 0.047 | 2026-08-28 | 2026-08-28 |  | 2026-10-09 | 2026-10-09 |  | 2026-11-20 | 2026-11-20 |  | 2026-12-04 | 2026-12-04 |  | Overdue
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2951 | ZWP22 JACKET - UPENDING & LOWERING SEQUENCE | 50% | 50% | 0% | -50% | 0.047 | 2026-08-28 | 2026-08-28 |  | 2026-10-09 | 2026-10-09 |  | 2026-11-20 | 2026-11-20 |  | 2026-12-04 | 2026-12-04 |  | Overdue
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2961 | ZWP22 JACKET - PILE LIFTING & UPENDING | 50% | 50% | 0% | -50% | 0.047 | 2026-08-28 | 2026-08-28 |  | 2026-10-09 | 2026-10-09 |  | 2026-11-20 | 2026-11-20 |  | 2026-12-04 | 2026-12-04 |  | Overdue
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2971 | ZWP22 JACKET - WELD PROFILE CONTROL SHEET 1 | 50% | 50% | 0% | -50% | 0.047 | 2026-08-28 | 2026-08-28 |  | 2026-10-09 | 2026-10-09 |  | 2026-11-20 | 2026-11-20 |  | 2026-12-04 | 2026-12-04 |  | Overdue
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2972 | ZWP22 JACKET - WELD PROFILE CONTROL SHEET 2 | 50% | 50% | 0% | -50% | 0.047 | 2026-08-28 | 2026-08-28 |  | 2026-10-09 | 2026-10-09 |  | 2026-11-20 | 2026-11-20 |  | 2026-12-04 | 2026-12-04 |  | Overdue
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2973 | ZWP22 JACKET - WELD PROFILE CONTROL SHEET 3 | 50% | 50% | 0% | -50% | 0.047 | 2026-08-28 | 2026-08-28 |  | 2026-10-09 | 2026-10-09 |  | 2026-11-20 | 2026-11-20 |  | 2026-12-04 | 2026-12-04 |  | Overdue
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2974 | ZWP22 JACKET - WELD PROFILE CONTROL SHEET 4 | 50% | 50% | 0% | -50% | 0.047 | 2026-08-28 | 2026-08-28 |  | 2026-10-09 | 2026-10-09 |  | 2026-11-20 | 2026-11-20 |  | 2026-12-04 | 2026-12-04 |  | Overdue
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2975 | ZWP22 JACKET - WELD PROFILE CONTROL SHEET 5 | 50% | 50% | 0% | -50% | 0.047 | 2026-08-28 | 2026-08-28 |  | 2026-10-09 | 2026-10-09 |  | 2026-11-20 | 2026-11-20 |  | 2026-12-04 | 2026-12-04 |  | Overdue
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2976 | ZWP22 JACKET - WELD PROFILE CONTROL SHEET 6 | 50% | 50% | 0% | -50% | 0.047 | 2026-08-28 | 2026-08-28 |  | 2026-10-09 | 2026-10-09 |  | 2026-11-20 | 2026-11-20 |  | 2026-12-04 | 2026-12-04 |  | Overdue
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2981 | ZWP22 JACKET - LEG PAINT MARKING DETAILS - SHEET 1 | 50% | 50% | 0% | -50% | 0.047 | 2026-08-28 | 2026-08-28 |  | 2026-10-09 | 2026-10-09 |  | 2026-11-20 | 2026-11-20 |  | 2026-12-04 | 2026-12-04 |  | Overdue
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2982 | ZWP22 JACKET - LEG PAINT MARKING DETAILS - SHEET 2 | 50% | 50% | 0% | -50% | 0.047 | 2026-08-28 | 2026-08-28 |  | 2026-10-09 | 2026-10-09 |  | 2026-11-20 | 2026-11-20 |  | 2026-12-04 | 2026-12-04 |  | Overdue
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2984 | ZWP22 JACKET - PULLING LUG DETAILS | 50% | 50% | 0% | -50% | 0.047 | 2026-08-28 | 2026-08-28 |  | 2026-10-09 | 2026-10-09 |  | 2026-11-20 | 2026-11-20 |  | 2026-12-04 | 2026-12-04 |  | Overdue
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2991 | ZWP22 JACKET - JACKET TRANSPORTATION ARRANGEMENT | 50% | 50% | 0% | -50% | 0.047 | 2026-08-28 | 2026-08-28 |  | 2026-10-09 | 2026-10-09 |  | 2026-11-20 | 2026-11-20 |  | 2026-12-04 | 2026-12-04 |  | Overdue
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2994 | ZWP22 JACKET - VORTEX SHEDDING PREVENTION - SHEET 1 | 50% | 50% | 0% | -50% | 0.047 | 2026-08-28 | 2026-08-28 |  | 2026-10-09 | 2026-10-09 |  | 2026-11-20 | 2026-11-20 |  | 2026-12-04 | 2026-12-04 |  | Overdue
ZWP-22 | Drawing | MM-ZTK-1F-ZWP22-STR-DWG-2995 | ZWP22 JACKET - VORTEX SHEDDING PREVENTION - SHEET 2 | 50% | 50% | 0% | -50% | 0.047 | 2026-08-28 | 2026-08-28 |  | 2026-10-09 | 2026-10-09 |  | 2026-11-20 | 2026-11-20 |  | 2026-12-04 | 2026-12-04 |  | Overdue
ZWP-22 | Drawing | AS-BUILT DRAWINGS (TO BE CONFIRMED) | ZWP22 AS-BUILT DRAWINGS | 0% | 0% | 0% | 0% | 1.5
ZWP-20 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-0051 | JACKET - GENERAL NOTES - SHEET 1 | 50% | 50% | 100% | 50% | 0.009 | 2026-07-31 | 2026-07-31 | 2026-06-02 | 2026-09-11 | 2026-09-11 | 2026-06-18 | 2026-10-23 | 2026-10-23 | 2026-08-11 | 2026-11-06 | 2026-11-06 | 2026-08-21 | Completed | Completed | Completed | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-0052 | JACKET - GENERAL NOTES - SHEET 2 | 50% | 50% | 100% | 50% | 0.009 | 2026-07-31 | 2026-07-31 | 2026-06-02 | 2026-09-11 | 2026-09-11 | 2026-06-18 | 2026-10-23 | 2026-10-23 | 2026-08-11 | 2026-11-06 | 2026-11-06 | 2026-08-21 | Completed | Completed | Completed | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-0061 | JACKET - STANDARD DETAILS WELD PROFILE - SHEET 1 | 50% | 50% | 100% | 50% | 0.047 | 2026-07-31 | 2026-07-31 | 2026-06-02 | 2026-09-11 | 2026-09-11 | 2026-06-18 | 2026-10-23 | 2026-10-23 | 2026-08-11 | 2026-11-06 | 2026-11-06 | 2026-08-21 | Completed | Completed | Completed | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-0062 | JACKET - STANDARD DETAILS WELD PROFILE - SHEET 2 | 50% | 50% | 100% | 50% | 0.047 | 2026-07-31 | 2026-07-31 | 2026-06-02 | 2026-09-11 | 2026-09-11 | 2026-06-18 | 2026-10-23 | 2026-10-23 | 2026-08-11 | 2026-11-06 | 2026-11-06 | 2026-08-21 | Completed | Completed | Completed | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2001 | ZWP20 JACKET - DRAWING INDEX - SHEET 1 | 50% | 50% | 0% | -50% | 0.047 | 2026-07-31 | 2026-07-31 |  | 2026-09-11 | 2026-09-11 |  | 2026-10-23 | 2026-10-23 |  | 2026-11-06 | 2026-11-06 |  | Overdue | Follow-Next Week
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2002 | ZWP20 JACKET - DRAWING INDEX - SHEET 2 | 50% | 50% | 0% | -50% | 0.047 | 2026-07-31 | 2026-07-31 |  | 2026-09-11 | 2026-09-11 |  | 2026-10-23 | 2026-10-23 |  | 2026-11-06 | 2026-11-06 |  | Overdue | Follow-Next Week
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2100 | ZWP20 JACKET - VERTICAL FRAMING ROW 'A' | 50% | 50% | 70% | 20% | 0.047 | 2026-07-31 | 2026-07-31 | 2026-04-18 | 2026-09-04 | 2026-09-04 | 2026-08-25 | 2026-10-12 | 2026-10-12 |  | 2026-10-26 | 2026-10-26 |  | Completed | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2101 | ZWP20 JACKET - VERTICAL FRAMING ROW 'B' | 50% | 50% | 70% | 20% | 0.047 | 2026-07-31 | 2026-07-31 | 2026-04-18 | 2026-09-04 | 2026-09-04 | 2026-08-25 | 2026-10-12 | 2026-10-12 |  | 2026-10-26 | 2026-10-26 |  | Completed | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2102 | ZWP20 JACKET - VERTICAL FRAMING ROW '1' & '1.1' | 50% | 50% | 70% | 20% | 0.047 | 2026-07-31 | 2026-07-31 | 2026-04-18 | 2026-09-04 | 2026-09-04 | 2026-08-25 | 2026-10-12 | 2026-10-12 |  | 2026-10-26 | 2026-10-26 |  | Completed | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2103 | ZWP20 JACKET - VERTICAL FRAMING ROW '2' | 50% | 50% | 70% | 20% | 0.047 | 2026-07-31 | 2026-07-31 | 2026-04-18 | 2026-09-04 | 2026-09-04 | 2026-08-25 | 2026-10-12 | 2026-10-12 |  | 2026-10-26 | 2026-10-26 |  | Completed | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2104 | ZWP20 JACKET - VERTICAL FRAMING LAUNCH TRUSS ROW 'Aa' | 50% | 50% | 70% | 20% | 0.047 | 2026-07-31 | 2026-07-31 | 2026-04-18 | 2026-09-04 | 2026-09-04 | 2026-08-25 | 2026-10-12 | 2026-10-12 |  | 2026-10-26 | 2026-10-26 |  | Completed | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2105 | ZWP20 JACKET - VERTICAL FRAMING LAUNCH TRUSS ROW 'Bb' | 50% | 50% | 70% | 20% | 0.047 | 2026-07-31 | 2026-07-31 | 2026-04-18 | 2026-09-04 | 2026-09-04 | 2026-08-25 | 2026-10-12 | 2026-10-12 |  | 2026-10-26 | 2026-10-26 |  | Completed | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2110 | ZWP20 JACKET - HORIZONTAL FRAMING PLAN AT EL(+) 8000 | 50% | 50% | 70% | 20% | 0.047 | 2026-07-31 | 2026-07-31 | 2026-04-18 | 2026-09-04 | 2026-09-04 | 2026-08-25 | 2026-10-12 | 2026-10-12 |  | 2026-10-26 | 2026-10-26 |  | Completed | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2111 | ZWP20 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 3000 | 50% | 50% | 70% | 20% | 0.047 | 2026-07-31 | 2026-07-31 | 2026-04-18 | 2026-09-04 | 2026-09-04 | 2026-08-25 | 2026-10-12 | 2026-10-12 |  | 2026-10-26 | 2026-10-26 |  | Completed | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2112 | ZWP20 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 14000 | 50% | 50% | 70% | 20% | 0.047 | 2026-07-31 | 2026-07-31 | 2026-04-18 | 2026-09-04 | 2026-09-04 | 2026-08-25 | 2026-10-12 | 2026-10-12 |  | 2026-10-26 | 2026-10-26 |  | Completed | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2113 | ZWP20 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 26000 | 50% | 50% | 70% | 20% | 0.047 | 2026-07-31 | 2026-07-31 | 2026-04-18 | 2026-09-04 | 2026-09-04 | 2026-08-25 | 2026-10-12 | 2026-10-12 |  | 2026-10-26 | 2026-10-26 |  | Completed | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2114 | ZWP20 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 38000 | 50% | 50% | 70% | 20% | 0.047 | 2026-07-31 | 2026-07-31 | 2026-04-18 | 2026-09-04 | 2026-09-04 | 2026-08-25 | 2026-10-12 | 2026-10-12 |  | 2026-10-26 | 2026-10-26 |  | Completed | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2115 | ZWP20 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 52000 | 50% | 50% | 70% | 20% | 0.047 | 2026-07-31 | 2026-07-31 | 2026-04-18 | 2026-09-04 | 2026-09-04 | 2026-08-25 | 2026-10-12 | 2026-10-12 |  | 2026-10-26 | 2026-10-26 |  | Completed | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2116 | ZWP20 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 66000 | 50% | 50% | 70% | 20% | 0.047 | 2026-07-31 | 2026-07-31 | 2026-04-18 | 2026-09-04 | 2026-09-04 | 2026-08-25 | 2026-10-12 | 2026-10-12 |  | 2026-10-26 | 2026-10-26 |  | Completed | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2117 | ZWP20 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 79500 | 50% | 50% | 70% | 20% | 0.047 | 2026-07-31 | 2026-07-31 | 2026-04-18 | 2026-09-04 | 2026-09-04 | 2026-08-25 | 2026-10-12 | 2026-10-12 |  | 2026-10-26 | 2026-10-26 |  | Completed | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2118 | ZWP20 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 93000 | 50% | 50% | 70% | 20% | 0.047 | 2026-07-31 | 2026-07-31 | 2026-04-18 | 2026-09-04 | 2026-09-04 | 2026-08-25 | 2026-10-12 | 2026-10-12 |  | 2026-10-26 | 2026-10-26 |  | Completed | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2119 | ZWP20 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 103000 | 50% | 50% | 70% | 20% | 0.047 | 2026-07-31 | 2026-07-31 | 2026-04-18 | 2026-09-04 | 2026-09-04 | 2026-08-25 | 2026-10-12 | 2026-10-12 |  | 2026-10-26 | 2026-10-26 |  | Completed | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2120 | ZWP20 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 113000 | 50% | 50% | 70% | 20% | 0.047 | 2026-07-31 | 2026-07-31 | 2026-04-18 | 2026-09-04 | 2026-09-04 | 2026-08-25 | 2026-10-12 | 2026-10-12 |  | 2026-10-26 | 2026-10-26 |  | Completed | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2121 | ZWP20 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 124000 | 50% | 50% | 70% | 20% | 0.047 | 2026-07-31 | 2026-07-31 | 2026-04-18 | 2026-09-04 | 2026-09-04 | 2026-08-25 | 2026-10-12 | 2026-10-12 |  | 2026-10-26 | 2026-10-26 |  | Completed | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2122 | ZWP20 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 133100 | 50% | 50% | 70% | 20% | 0.047 | 2026-07-31 | 2026-07-31 | 2026-04-18 | 2026-09-04 | 2026-09-04 | 2026-06-18 | 2026-10-12 | 2026-10-12 |  | 2026-10-26 | 2026-10-26 |  | Completed | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2123 | ZWP20 JACKET - FRAMING SECTIONS | 50% | 50% | 70% | 20% | 0.047 | 2026-07-31 | 2026-07-31 | 2026-04-18 | 2026-09-04 | 2026-09-04 | 2026-08-25 | 2026-10-12 | 2026-10-12 |  | 2026-10-26 | 2026-10-26 |  | Completed | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2130 | ZWP20 JACKET - LAUNCH CRADLE GENERAL ARRANGEMENT | 50% | 50% | 70% | 20% | 0.047 | 2026-07-31 | 2026-07-31 | 2026-05-08 | 2026-09-04 | 2026-09-04 | 2026-07-02 | 2026-10-12 | 2026-10-12 |  | 2026-10-26 | 2026-10-26 |  | Completed | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2131 | ZWP20 JACKET - LAUNCH CRADLE DETAILS - SHEET 1 | 50% | 50% | 70% | 20% | 0.047 | 2026-07-31 | 2026-07-31 | 2026-05-08 | 2026-09-04 | 2026-09-04 | 2026-07-02 | 2026-10-12 | 2026-10-12 |  | 2026-10-26 | 2026-10-26 |  | Completed | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2132 | ZWP20 JACKET - LAUNCH CRADLE DETAILS - SHEET 2 | 50% | 50% | 100% | 50% | 0.047 | 2026-07-31 | 2026-07-31 | 2026-05-08 | 2026-09-04 | 2026-09-04 | 2026-07-02 | 2026-10-12 | 2026-10-12 | 2026-08-14 | 2026-10-26 | 2026-10-26 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2133 | ZWP20 JACKET - LAUNCH CRADLE AND VERTICAL FRAMING INTERNAL RING STIFFENER DETAILS - SHEET 1 | 50% | 50% | 50% | 0% | 0.047 | 2026-07-31 | 2026-07-31 | 2026-05-15 | 2026-09-04 | 2026-09-04 |  | 2026-10-12 | 2026-10-12 |  | 2026-10-26 | 2026-10-26 |  | Completed | Follow-This Week
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2134 | ZWP20 JACKET - LAUNCH CRADLE AND VERTICAL FRAMING INTERNAL RING STIFFENER DETAILS - SHEET 2 | 50% | 50% | 50% | 0% | 0.047 | 2026-07-31 | 2026-07-31 | 2026-05-15 | 2026-09-04 | 2026-09-04 |  | 2026-10-12 | 2026-10-12 |  | 2026-10-26 | 2026-10-26 |  | Completed | Follow-This Week
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2135 | ZWP20 JACKET - LAUNCH CRADLE AND VERTICAL FRAMING INTERNAL RING STIFFENER DETAILS - SHEET 3 | 50% | 50% | 50% | 0% | 0.047 | 2026-07-31 | 2026-07-31 | 2026-05-15 | 2026-09-04 | 2026-09-04 |  | 2026-10-12 | 2026-10-12 |  | 2026-10-26 | 2026-10-26 |  | Completed | Follow-This Week
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2136 | ZWP20 JACKET - LAUNCH CRADLE AND VERTICAL FRAMING INTERNAL RING STIFFENER DETAILS - SHEET 4 | 50% | 50% | 70% | 20% | 0.047 | 2026-07-31 | 2026-07-31 | 2026-05-15 | 2026-09-04 | 2026-09-04 | 2026-07-02 | 2026-10-12 | 2026-10-12 |  | 2026-10-26 | 2026-10-26 |  | Completed | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2141 | ZWP20 JACKET - PILE CLUSTER ARRANGEMENT | 50% | 50% | 50% | 0% | 0.047 | 2026-08-21 | 2026-08-21 | 2026-05-14 | 2026-10-02 | 2026-10-02 |  | 2026-11-13 | 2026-11-13 |  | 2026-11-27 | 2026-11-27 |  | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2142 | ZWP20 JACKET - PILE SLEEVE DETAILS | 50% | 50% | 50% | 0% | 0.047 | 2026-08-21 | 2026-08-21 | 2026-05-14 | 2026-10-02 | 2026-10-02 |  | 2026-11-13 | 2026-11-13 |  | 2026-11-27 | 2026-11-27 |  | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2143 | ZWP20 JACKET - SKIRT SLEEVE MARKING | 50% | 50% | 50% | 0% | 0.047 | 2026-08-21 | 2026-08-21 | 2026-05-14 | 2026-10-02 | 2026-10-02 |  | 2026-11-13 | 2026-11-13 |  | 2026-11-27 | 2026-11-27 |  | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2144 | ZWP20 JACKET - PILE MAKE-UP | 50% | 50% | 50% | 0% | 0.047 | 2026-08-14 | 2026-08-14 | 2026-06-05 | 2026-09-25 | 2026-09-25 |  | 2026-11-06 | 2026-11-06 |  | 2026-11-20 | 2026-11-20 |  | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2145 | ZWP20 JACKET - PILE MARKING | 50% | 50% | 0% | -50% | 0.047 | 2026-08-21 | 2026-08-21 |  | 2026-10-02 | 2026-10-02 |  | 2026-11-13 | 2026-11-13 |  | 2026-11-27 | 2026-11-27 |  | Overdue
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2200 | ZWP20 JACKET - HYDROSTATIC RING DETAILS - SHEET 1 | 50% | 50% | 50% | 0% | 0.047 | 2026-08-14 | 2026-08-14 | 2026-07-02 | 2026-09-25 | 2026-09-25 |  | 2026-11-06 | 2026-11-06 |  | 2026-11-20 | 2026-11-20 |  | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2201 | ZWP20 JACKET - HYDROSTATIC RING DETAILS - SHEET 2 | 50% | 50% | 50% | 0% | 0.047 | 2026-08-14 | 2026-08-14 | 2026-07-02 | 2026-09-25 | 2026-09-25 |  | 2026-11-06 | 2026-11-06 |  | 2026-11-20 | 2026-11-20 |  | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-2221 | JACKET - JACKET ACCESS LAYOUT AND DETAILS - SHEET 1 | 50% | 50% | 100% | 50% | 0.047 | 2026-08-28 | 2026-08-28 | 2026-06-09 | 2026-10-09 | 2026-10-09 | 2026-06-18 | 2026-11-20 | 2026-11-20 | 2026-08-18 | 2026-12-04 | 2026-12-04 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-2222 | JACKET - JACKET ACCESS LAYOUT AND DETAILS - SHEET 2 | 50% | 50% | 100% | 50% | 0.047 | 2026-08-28 | 2026-08-28 | 2026-06-09 | 2026-10-09 | 2026-10-09 | 2026-06-18 | 2026-11-20 | 2026-11-20 | 2026-08-18 | 2026-12-04 | 2026-12-04 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-2223 | JACKET - JACKET ACCESS LAYOUT AND DETAILS - SHEET 3 | 50% | 50% | 100% | 50% | 0.047 | 2026-08-28 | 2026-08-28 | 2026-06-09 | 2026-10-09 | 2026-10-09 | 2026-06-18 | 2026-11-20 | 2026-11-20 | 2026-08-18 | 2026-12-04 | 2026-12-04 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-2224 | JACKET - JACKET WALKWAY STAIR No 8 LANDING PLANS, SECTION & DETAILS | 50% | 50% | 100% | 50% | 0.047 | 2026-08-28 | 2026-08-28 | 2026-06-09 | 2026-10-09 | 2026-10-09 | 2026-06-18 | 2026-11-20 | 2026-11-20 | 2026-08-18 | 2026-12-04 | 2026-12-04 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-2225 | JACKET - STAIR No 9 PLANS, SECTIONS & DETAILS | 50% | 50% | 100% | 50% | 0.047 | 2026-08-28 | 2026-08-28 | 2026-06-09 | 2026-10-09 | 2026-10-09 | 2026-06-18 | 2026-11-20 | 2026-11-20 | 2026-08-18 | 2026-12-04 | 2026-12-04 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-2231 | JACKET - BOATLANDING ARRANGEMENT | 50% | 50% | 100% | 50% | 0.047 | 2026-08-28 | 2026-08-28 | 2026-05-20 | 2026-10-09 | 2026-10-09 | 2026-06-18 | 2026-11-20 | 2026-11-20 | 2026-08-18 | 2026-12-04 | 2026-12-04 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-2232 | JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 1 | 50% | 50% | 100% | 50% | 0.047 | 2026-08-28 | 2026-08-28 | 2026-05-20 | 2026-10-09 | 2026-10-09 | 2026-06-18 | 2026-11-20 | 2026-11-20 | 2026-08-18 | 2026-12-04 | 2026-12-04 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-2233 | JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 2 | 50% | 50% | 100% | 50% | 0.047 | 2026-08-28 | 2026-08-28 | 2026-05-20 | 2026-10-09 | 2026-10-09 | 2026-06-18 | 2026-11-20 | 2026-11-20 | 2026-08-18 | 2026-12-04 | 2026-12-04 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-2234 | JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 3 | 50% | 50% | 100% | 50% | 0.047 | 2026-08-28 | 2026-08-28 | 2026-05-20 | 2026-10-09 | 2026-10-09 | 2026-06-18 | 2026-11-20 | 2026-11-20 | 2026-08-18 | 2026-12-04 | 2026-12-04 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-2235 | JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 4 | 50% | 50% | 100% | 50% | 0.047 | 2026-08-28 | 2026-08-28 | 2026-05-20 | 2026-10-09 | 2026-10-09 | 2026-06-18 | 2026-11-20 | 2026-11-20 | 2026-08-18 | 2026-12-04 | 2026-12-04 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-2236 | JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 5 | 50% | 50% | 100% | 50% | 0.047 | 2026-08-28 | 2026-08-28 | 2026-05-20 | 2026-10-09 | 2026-10-09 | 2026-06-18 | 2026-11-20 | 2026-11-20 | 2026-08-18 | 2026-12-04 | 2026-12-04 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-2237 | JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 6 | 50% | 50% | 100% | 50% | 0.047 | 2026-08-28 | 2026-08-28 | 2026-05-20 | 2026-10-09 | 2026-10-09 | 2026-06-18 | 2026-11-20 | 2026-11-20 | 2026-08-18 | 2026-12-04 | 2026-12-04 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWPX-STR-DWG-2238 | JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 7 | 50% | 50% | 100% | 50% | 0.047 | 2026-08-28 | 2026-08-28 | 2026-05-20 | 2026-10-09 | 2026-10-09 | 2026-06-18 | 2026-11-20 | 2026-11-20 | 2026-08-18 | 2026-12-04 | 2026-12-04 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2241 | ZWP20 JACKET - RISER PROTECTOR | 50% | 50% | 70% | 20% | 0.047 | 2026-08-14 | 2026-08-14 | 2026-06-11 | 2026-09-25 | 2026-09-25 | 2026-06-19 | 2026-11-06 | 2026-11-06 |  | 2026-11-20 | 2026-11-20 |  | Completed | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2242 | ZWP20 JACKET - RISER PROTECTOR (OPTION) - CANCELLED | 50% | 50% | 100% | 50% | 0.047 | 2026-08-14 | 2026-08-14 | 2026-06-11 | 2026-09-25 | 2026-09-25 | 2026-06-19 | 2026-11-06 | 2026-11-06 | 2026-08-28 | 2026-11-20 | 2026-11-20 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2300 | ZWP20 JACKET - CASING GUIDE ARRANGEMENT | 50% | 50% | 0% | -50% | 0.047 | 2026-08-14 | 2026-08-14 |  | 2026-09-25 | 2026-09-25 |  | 2026-11-06 | 2026-11-06 |  | 2026-11-20 | 2026-11-20 |  | Overdue
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2301 | ZWP20 JACKET - CASING GUIDE DETAILS | 50% | 50% | 0% | -50% | 0.047 | 2026-08-14 | 2026-08-14 |  | 2026-09-25 | 2026-09-25 |  | 2026-11-06 | 2026-11-06 |  | 2026-11-20 | 2026-11-20 |  | Overdue
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2311 | ZWP20 JACKET - ANODE STRUCTURE AND INSTALLATION | 0% | 0% | 50% | 50% | 0.047 | 2026-09-04 | 2026-09-04 | 2026-04-30 | 2026-10-16 | 2026-10-16 |  | 2026-11-27 | 2026-11-27 |  | 2026-12-11 | 2026-12-11 |  | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2312 | ZWP20 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING ROW 'A' | 0% | 0% | 50% | 50% | 0.047 | 2026-09-04 | 2026-09-04 | 2026-04-30 | 2026-10-16 | 2026-10-16 |  | 2026-11-27 | 2026-11-27 |  | 2026-12-11 | 2026-12-11 |  | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2313 | ZWP20 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING ROW 'B' | 0% | 0% | 50% | 50% | 0.047 | 2026-09-04 | 2026-09-04 | 2026-04-30 | 2026-10-16 | 2026-10-16 |  | 2026-11-27 | 2026-11-27 |  | 2026-12-11 | 2026-12-11 |  | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2314 | ZWP20 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING ROW '1' & '1.1' | 0% | 0% | 50% | 50% | 0.047 | 2026-09-04 | 2026-09-04 | 2026-04-30 | 2026-10-16 | 2026-10-16 |  | 2026-11-27 | 2026-11-27 |  | 2026-12-11 | 2026-12-11 |  | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2315 | ZWP20 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING ROW '2' | 0% | 0% | 50% | 50% | 0.047 | 2026-09-04 | 2026-09-04 | 2026-04-30 | 2026-10-16 | 2026-10-16 |  | 2026-11-27 | 2026-11-27 |  | 2026-12-11 | 2026-12-11 |  | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2316 | ZWP20 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING LAUNCH TRUSS ROW 'Aa' | 0% | 0% | 50% | 50% | 0.047 | 2026-09-04 | 2026-09-04 | 2026-04-30 | 2026-10-16 | 2026-10-16 |  | 2026-11-27 | 2026-11-27 |  | 2026-12-11 | 2026-12-11 |  | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2317 | ZWP20 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING LAUNCH TRUSS ROW 'Bb' | 0% | 0% | 50% | 50% | 0.047 | 2026-09-04 | 2026-09-04 | 2026-04-30 | 2026-10-16 | 2026-10-16 |  | 2026-11-27 | 2026-11-27 |  | 2026-12-11 | 2026-12-11 |  | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2321 | ZWP20 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 14000 | 0% | 0% | 50% | 50% | 0.047 | 2026-09-04 | 2026-09-04 | 2026-04-30 | 2026-10-16 | 2026-10-16 |  | 2026-11-27 | 2026-11-27 |  | 2026-12-11 | 2026-12-11 |  | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2322 | ZWP20 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 26000 | 0% | 0% | 50% | 50% | 0.047 | 2026-09-04 | 2026-09-04 | 2026-04-30 | 2026-10-16 | 2026-10-16 |  | 2026-11-27 | 2026-11-27 |  | 2026-12-11 | 2026-12-11 |  | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2323 | ZWP20 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 38000 | 0% | 0% | 50% | 50% | 0.047 | 2026-09-04 | 2026-09-04 | 2026-04-30 | 2026-10-16 | 2026-10-16 |  | 2026-11-27 | 2026-11-27 |  | 2026-12-11 | 2026-12-11 |  | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2324 | ZWP20 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 52000 | 0% | 0% | 50% | 50% | 0.047 | 2026-09-04 | 2026-09-04 | 2026-04-30 | 2026-10-16 | 2026-10-16 |  | 2026-11-27 | 2026-11-27 |  | 2026-12-11 | 2026-12-11 |  | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2325 | ZWP20 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 66000 | 0% | 0% | 50% | 50% | 0.047 | 2026-09-04 | 2026-09-04 | 2026-04-30 | 2026-10-16 | 2026-10-16 |  | 2026-11-27 | 2026-11-27 |  | 2026-12-11 | 2026-12-11 |  | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2326 | ZWP20 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 79500 | 0% | 0% | 50% | 50% | 0.047 | 2026-09-04 | 2026-09-04 | 2026-04-30 | 2026-10-16 | 2026-10-16 |  | 2026-11-27 | 2026-11-27 |  | 2026-12-11 | 2026-12-11 |  | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2327 | ZWP20 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 93000 | 0% | 0% | 50% | 50% | 0.047 | 2026-09-04 | 2026-09-04 | 2026-04-30 | 2026-10-16 | 2026-10-16 |  | 2026-11-27 | 2026-11-27 |  | 2026-12-11 | 2026-12-11 |  | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2328 | ZWP20 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 103000 | 0% | 0% | 50% | 50% | 0.047 | 2026-09-04 | 2026-09-04 | 2026-04-30 | 2026-10-16 | 2026-10-16 |  | 2026-11-27 | 2026-11-27 |  | 2026-12-11 | 2026-12-11 |  | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2329 | ZWP20 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 113000 | 0% | 0% | 50% | 50% | 0.047 | 2026-09-04 | 2026-09-04 | 2026-04-30 | 2026-10-16 | 2026-10-16 |  | 2026-11-27 | 2026-11-27 |  | 2026-12-11 | 2026-12-11 |  | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2330 | ZWP20 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 124000 | 0% | 0% | 50% | 50% | 0.047 | 2026-09-04 | 2026-09-04 | 2026-04-30 | 2026-10-16 | 2026-10-16 |  | 2026-11-27 | 2026-11-27 |  | 2026-12-11 | 2026-12-11 |  | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2331 | ZWP20 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 133100 | 0% | 0% | 50% | 50% | 0.047 | 2026-09-04 | 2026-09-04 | 2026-04-30 | 2026-10-16 | 2026-10-16 |  | 2026-11-27 | 2026-11-27 |  | 2026-12-11 | 2026-12-11 |  | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2332 | ZWP20 JACKET - ANODE DISTRIBUTION OF PILE CLUSTER | 0% | 0% | 50% | 50% | 0.047 | 2026-09-04 | 2026-09-04 | 2026-04-30 | 2026-10-16 | 2026-10-16 |  | 2026-11-27 | 2026-11-27 |  | 2026-12-11 | 2026-12-11 |  | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2411 | ZWP20 JACKET - INSTALLATION PROCEDURE - CANCELLED |  |  | 100% |  | 0.047 | 2026-09-11 | 2026-09-11 | 2026-08-28 | 2026-10-23 | 2026-10-23 | 2026-08-28 | 2026-12-04 | 2026-12-04 | 2026-08-28 | 2026-12-18 | 2026-12-18 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2421 | ZWP20 JACKET - INSTALLATION AID CLASH CHECK - CANCELLED |  |  | 100% |  | 0.047 | 2026-09-11 | 2026-09-11 | 2026-08-28 | 2026-10-23 | 2026-10-23 | 2026-08-28 | 2026-12-04 | 2026-12-04 | 2026-08-28 | 2026-12-18 | 2026-12-18 | 2026-08-28 | Completed | Completed | Completed | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-XXXX | ZWP20 JACKET - INSTALLATION PROCEDURE - T&I ITEM | 0% | 0% | 0% | 0% |  | 2027-01-01 | 2027-01-01 |  | 2027-02-12 | 2027-02-12 |  | 2027-03-26 | 2027-03-26 |  | 2027-04-09 | 2027-04-09
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-XXXX | ZWP20 JACKET - INSTALLATION AID CLASH CHECK T&I ITEM | 0% | 0% | 0% | 0% |  | 2027-01-01 | 2027-01-01 |  | 2027-02-12 | 2027-02-12 |  | 2027-03-26 | 2027-03-26 |  | 2027-04-09 | 2027-04-09
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2801 | ZWP20 JACKET - RISER SUPPORT LOCATION | 0% | 0% | 50% | 50% |  | 2026-09-18 | 2026-09-18 | 2026-06-17 | 2026-10-30 | 2026-10-30 |  | 2026-12-11 | 2026-12-11 |  | 2026-12-25 | 2026-12-25 |  | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2802 | ZWP20 JACKET - RISER CLAMP DETAILS SHEET 1 | 0% | 0% | 0% | 0% |  | 2026-11-23 | 2026-11-23 |  | 2027-01-04 | 2027-01-04 |  | 2027-02-15 | 2027-02-15 |  | 2027-03-01 | 2027-03-01
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2803 | ZWP20 JACKET - RISER CLAMP DETAILS SHEET 2 | 0% | 0% | 0% | 0% |  | 2026-11-23 | 2026-11-23 |  | 2027-01-04 | 2027-01-04 |  | 2027-02-15 | 2027-02-15 |  | 2027-03-01 | 2027-03-01
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2804 | ZWP20 JACKET - RISER CLAMP DETAILS SHEET 3 | 0% | 0% | 0% | 0% |  | 2026-11-23 | 2026-11-23 |  | 2027-01-04 | 2027-01-04 |  | 2027-02-15 | 2027-02-15 |  | 2027-03-01 | 2027-03-01
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2805 | ZWP20 JACKET - RISER CLAMP DETAILS SHEET 4 | 0% | 0% | 0% | 0% |  | 2026-11-23 | 2026-11-23 |  | 2027-01-04 | 2027-01-04 |  | 2027-02-15 | 2027-02-15 |  | 2027-03-01 | 2027-03-01
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2900 | ZWP20 JACKET - CLOSURE PLATE DETAILS - SHEET 1 | 0% | 0% | 50% | 50% | 0.047 | 2026-09-11 | 2026-09-11 | 2026-06-11 | 2026-10-23 | 2026-10-23 |  | 2026-12-04 | 2026-12-04 |  | 2026-12-18 | 2026-12-18 |  | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2901 | ZWP20 JACKET - CLOSURE PLATE DETAILS - SHEET 2 | 0% | 0% | 50% | 50% | 0.047 | 2026-09-11 | 2026-09-11 | 2026-06-11 | 2026-10-23 | 2026-10-23 |  | 2026-12-04 | 2026-12-04 |  | 2026-12-18 | 2026-12-18 |  | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2902 | ZWP20 JACKET - LEG PARTITION DETAILS | 0% | 0% | 50% | 50% | 0.047 | 2026-09-11 | 2026-09-11 | 2026-06-11 | 2026-10-23 | 2026-10-23 |  | 2026-12-04 | 2026-12-04 |  | 2026-12-18 | 2026-12-18 |  | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2911 | ZWP20 JACKET - UPENDING ARRANGEMENT AND DETAILS | 0% | 0% | 0% | 0% | 0.047 | 2026-09-11 | 2026-09-11 |  | 2026-10-23 | 2026-10-23 |  | 2026-12-04 | 2026-12-04 |  | 2026-12-18 | 2026-12-18 |  | Follow-Next Week
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2931 | ZWP20 JACKET - BALLAST / DEBASSAST SCHEMATIC | 0% | 0% | 70% | 70% | 0.047 | 2026-09-18 | 2026-09-18 | 2026-04-30 | 2026-10-30 | 2026-10-30 | 2026-08-21 | 2026-12-11 | 2026-12-11 |  | 2026-12-25 | 2026-12-25 |  | Completed | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2932 | ZWP20 JACKET - GROUTING SCHEMATIC | 0% | 0% | 70% | 70% | 0.047 | 2026-09-18 | 2026-09-18 | 2026-04-30 | 2026-10-30 | 2026-10-30 | 2026-08-21 | 2026-12-11 | 2026-12-11 |  | 2026-12-25 | 2026-12-25 |  | Completed | Completed
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2933 | ZWP20 JACKET - BALLAST SYSTEM AND GROUTING LINE ROUTING AT ROW A ELEVATION | 0% | 0% | 0% | 0% | 0.047 | 2026-09-18 | 2026-09-18 |  | 2026-10-30 | 2026-10-30 |  | 2026-12-11 | 2026-12-11 |  | 2026-12-25 | 2026-12-25
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2934 | ZWP20 JACKET - BALLAST SYSTEM AND GROUTING LINE ROUTING AT ROW B ELEVATION | 0% | 0% | 0% | 0% | 0.047 | 2026-09-18 | 2026-09-18 |  | 2026-10-30 | 2026-10-30 |  | 2026-12-11 | 2026-12-11 |  | 2026-12-25 | 2026-12-25
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2935 | ZWP20 JACKET - BALLAST AND GROUTING SYSTEM SUPPORT DETAILS SHEET 1 | 0% | 0% | 0% | 0% | 0.047 | 2026-09-18 | 2026-09-18 |  | 2026-10-30 | 2026-10-30 |  | 2026-12-11 | 2026-12-11 |  | 2026-12-25 | 2026-12-25
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2936 | ZWP20 JACKET - BALLAST AND GROUTING SYSTEM SUPPORT DETAILS SHEET 2 | 0% | 0% | 0% | 0% | 0.047 | 2026-09-18 | 2026-09-18 |  | 2026-10-30 | 2026-10-30 |  | 2026-12-11 | 2026-12-11 |  | 2026-12-25 | 2026-12-25
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2937 | ZWP20 JACKET - BALLAST SYSTEM VALVE DETAILS | 0% | 0% | 0% | 0% | 0.047 | 2026-09-18 | 2026-09-18 |  | 2026-10-30 | 2026-10-30 |  | 2026-12-11 | 2026-12-11 |  | 2026-12-25 | 2026-12-25
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2938 | ZWP20 JACKET -GROUT, SKIRT SLEEVE VENT AND FLOODING DETAILS AT SKIRT PILE SLEEVE SHEET 1 | 0% | 0% | 0% | 0% | 0.047 | 2026-09-18 | 2026-09-18 |  | 2026-10-30 | 2026-10-30 |  | 2026-12-11 | 2026-12-11 |  | 2026-12-25 | 2026-12-25
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2939 | ZWP20 JACKET -GROUT, SKIRT SLEEVE VENT AND FLOODING DETAILS AT SKIRT PILE SLEEVE SHEET 2 | 0% | 0% | 0% | 0% | 0.047 | 2026-09-18 | 2026-09-18 |  | 2026-10-30 | 2026-10-30 |  | 2026-12-11 | 2026-12-11 |  | 2026-12-25 | 2026-12-25
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2940 | ZWP20 JACKET - BALLAST SYSTEM AND GROUTING LINE ROUTING AT EL(+) 8000 | 0% | 0% | 0% | 0% | 0.047 | 2026-09-18 | 2026-09-18 |  | 2026-10-30 | 2026-10-30 |  | 2026-12-11 | 2026-12-11 |  | 2026-12-25 | 2026-12-25
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2941 | ZWP20 JACKET - GROUT SYSTEM DETAILS | 0% | 0% | 0% | 0% | 0.047 | 2026-09-18 | 2026-09-18 |  | 2026-10-30 | 2026-10-30 |  | 2026-12-11 | 2026-12-11 |  | 2026-12-25 | 2026-12-25
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2950 | ZWP20 JACKET - LAUNCHING SEQUENCE | 0% | 0% | 0% | 0% | 0.047 | 2026-09-25 | 2026-09-25 |  | 2026-11-06 | 2026-11-06 |  | 2026-12-18 | 2026-12-18 |  | 2027-01-01 | 2027-01-01
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2951 | ZWP20 JACKET - UPENDING & LOWERING SEQUENCE | 0% | 0% | 0% | 0% | 0.047 | 2026-09-25 | 2026-09-25 |  | 2026-11-06 | 2026-11-06 |  | 2026-12-18 | 2026-12-18 |  | 2027-01-01 | 2027-01-01
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2961 | ZWP20 JACKET - PILE LIFTING & UPENDING | 0% | 0% | 0% | 0% | 0.047 | 2026-09-25 | 2026-09-25 |  | 2026-11-06 | 2026-11-06 |  | 2026-12-18 | 2026-12-18 |  | 2027-01-01 | 2027-01-01
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2971 | ZWP20 JACKET - WELD PROFILE CONTROL SHEET 1 | 0% | 0% | 0% | 0% | 0.047 | 2026-09-25 | 2026-09-25 |  | 2026-11-06 | 2026-11-06 |  | 2026-12-18 | 2026-12-18 |  | 2027-01-01 | 2027-01-01
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2972 | ZWP20 JACKET - WELD PROFILE CONTROL SHEET 2 | 0% | 0% | 0% | 0% | 0.047 | 2026-09-25 | 2026-09-25 |  | 2026-11-06 | 2026-11-06 |  | 2026-12-18 | 2026-12-18 |  | 2027-01-01 | 2027-01-01
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2973 | ZWP20 JACKET - WELD PROFILE CONTROL SHEET 3 | 0% | 0% | 0% | 0% | 0.047 | 2026-09-25 | 2026-09-25 |  | 2026-11-06 | 2026-11-06 |  | 2026-12-18 | 2026-12-18 |  | 2027-01-01 | 2027-01-01
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2974 | ZWP20 JACKET - WELD PROFILE CONTROL SHEET 4 | 0% | 0% | 0% | 0% | 0.047 | 2026-09-25 | 2026-09-25 |  | 2026-11-06 | 2026-11-06 |  | 2026-12-18 | 2026-12-18 |  | 2027-01-01 | 2027-01-01
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2975 | ZWP20 JACKET - WELD PROFILE CONTROL SHEET 5 | 0% | 0% | 0% | 0% | 0.047 | 2026-09-25 | 2026-09-25 |  | 2026-11-06 | 2026-11-06 |  | 2026-12-18 | 2026-12-18 |  | 2027-01-01 | 2027-01-01
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2976 | ZWP20 JACKET - WELD PROFILE CONTROL SHEET 6 | 0% | 0% | 0% | 0% | 0.047 | 2026-09-25 | 2026-09-25 |  | 2026-11-06 | 2026-11-06 |  | 2026-12-18 | 2026-12-18 |  | 2027-01-01 | 2027-01-01
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2981 | ZWP20 JACKET - LEG PAINT MARKING DETAILS - SHEET 1 | 0% | 0% | 0% | 0% | 0.047 | 2026-09-25 | 2026-09-25 |  | 2026-11-06 | 2026-11-06 |  | 2026-12-18 | 2026-12-18 |  | 2027-01-01 | 2027-01-01
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2982 | ZWP20 JACKET - LEG PAINT MARKING DETAILS - SHEET 2 | 0% | 0% | 0% | 0% | 0.047 | 2026-09-25 | 2026-09-25 |  | 2026-11-06 | 2026-11-06 |  | 2026-12-18 | 2026-12-18 |  | 2027-01-01 | 2027-01-01
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2984 | ZWP20 JACKET - PULLING LUG DETAILS | 0% | 0% | 0% | 0% | 0.047 | 2026-09-25 | 2026-09-25 |  | 2026-11-06 | 2026-11-06 |  | 2026-12-18 | 2026-12-18 |  | 2027-01-01 | 2027-01-01
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2991 | ZWP20 JACKET - JACKET TRANSPORTATION ARRANGEMENT | 0% | 0% | 0% | 0% | 0.047 | 2026-09-25 | 2026-09-25 |  | 2026-11-06 | 2026-11-06 |  | 2026-12-18 | 2026-12-18 |  | 2027-01-01 | 2027-01-01
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2994 | ZWP20 JACKET - VORTEX SHEDDING PREVENTION - SHEET 1 | 0% | 0% | 0% | 0% | 0.047 | 2026-09-25 | 2026-09-25 |  | 2026-11-06 | 2026-11-06 |  | 2026-12-18 | 2026-12-18 |  | 2027-01-01 | 2027-01-01
ZWP-20 | Drawing | MM-ZTK-1F-ZWP20-STR-DWG-2995 | ZWP20 JACKET - VORTEX SHEDDING PREVENTION - SHEET 2 | 0% | 0% | 0% | 0% | 0.047 | 2026-09-25 | 2026-09-25 |  | 2026-11-06 | 2026-11-06 |  | 2026-12-18 | 2026-12-18 |  | 2027-01-01 | 2027-01-01
ZWP-20 | Drawing | AS-BUILT DRAWINGS (TO BE CONFIRMED) | ZWP20 AS-BUILT DRAWINGS | 0% | 0% | 0% | 0% | 1.5
[5 empty] | Total |  |  | 100
Formulas:
Forecast = [IFR (50%)]
Forecast = [IFA (20%)]
IFA (20%) = [IFR (50%)]+42
AFC Sub (10%) = [IFA (20%)]+42
AFC App. (20%) = [AFC Sub (10%)]+14
IFR (50%) = [IFR (50%), row above]

## Review Cycle (hidden)
IFR |  | IFA | AFC Sub | AFC Approv.
| 14 | 14
21 Days
21 Days
14 Days
14 Days for COMPANY review, 7 Days to Incorporate the co
mments
14 Days for COMPANY review, 7 Days to Incorporate the co
mments
14 Days for COMPANY review

## Sheet4 (hidden)
Row Labels | Sum of Weight %
ZWP-16 | 22.075
ZWP-17 | 22.075
ZWP-18 | 22.075
ZWP-19 | 22.075
Grand Total | 88.3