## Cut_Off (hidden)
2026-03-20 | ZAWTIKA Z1F TS | 7
2026-03-27
2026-04-03
2026-04-10
2026-04-17
2026-04-24
2026-05-01
2026-05-08
2026-05-15
2026-05-22
2026-05-29
2026-06-05
2026-06-12
2026-06-19
2026-06-26
2026-07-03
2026-07-10
2026-07-17
2026-07-24
2026-07-31
2026-08-07
2026-08-14
2026-08-21
2026-08-28
2026-09-04
2026-09-11
2026-09-18
2026-09-25
2026-10-02
2026-10-09
2026-10-16
2026-10-23
2026-10-30
2026-11-06
2026-11-13
2026-11-20
2026-11-27
2026-12-04
2026-12-11
2026-12-18
2026-12-25
2027-01-01
2027-01-08
2027-01-15
2027-01-22
2027-01-29
2027-02-05
2027-02-12
2027-02-19
2027-02-26
2027-03-05
2027-03-12
2027-03-19
2027-03-26
2027-04-02
2027-04-09
2027-04-16
2027-04-23
2027-04-30
2027-05-07
2027-05-14
2027-05-21
2027-05-28
2027-06-04
2027-06-11
2027-06-18
2027-06-25
2027-07-02
2027-07-09
2027-07-16
2027-07-23
2027-07-30
2027-08-06
2027-08-13
2027-08-20
2027-08-27
2027-09-03
2027-09-10
2027-09-17
2027-09-24
2027-10-01
2027-10-08
2027-10-15
2027-10-22
2027-10-29
2027-11-05
2027-11-12
2027-11-19
2027-11-26
2027-12-03
2027-12-10
2027-12-17
2027-12-24
2027-12-31
2028-01-07
2028-01-14
2028-01-21
2028-01-28
2028-02-04
2028-02-11
2028-02-18
2028-02-25
2028-03-03
2028-03-10
2028-03-17
2028-03-24
2028-03-31
2028-04-07
2028-04-14
2028-04-21
2028-04-28
2028-05-05
2028-05-12
2028-05-19

## Progress Summary
[5 empty] | 34 | 34 | 34 | 34 |  |  |  |  | 35 | 35 | 35 | 35
Cut_Off Date
2026-10-09
Topsides DDE Progress by Platform
|  |  | Descriptions | % WT | Last Week Cumulative (%) |  |  |  | This Week Period (%) |  |  |  | Cumulative up to this week (%)
[5 empty] | Plan [A] | Forecast [B] | Actual [C] | Var. [C-A] | Plan [A] | Forecast [B] | Actual [C] | Var. [C-A] | Plan [A] | Forecast [B] | Actual [C] | Var. [C-A]
7 | 8 | 9 | Overall Topsides | 100% | 84.42% | 84.42% | 80.59% | -3.833% | 1.32% | 1.32% | 1.25% | -0.07% | 85.74% | 85.74% | 81.84% | -3.903%
Click Here to Change the cut_off

## Progress%
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117
2 |  |  | Cut_Off
3 |  |  | 2026-10-09
4
5 | Scope | Total WF | WF% | ZWP-18 Topsides
6 | time axis 2026-03-20 to 2028-05-05
7 | ZAWTIKA Z1F TS | 100 | 100% | Plan | 0% | 0% | 0.5% | 7% | 7% | 9.75% | 13% | 14% | 16.57% | 21.17% | 24.7% | 29.52% | 34.75% | 36.15% | 41.6% | 45.7% | 49.36% | 55.76% | 60.37% | 62.42% | 65.96% | 67.56% | 70.51% | 73.28% | 76.71% | 78.72% | 81.01% | 82.01% | 84.42% | 85.74% | 87.35% | 88.02% | 89.04% | 89.1% | 89.2% | 89.3% | 89.6% | 89.8% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90%
8 | ZAWTIKA Z1F TS | 100 | 100% | Forecast | 0% | 0% | 0.5% | 7% | 7% | 9.75% | 13% | 14% | 16.57% | 21.17% | 24.7% | 29.52% | 34.75% | 36.15% | 41.6% | 45.7% | 49.36% | 55.76% | 60.37% | 62.42% | 65.96% | 67.56% | 70.51% | 73.28% | 76.71% | 78.72% | 81.01% | 82.01% | 84.42% | 85.74% | 87.35% | 88.02% | 89.04% | 89.1% | 89.2% | 89.3% | 89.6% | 89.8% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90%
9 | ZAWTIKA Z1F TS | 100 | 100% | Actual | 0% | 0% | 0% | 2% | 2% | 6.125% | 11.12% | 13.45% | 15.45% | 18.85% | 23.77% | 26.75% | 33.81% | 40.15% | 44.22% | 47.71% | 49.17% | 54.07% | 59.41% | 62.46% | 65.09% | 67.21% | 69.57% | 72.63% | 74.91% | 76.3% | 78% | 78.81% | 80.59% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84% | 81.84%
10

## S-Curves
Zawtika 1F
Topsides Detailed Design
|  |  | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111
ZAWTIKA Z1F TS |  | Description | time axis 2026-03-20 to 2028-03-24
7 |  | Cumulative Plan | 0% | 0% | 0.5% | 7% | 7% | 9.75% | 13% | 14% | 16.57% | 21.17% | 24.7% | 29.52% | 34.75% | 36.15% | 41.6% | 45.7% | 49.36% | 55.76% | 60.37% | 62.42% | 65.96% | 67.56% | 70.51% | 73.28% | 76.71% | 78.72% | 81.01% | 82.01% | 84.42% | 85.74% | 87.35% | 88.02% | 89.04% | 89.1% | 89.2% | 89.3% | 89.6% | 89.8% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90%
8 |  | Cumulative Forecast | 0% | 0% | 0.5% | 7% | 7% | 9.75% | 13% | 14% | 16.57% | 21.17% | 24.7% | 29.52% | 34.75% | 36.15% | 41.6% | 45.7% | 49.36% | 55.76% | 60.37% | 62.42% | 65.96% | 67.56% | 70.51% | 73.28% | 76.71% | 78.72% | 81.01% | 82.01% | 84.42% | 85.74% | 87.35% | 88.02% | 89.04% | 89.1% | 89.2% | 89.3% | 89.6% | 89.8% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90%
9 |  | Cumulative Actual | 2026-03-20: 0%; 2026-03-27: 0%; 2026-04-03: 0%; 2026-04-10: 2%; 2026-04-17: 2%; 2026-04-24: 6.125%; 2026-05-01: 11.12%; 2026-05-08: 13.45%; 2026-05-15: 15.45%; 2026-05-22: 18.85%; 2026-05-29: 23.77%; 2026-06-05: 26.75%; 2026-06-12: 33.81%; 2026-06-19: 40.15%; 2026-06-26: 44.22%; 2026-07-03: 47.71%; 2026-07-10: 49.17%; 2026-07-17: 54.07%; 2026-07-24: 59.41%; 2026-07-31: 62.46%; 2026-08-07: 65.09%; 2026-08-14: 67.21%; 2026-08-21: 69.57%; 2026-08-28: 72.63%; 2026-09-04: 74.91%; 2026-09-11: 76.3%; 2026-09-18: 78%; 2026-09-25: 78.81%; 2026-10-02: 80.59%; 2026-10-09: 81.84%
|  | Period Plan (Early) | 0% | 0% | 0.5% | 6.5% | 0% | 2.75% | 3.25% | 1% | 2.575% | 4.6% | 3.525% | 4.825% | 5.225% | 1.4% | 5.45% | 4.1% | 3.66% | 6.4% | 4.61% | 2.05% | 3.535% | 1.6% | 2.955% | 2.765% | 3.435% | 2.01% | 2.29% | 1% | 2.41% | 1.32% | 1.61% | 0.67% | 1.02% | 0.06% | 0.1% | 0.1% | 0.3% | 0.2% | 0.2% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Period Forecast | 0% | 0% | 0.5% | 6.5% | 0% | 2.75% | 3.25% | 1% | 2.575% | 4.6% | 3.525% | 4.825% | 5.225% | 1.4% | 5.45% | 4.1% | 3.66% | 6.4% | 4.61% | 2.05% | 3.535% | 1.6% | 2.955% | 2.765% | 3.435% | 2.01% | 2.29% | 1% | 2.41% | 1.32% | 1.61% | 0.67% | 1.02% | 0.06% | 0.1% | 0.1% | 0.3% | 0.2% | 0.2% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Remaining Units | Period Actual | 2026-03-20: 0%; 2026-03-27: 0%; 2026-04-03: 0%; 2026-04-10: 2%; 2026-04-17: 0%; 2026-04-24: 4.125%; 2026-05-01: 5%; 2026-05-08: 2.325%; 2026-05-15: 2%; 2026-05-22: 3.4%; 2026-05-29: 4.925%; 2026-06-05: 2.975%; 2026-06-12: 7.065%; 2026-06-19: 6.34%; 2026-06-26: 4.07%; 2026-07-03: 3.49%; 2026-07-10: 1.45%; 2026-07-17: 4.9%; 2026-07-24: 5.345%; 2026-07-31: 3.05%; 2026-08-07: 2.625%; 2026-08-14: 2.125%; 2026-08-21: 2.36%; 2026-08-28: 3.06%; 2026-09-04: 2.275%; 2026-09-11: 1.395%; 2026-09-18: 1.7%; 2026-09-25: 0.805%; 2026-10-02: 1.782%; 2026-10-09: 1.25%

## EDSR
Cut-off Date |  |  | 2026-10-09
EDSR -TOPSIDES | [9 empty] | IFR (50%) |  |  | IFA (20%) |  |  | AFC Sub (10%) |  |  | AFC App. (20%) |  |  | AFC | For Project control engineer follow up
Facility |  | Type | Deliverable Title | Description | Plan [A] | Forecast [B] | Actual [C] | Var. [C-A] | Weight % | Plan | Forecast | Actual | Plan | Forecast | Actual | Plan | Forecast | Actual | Plan | Forecast | Actual | Status (AWC) | IFR (50%) | IFA (20%) | AFC Sub (10%) | AFC App. (20%)
ZAWTIKA Z1F TS | GENERIC | RPT | MM-ZTK-1F-GEN-STR-BOD-0001 | STRUCTURAL DESIGN BASIS | 100% | 100% | 70% | -30% | 1 | 2026-04-03 | 2026-04-03 | 2026-04-24 | 2026-05-15 | 2026-05-15 | 2026-07-24 | 2026-06-26 | 2026-06-26 |  | 2026-07-10 | 2026-07-10 |  |  | Completed | Completed | Overdue | Overdue
ZAWTIKA Z1F TS | GENERIC | RPT | MM-ZTK-1F-GEN-NVA-BOD-0001 | NAVAL ARCHITECTURE DESIGN BASIS | 100% | 100% | 70% | -30% | 1 | 2026-04-10 | 2026-04-10 | 2026-04-23 | 2026-05-22 | 2026-05-22 | 2026-07-27 | 2026-07-03 | 2026-07-03 |  | 2026-07-17 | 2026-07-17 |  |  | Completed | Completed | Overdue | Overdue
ZAWTIKA Z1F TS | GENERIC | RPT | MM-ZTK-1F-GEN-STR-PDR-0001 | WEIGHT CONTROL PROCEDURE | 100% | 100% | 100% | 0% | 1 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-05-22 | 2026-05-22 | 2026-05-29 | 2026-07-03 | 2026-07-03 | 2026-05-29 | 2026-07-17 | 2026-07-17 | 2026-06-19 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | ZWP-20 | RPT | MM-ZTK-1F-ZWP20-STR-CAL-0001 | ZWP20- BASIC STRUCTURAL ENGINEERING VERIFICATION REPORT
ZAWTIKA Z1F TS | ZWP-21 | RPT | MM-ZTK-1F-ZWP21-STR-CAL-0001 | ZWP21- BASIC STRUCTURAL ENGINEERING VERIFICATION REPORT
ZAWTIKA Z1F TS | ZWP-22 | RPT | MM-ZTK-1F-ZWP22-STR-CAL-0001 | ZWP22- BASIC STRUCTURAL ENGINEERING VERIFICATION REPORT
ZAWTIKA Z1F TS | ZWP-23 | RPT | MM-ZTK-1F-ZWP23-STR-CAL-0001 | ZWP23- BASIC STRUCTURAL ENGINEERING VERIFICATION REPORT
ZAWTIKA Z1F TS | GENERIC | RPT | MM-ZTK-1F-GEN-STR-CAL-0001 | TOPSIDES- BASIC STRUCTURAL ENGINEERING VERIFICATION REPORT | 100% | 100% | 100% | 0% | 8 | 2026-04-10 | 2026-04-10 | 2026-04-30 | 2026-05-22 | 2026-05-22 | 2026-06-10 | 2026-07-03 | 2026-07-03 | 2026-06-10 | 2026-07-17 | 2026-07-17 | 2026-06-10 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | RPT | MM-ZTK-1F-GEN-STR-WCR-1001 | TOPSIDES WEIGHT CONTROL REPORT (UPDATE MONHLY) - SUPERSEDED | 100% | 100% | 100% | 0% | 1.25 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-06-05 | 2026-06-05 | 2026-06-15 | 2026-07-17 | 2026-07-17 | 2026-08-21 | 2026-07-31 | 2026-07-31 | 2026-08-21 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | RPT | MM-ZTK-1F-GEN-STR-WCR-1001 | TOPSIDES WEIGHT CONTROL REPORT (UPDATE MONHLY) - MINOR AFC | 100% | 100% | 100% | 0% | 0.375 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-06-05 | 2026-06-05 | 2026-06-15 | 2026-07-17 | 2026-07-17 | 2026-09-04 | 2026-07-31 | 2026-07-31 | 2026-10-02 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | RPT | MM-ZTK-1F-GEN-STR-WCR-1001 | TOPSIDES WEIGHT CONTROL REPORT (UPDATE MONHLY) | 100% | 100% | 80% | -20% | 0.375 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-06-05 | 2026-06-05 | 2026-06-15 | 2026-07-17 | 2026-07-17 | 2026-09-04 | 2026-07-31 | 2026-07-31 |  | AWC | Completed | Completed | Completed | Overdue
ZAWTIKA Z1F TS | GENERIC | RPT | MM-ZTK-1F-GEN-STR-CAL-1001 | TOPSIDES COMPUTER MODELLING WITH VENT BOOM & LOAD FORMULATION | 100% | 100% | 100% | 0% | 1 | 2026-04-24 | 2026-04-24 | 2026-04-30 | 2026-06-05 | 2026-06-05 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-08-28 | 2026-07-31 | 2026-07-31 | 2026-08-28 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | RPT | MM-ZTK-1F-GEN-STR-CAL-1001 | TOPSIDES COMPUTER MODELLING WITH VENT BOOM & LOAD FORMULATION - MINOR AFC | 100% | 100% | 100% | 0% | 0.5 | 2026-04-24 | 2026-04-24 | 2026-04-30 | 2026-06-05 | 2026-06-05 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-09-18 | 2026-07-31 | 2026-07-31 | 2026-10-02 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | RPT | MM-ZTK-1F-GEN-STR-CAL-1001 | TOPSIDES COMPUTER MODELLING WITH VENT BOOM & LOAD FORMULATION - UPDATED INFO | 100% | 100% | 80% | -20% | 0.5 | 2026-04-24 | 2026-04-24 | 2026-04-30 | 2026-06-05 | 2026-06-05 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-09-18 | 2026-07-31 | 2026-07-31 |  | AWC | Completed | Completed | Completed | Overdue
ZAWTIKA Z1F TS | GENERIC | RPT | MM-ZTK-1F-GEN-STR-CAL-1011 | TOPSIDES IN-PLACE ANALYSIS REPORT | 100% | 100% | 100% | 0% | 1 | 2026-05-01 | 2026-05-01 | 2026-05-19 | 2026-06-12 | 2026-06-12 | 2026-07-31 | 2026-07-24 | 2026-07-24 | 2026-08-28 | 2026-08-07 | 2026-08-07 | 2026-08-28 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | RPT | MM-ZTK-1F-GEN-STR-CAL-1011 | TOPSIDES IN-PLACE ANALYSIS REPORT - UPDATED INFO | 100% | 100% | 80% | -20% | 1 | 2026-05-01 | 2026-05-01 | 2026-05-19 | 2026-06-12 | 2026-06-12 | 2026-07-31 | 2026-07-24 | 2026-07-24 | 2026-09-25 | 2026-08-07 | 2026-08-07 |  |  | Completed | Completed | Completed | Overdue
ZAWTIKA Z1F TS | GENERIC | RPT | MM-ZTK-1F-GEN-STR-CAL-1012 | TOPSIDES LOADOUT ANALYSIS REPORT - SUPERSEDED' | 100% | 100% | 100% | 0% | 1 | 2026-05-08 | 2026-05-08 | 2026-05-13 | 2026-06-19 | 2026-06-19 | 2026-07-23 | 2026-07-31 | 2026-07-31 | 2026-08-28 | 2026-08-14 | 2026-08-14 | 2026-08-28 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | RPT | MM-ZTK-1F-GEN-STR-CAL-1012 | TOPSIDES LOADOUT ANALYSIS REPORT (UPDATE INFO0 | 100% | 100% | 80% | -20% | 1 | 2026-05-08 | 2026-05-08 | 2026-05-13 | 2026-06-19 | 2026-06-19 | 2026-07-23 | 2026-07-31 | 2026-07-31 | 2026-09-24 | 2026-08-14 | 2026-08-14 |  |  | Completed | Completed | Completed | Overdue
ZAWTIKA Z1F TS | GENERIC | RPT | MM-ZTK-1F-GEN-STR-CAL-1013 | TOPSIDES TRANSPORATION ANALYSIS - SUPERSEDED | 100% | 100% | 100% | 0% | 1.2 | 2026-05-29 | 2026-05-29 | 2026-06-05 | 2026-07-10 | 2026-07-10 | 2026-07-31 | 2026-08-21 | 2026-08-21 | 2026-07-31 | 2026-09-04 | 2026-09-04 | 2026-07-31 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | RPT | MM-ZTK-1F-GEN-STR-CAL-1013 | TOPSIDES TRANSPORATION ANALYSIS REPORT - UPDATED TOW ROUTE - SUPERSEDED | 100% | 100% | 100% | 0% | 0.4 | 2026-05-29 | 2026-05-29 | 2026-06-05 | 2026-07-10 | 2026-07-10 | 2026-08-10 | 2026-08-21 | 2026-08-21 | 2026-10-02 | 2026-09-04 | 2026-09-04 | 2026-10-02 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | RPT | MM-ZTK-1F-GEN-STR-CAL-1013 | TOPSIDES TRANSPORATION ANALYSIS REPORT - UPDATED SEA-FASTENING | 100% | 100% | 80% | -20% | 0.4 | 2026-05-29 | 2026-05-29 | 2026-06-05 | 2026-07-10 | 2026-07-10 | 2026-08-10 | 2026-08-21 | 2026-08-21 | 2026-09-28 | 2026-09-04 | 2026-09-04 |  |  | Completed | Completed | Completed | Overdue
ZAWTIKA Z1F TS | GENERIC | RPT | MM-ZTK-1F-GEN-STR-CAL-1014 | TOPSIDES TRANSPORATION FATIGUE ANALYSIS REPORT - SUPERSEDED | 100% | 100% | 100% | 0% | 1.2 | 2026-06-12 | 2026-06-12 | 2026-07-02 | 2026-07-24 | 2026-07-24 | 2026-07-31 | 2026-09-04 | 2026-09-04 | 2026-07-31 | 2026-09-18 | 2026-09-18 | 2026-07-31 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | RPT | MM-ZTK-1F-GEN-STR-CAL-1014 | TOPSIDES TRANSPORATION FATIGUE ANALYSIS REPORT - UPDATED TOW ROUTE - SUPERSEDED | 100% | 100% | 100% | 0% | 0.4 | 2026-06-12 | 2026-06-12 | 2026-07-02 | 2026-07-15 | 2026-07-15 | 2026-08-14 | 2026-08-26 | 2026-08-26 | 2026-10-02 | 2026-09-09 | 2026-09-09 | 2026-10-02 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | RPT | MM-ZTK-1F-GEN-STR-CAL-1014 | TOPSIDES TRANSPORATION FATIGUE ANALYSIS REPORT - UPDATED SEA-FASTENING | 100% | 100% | 80% | -20% | 0.4 | 2026-06-12 | 2026-06-12 | 2026-07-02 | 2026-07-15 | 2026-07-15 | 2026-08-14 | 2026-08-26 | 2026-08-26 | 2026-10-09 | 2026-09-09 | 2026-09-09 |  |  | Completed | Completed | Completed | Overdue
ZAWTIKA Z1F TS | GENERIC | RPT | MM-ZTK-1F-GEN-STR-CAL-1015 | TOPSIDES LIFTING ANALYSIS REPORT - SUPERSEDED | 100% | 100% | 100% | 0% | 1 | 2026-05-22 | 2026-05-22 | 2026-05-15 | 2026-07-03 | 2026-07-03 | 2026-07-23 | 2026-08-14 | 2026-08-14 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | RPT | MM-ZTK-1F-GEN-STR-CAL-1015 | TOPSIDES LIFTING ANALYSIS REPORT - UPDATE INFO | 100% | 100% | 80% | -20% | 1 | 2026-05-22 | 2026-05-22 | 2026-05-15 | 2026-07-03 | 2026-07-03 | 2026-07-23 | 2026-08-14 | 2026-08-14 | 2026-09-24 | 2026-08-28 | 2026-08-28 |  |  | Completed | Completed | Completed | Overdue
ZAWTIKA Z1F TS | GENERIC | RPT | MM-ZTK-1F-GEN-STR-CAL-1016 | TOPSIDES MISCELLANEOUSD DESIGN REPORT - SUPERSEDED | 100% | 100% | 100% | 0% | 2.05 | 2026-06-26 | 2026-06-26 | 2026-06-23 | 2026-08-07 | 2026-08-07 | 2026-08-21 | 2026-09-18 | 2026-09-18 | 2026-09-11 | 2026-10-02 | 2026-10-02 | 2026-09-11 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | RPT | MM-ZTK-1F-GEN-STR-CAL-1016 | TOPSIDES MISCELLANEOUSD DESIGN REPORT - UPDATED INFO - SUPERSEDED | 100% | 100% | 100% | 0% | 1.025 | 2026-06-26 | 2026-06-26 | 2026-06-23 | 2026-08-07 | 2026-08-07 | 2026-08-21 | 2026-09-18 | 2026-09-18 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | RPT | MM-ZTK-1F-GEN-STR-CAL-1016 | TOPSIDES MISCELLANEOUSD DESIGN REPORT - UPDATED SEA-FASTENING | 100% | 100% | 70% | -30% | 1.025 | 2026-06-26 | 2026-06-26 | 2026-06-23 | 2026-08-07 | 2026-08-07 | 2026-08-21 | 2026-09-18 | 2026-09-18 |  | 2026-10-02 | 2026-10-02 |  |  | Completed | Completed | Overdue | Overdue
ZAWTIKA Z1F TS | GENERIC | RPT | MM-ZTK-1F-GEN-STR-CAL-1017 | TOPSIDE FINITE ELEMENT ANALYSIS FOR CASING SLOTS AND UNIHEAD SPACER REPORT | 100% | 100% | 100% | 0% | 1 | 2026-07-03 | 2026-07-03 | 2026-07-10 | 2026-08-14 | 2026-08-14 | 2026-07-17 | 2026-09-25 | 2026-09-25 | 2026-09-25 | 2026-10-09 | 2026-10-09 | 2026-09-25 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | RPT | MM-ZTK-1F-GEN-STR-CAL-1017 | TOPSIDE FINITE ELEMENT ANALYSIS FOR CASING SLOTS AND UNIHEAD SPACER REPORT | 100% | 100% | 70% | -30% | 1 | 2026-07-03 | 2026-07-03 | 2026-07-10 | 2026-08-14 | 2026-08-14 | 2026-07-17 | 2026-09-25 | 2026-09-25 |  | 2026-10-09 | 2026-10-09 |  |  | Completed | Completed | Overdue | Overdue
ZAWTIKA Z1F TS | ZWP-20 | RPT | MM-ZTK-1F-ZWP20-STR-CAL-2013 | ZWP20 IN-SERVICE COMBINED TOPSIDES AND JACKET FATIGUE ANALYSIS REPORT - SUPERSEDED | 100% | 100% | 100% | 0% | 1 | 2026-06-26 | 2026-06-26 | 2026-07-17 | 2026-08-07 | 2026-08-07 | 2026-07-17 | 2026-09-18 | 2026-09-18 | 2026-07-17 | 2026-10-02 | 2026-10-02 | 2026-07-17 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | ZWP-20 | RPT | MM-ZTK-1F-ZWP20-STR-CAL-2013 | ZWP20 IN-SERVICE COMBINED TOPSIDES AND JACKET FATIGUE ANALYSIS REPORT - NEW WATER DEPTH | 50% | 50% | 70% | 20% | 1 | 2026-08-31 | 2026-08-31 | 2026-09-04 | 2026-10-12 | 2026-10-12 | 2026-09-18 | 2026-11-23 | 2026-11-23 |  | 2026-12-07 | 2026-12-07 |  |  | Completed | Completed
ZAWTIKA Z1F TS | ZWP-21 | RPT | MM-ZTK-1F-ZWP21-STR-CAL-2013 | ZWP21 IN-SERVICE COMBINED TOPSIDES AND JACKET FATIGUE ANALYSIS REPORT - SUPERSEDED | 100% | 100% | 100% | 0% | 1 | 2026-05-15 | 2026-05-15 | 2026-06-15 | 2026-06-26 | 2026-06-26 | 2026-07-17 | 2026-08-07 | 2026-08-07 | 2026-07-17 | 2026-08-21 | 2026-08-21 | 2026-07-17 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | ZWP-21 | RPT | MM-ZTK-1F-ZWP21-STR-CAL-2013 | ZWP21 IN-SERVICE COMBINED TOPSIDES AND JACKET FATIGUE ANALYSIS REPORT - NEW WATER DEPTH | 100% | 100% | 100% | 0% | 1 | 2026-05-15 | 2026-05-15 | 2026-07-20 | 2026-06-26 | 2026-06-26 | 2026-07-20 | 2026-08-07 | 2026-08-07 | 2026-09-14 | 2026-08-21 | 2026-08-21 | 2026-09-30 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | ZWP-22 | RPT | MM-ZTK-1F-ZWP22-STR-CAL-2013 | ZWP22 IN-SERVICE COMBINED TOPSIDES AND JACKET FATIGUE ANALYSIS REPORT - SUPERRSEDED | 100% | 100% | 100% | 0% | 1 | 2026-06-12 | 2026-06-12 | 2026-07-17 | 2026-07-24 | 2026-07-24 | 2026-07-17 | 2026-09-04 | 2026-09-04 | 2026-07-17 | 2026-09-18 | 2026-09-18 | 2026-07-17 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | ZWP-22 | RPT | MM-ZTK-1F-ZWP22-STR-CAL-2013 | ZWP22 IN-SERVICE COMBINED TOPSIDES AND JACKET FATIGUE ANALYSIS REPORT - NEW WATER DEPTH | 70% | 70% | 70% | 0% | 1 | 2026-08-17 | 2026-08-17 | 2026-08-28 | 2026-09-28 | 2026-09-28 | 2026-09-18 | 2026-11-09 | 2026-11-09 |  | 2026-11-23 | 2026-11-23 |  |  | Completed | Completed
ZAWTIKA Z1F TS | ZWP-23 | RPT | MM-ZTK-1F-ZWP23-STR-CAL-2013 | ZWP23 IN-SERVICE COMBINED TOPSIDES AND JACKET FATIGUE ANALYSIS REPORT - SUPERSEDED | 100% | 100% | 100% | 0% | 1 | 2026-05-29 | 2026-05-29 | 2026-06-26 | 2026-07-10 | 2026-07-10 | 2026-07-17 | 2026-08-21 | 2026-08-21 | 2026-07-17 | 2026-09-04 | 2026-09-04 | 2026-07-17 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | ZWP-23 | RPT | MM-ZTK-1F-ZWP23-STR-CAL-2013 | ZWP23 IN-SERVICE COMBINED TOPSIDES AND JACKET FATIGUE ANALYSIS REPORT - NEW WATER DEPTH | 100% | 100% | 100% | 0% | 1 | 2026-05-29 | 2026-05-29 | 2026-06-26 | 2026-07-31 | 2026-07-31 | 2026-08-07 | 2026-09-11 | 2026-09-11 | 2026-09-28 | 2026-09-25 | 2026-09-25 | 2026-09-30 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | ZWP-20 | RPT | MM-ZTK-1F-ZWP20-STR-CAL-2031 | ZWP20 COMBINED TOPSIDES AND JACKET SEISMIC ANALYSIS REPORT (EXTREME LEVEL EARTHQUAKE-ELE) - SUPERSEDED | 80% | 80% | 100% | 20% | 1 | 2026-07-17 | 2026-07-17 | 2026-06-15 | 2026-08-28 | 2026-08-28 | 2026-07-24 | 2026-10-09 | 2026-10-09 | 2026-07-24 | 2026-10-23 | 2026-10-23 | 2026-07-24 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | ZWP-20 | RPT | MM-ZTK-1F-ZWP20-STR-CAL-2032 | ZWP20 COMBINED TOPSIDES AND JACKET SEISMIC ANALYSIS REPORT (ABNORMAL LEVEL EARTHQUAKE-ALE) - SUPERSEDED | 70% | 70% | 100% | 30% | 1 | 2026-07-24 | 2026-07-24 | 2026-07-24 | 2026-09-04 | 2026-09-04 | 2026-07-24 | 2026-10-16 | 2026-10-16 | 2026-07-24 | 2026-10-30 | 2026-10-30 | 2026-07-24 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | ZWP-20 | RPT | MM-ZTK-1F-ZWP20-STR-CAL-2031 | ZWP20 COMBINED TOPSIDES AND JACKET SEISMIC ANALYSIS REPORT (EXTREME LEVEL EARTHQUAKE-ELE) - NEW WATER DEPTH | 80% | 80% | 80% | 0% | 1 | 2026-07-17 | 2026-07-17 | 2026-06-15 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-10-09 | 2026-10-09 | 2026-10-05 | 2026-10-23 | 2026-10-23 |  |  | Completed | Completed | Completed
ZAWTIKA Z1F TS | ZWP-20 | RPT | MM-ZTK-1F-ZWP20-STR-CAL-2032 | ZWP20 COMBINED TOPSIDES AND JACKET SEISMIC ANALYSIS REPORT (ABNORMAL LEVEL EARTHQUAKE-ALE) - NEW WATER DEPTH | 70% | 70% | 70% | 0% | 1 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-10-09 | 2026-10-09 | 2026-09-04 | 2026-11-20 | 2026-11-20 |  | 2026-12-04 | 2026-12-04 |  |  | Completed | Completed
ZAWTIKA Z1F TS | ZWP-21 | RPT | MM-ZTK-1F-ZWP21-STR-CAL-2031 | ZWP21 COMBINED TOPSIDES AND JACKET SEISMIC ANALYSIS REPORT (EXTREME LEVEL EARTHQUAKE-ELE) | 100% | 100% | 100% | 0% | 2 | 2026-06-05 | 2026-06-05 | 2026-05-29 | 2026-07-17 | 2026-07-17 | 2026-07-14 | 2026-08-28 | 2026-08-28 | 2026-08-21 | 2026-09-11 | 2026-09-11 | 2026-09-04 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | ZWP-21 | RPT | MM-ZTK-1F-ZWP21-STR-CAL-2032 | ZWP21 COMBINED TOPSIDES AND JACKET SEISMIC ANALYSIS REPORT (ABNORMAL LEVEL EARTHQUAKE-ALE) | 100% | 100% | 100% | 0% | 2 | 2026-06-12 | 2026-06-12 | 2026-05-29 | 2026-07-24 | 2026-07-24 | 2026-07-14 | 2026-09-04 | 2026-09-04 | 2026-08-28 | 2026-09-18 | 2026-09-18 | 2026-09-04 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | ZWP-22 | RPT | MM-ZTK-1F-ZWP22-STR-CAL-2031 | ZWP22 COMBINED TOPSIDES AND JACKET SEISMIC ANALYSIS REPORT (EXTREME LEVEL EARTHQUAKE-ELE) - SUPERSEDED | 100% | 100% | 100% | 0% | 1 | 2026-07-03 | 2026-07-03 | 2026-06-12 | 2026-08-14 | 2026-08-14 | 2026-08-07 | 2026-09-25 | 2026-09-25 | 2026-08-07 | 2026-10-09 | 2026-10-09 | 2026-08-07 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | ZWP-22 | RPT | MM-ZTK-1F-ZWP22-STR-CAL-2032 | ZWP22 COMBINED TOPSIDES AND JACKET SEISMIC ANALYSIS REPORT (ABNORMAL LEVEL EARTHQUAKE-ALE) - SUPERSEDED | 80% | 80% | 100% | 20% | 1 | 2026-07-10 | 2026-07-10 | 2026-06-15 | 2026-08-21 | 2026-08-21 | 2026-08-07 | 2026-10-02 | 2026-10-02 | 2026-08-07 | 2026-10-16 | 2026-10-16 | 2026-08-07 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | ZWP-22 | RPT | MM-ZTK-1F-ZWP22-STR-CAL-2031 | ZWP22 COMBINED TOPSIDES AND JACKET SEISMIC ANALYSIS REPORT (EXTREME LEVEL EARTHQUAKE-ELE) - NEW WATER DEPTH | 100% | 100% | 80% | -20% | 1 | 2026-07-03 | 2026-07-03 | 2026-06-12 | 2026-08-14 | 2026-08-14 | 2026-08-14 | 2026-09-25 | 2026-09-25 | 2026-09-28 | 2026-10-09 | 2026-10-09 |  |  | Completed | Completed | Completed | Overdue
ZAWTIKA Z1F TS | ZWP-22 | RPT | MM-ZTK-1F-ZWP22-STR-CAL-2032 | ZWP22 COMBINED TOPSIDES AND JACKET SEISMIC ANALYSIS REPORT (ABNORMAL LEVEL EARTHQUAKE-ALE) - NEW WATER DEPTH | 80% | 80% | 80% | 0% | 1 | 2026-07-10 | 2026-07-10 | 2026-06-15 | 2026-08-21 | 2026-08-21 | 2026-08-14 | 2026-10-02 | 2026-10-02 | 2026-10-05 | 2026-10-16 | 2026-10-16 |  |  | Completed | Completed | Completed | Follow-Next Week
ZAWTIKA Z1F TS | ZWP-23 | RPT | MM-ZTK-1F-ZWP23-STR-CAL-2031 | ZWP23 COMBINED TOPSIDES AND JACKET SEISMIC ANALYSIS REPORT (EXTREME LEVEL EARTHQUAKE-ELE) - SUPERSEDED | 100% | 100% | 100% | 0% | 1 | 2026-06-19 | 2026-06-19 | 2026-06-05 | 2026-07-31 | 2026-07-31 | 2026-07-24 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-25 | 2026-09-25 | 2026-09-11 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | ZWP-23 | RPT | MM-ZTK-1F-ZWP23-STR-CAL-2032 | ZWP23 COMBINED TOPSIDES AND JACKET SEISMIC ANALYSIS REPORT (ABNORMAL LEVEL EARTHQUAKE-ALE) - SUPERSEDED | 100% | 100% | 100% | 0% | 1 | 2026-06-26 | 2026-06-26 | 2026-06-08 | 2026-08-07 | 2026-08-07 | 2026-07-24 | 2026-09-18 | 2026-09-18 | 2026-09-11 | 2026-10-02 | 2026-10-02 | 2026-09-11 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | ZWP-23 | RPT | MM-ZTK-1F-ZWP23-STR-CAL-2031 | ZWP23 COMBINED TOPSIDES AND JACKET SEISMIC ANALYSIS REPORT (EXTREME LEVEL EARTHQUAKE-ELE) - NEW WATER DEPTH | 100% | 100% | 100% | 0% | 1 | 2026-06-19 | 2026-06-19 | 2026-06-05 | 2026-07-31 | 2026-07-31 | 2026-07-24 | 2026-09-11 | 2026-09-11 | 2026-09-18 | 2026-09-25 | 2026-09-25 | 2026-10-05 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | ZWP-23 | RPT | MM-ZTK-1F-ZWP23-STR-CAL-2032 | ZWP23 COMBINED TOPSIDES AND JACKET SEISMIC ANALYSIS REPORT (ABNORMAL LEVEL EARTHQUAKE-ALE) - NEW WATER DEPTH | 100% | 100% | 100% | 0% | 1 | 2026-06-26 | 2026-06-26 | 2026-06-08 | 2026-08-07 | 2026-08-07 | 2026-07-24 | 2026-09-18 | 2026-09-18 | 2026-09-18 | 2026-10-02 | 2026-10-02 | 2026-10-05 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | RPT | MM-ZTK-1F-GEN-NVA-CAL-1011 | TOPSIDES BARGE MOTION ANALYSIS REPORT - SUPERSEDED | 100% | 100% | 100% | 0% | 1.2 | 2026-05-22 | 2026-05-22 | 2026-06-29 | 2026-07-03 | 2026-07-03 | 2026-08-07 | 2026-08-14 | 2026-08-14 | 2026-08-07 | 2026-08-28 | 2026-08-28 | 2026-08-07 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | RPT | MM-ZTK-1F-GEN-NVA-CAL-1011 | TOPSIDES BARGE MOTION ANALYSIS REPORT - UPDATED TOW ROUTE | 100% | 100% | 80% | -20% | 0.8 | 2026-05-22 | 2026-05-22 | 2026-06-29 | 2026-07-03 | 2026-07-03 | 2026-08-28 | 2026-08-14 | 2026-08-14 | 2026-10-09 | 2026-08-28 | 2026-08-28 |  |  | Completed | Completed | Completed | Overdue
ZAWTIKA Z1F TS | GENERIC | RPT | MM-ZTK-1F-GEN-STR-CAL-1001 | TOPSIDES PRIMARY STEEL MTO REPORT - SUPERSEDED | 100% | 100% | 100% | 0% | 1 | 2026-05-29 | 2026-05-29 | 2026-06-15 | 2026-07-10 | 2026-07-10 | 2026-07-24 | 2026-08-21 | 2026-08-21 | 2026-09-04 | 2026-09-04 | 2026-09-04 | 2026-09-04 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | RPT | MM-ZTK-1F-GEN-STR-CAL-1002 | TOPSIDES SECONDARY AND TERTIARY STEEL MTO REPORT - SUPERSEDED | 100% | 100% | 100% | 0% | 1 | 2026-06-05 | 2026-06-05 | 2026-06-29 | 2026-07-17 | 2026-07-17 | 2026-07-01 | 2026-08-28 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-11 | 2026-09-04 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | RPT | MM-ZTK-1F-GEN-STR-CAL-1001 | TOPSIDES PRIMARY STEEL MTO REPORT - UPDATED INFO | 100% | 100% | 70% | -30% | 1 | 2026-05-29 | 2026-05-29 | 2026-06-15 | 2026-07-10 | 2026-07-10 | 2026-07-24 | 2026-08-21 | 2026-08-21 |  | 2026-09-04 | 2026-09-04 |  |  | Completed | Completed | Overdue | Overdue
ZAWTIKA Z1F TS | GENERIC | RPT | MM-ZTK-1F-GEN-STR-CAL-1002 | TOPSIDES SECONDARY AND TERTIARY STEEL MTO REPORT - UPDATED INFO | 100% | 100% | 70% | -30% | 1 | 2026-06-05 | 2026-06-05 | 2026-06-29 | 2026-07-17 | 2026-07-17 | 2026-07-01 | 2026-08-28 | 2026-08-28 |  | 2026-09-11 | 2026-09-11 |  |  | Completed | Completed | Overdue | Overdue
ZAWTIKA Z1F TS | GENERIC | RPT | MM-ZTK-1F-GEN-STR-MR-1001 | MATERIAL REQUISITION FOR TOPSIDES HIGH STRENGTH TUBULAR STEEL - CANCELLED, COMPLETED BY YARD ALREADY | 100% | 100% | 100% | 0% | 1.5 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-05-22 | 2026-05-22 | 2026-06-18 | 2026-07-03 | 2026-07-03 | 2026-07-06 | 2026-07-17 | 2026-07-17 | 2026-09-18 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | RPT | MM-ZTK-1F-GEN-STR-MR-1002 | MATERIAL REQUISITION FOR TOPSIDES SECONDARY AND TERTIARY TUBULAR STEEL - CANCELLED, COMPLETED BY YARD ALREADY | 100% | 100% | 100% | 0% | 1.5 | 2026-04-30 | 2026-04-30 | 2026-05-22 | 2026-06-11 | 2026-06-11 | 2026-06-18 | 2026-07-23 | 2026-07-23 | 2026-07-17 | 2026-08-06 | 2026-08-06 | 2026-07-30 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | RPT | MM-ZTK-1F-GEN-STR-MR-1011 | MATERIAL REQUISITION FOR TOPSIDES HIGH STRENGTH HOT-ROLLED STEEL SECTIONS (SHAPES) - CANCELLED, COMPLETED BY YARD ALREADY | 100% | 100% | 100% | 0% | 1.5 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-05-22 | 2026-05-22 | 2026-06-18 | 2026-07-03 | 2026-07-03 | 2026-07-06 | 2026-07-17 | 2026-07-17 | 2026-09-18 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | RPT | MM-ZTK-1F-GEN-STR-MR-1012 | MATERIAL REQUISITION FOR TOPSIDES SECONDARY AND TERTIARY HOT-ROLLED STEEL (SHAPES) - CANCELLED, COMPLETED BY YARD ALREADY | 100% | 100% | 100% | 0% | 1.5 | 2026-04-30 | 2026-04-30 | 2026-05-22 | 2026-06-11 | 2026-06-11 | 2026-06-18 | 2026-07-23 | 2026-07-23 | 2026-07-17 | 2026-08-06 | 2026-08-06 | 2026-07-30 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | RPT | MM-ZTK-1F-GEN-STR-MR-1021 | MATERIAL REQUISITION FOR TOPSIDES HIGH STRENGTH STEEL PLATES - CANCELLED, COMPLETED BY YARD ALREADY | 100% | 100% | 100% | 0% | 1.5 | 2026-04-24 | 2026-04-24 | 2026-04-23 | 2026-06-05 | 2026-06-05 | 2026-06-18 | 2026-07-17 | 2026-07-17 | 2026-07-06 | 2026-07-31 | 2026-07-31 | 2026-09-18 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | RPT | MM-ZTK-1F-GEN-STR-MR-1022 | MATERIAL REQUISITION FOR TOPSIDES LOW STRENGTH STEEL PLATES - CANCELLED, COMPLETED BY YARD ALREADY | 100% | 100% | 100% | 0% | 1.5 | 2026-04-30 | 2026-04-30 | 2026-05-29 | 2026-06-11 | 2026-06-11 | 2026-06-18 | 2026-07-23 | 2026-07-23 | 2026-08-03 | 2026-08-06 | 2026-08-06 | 2026-08-13 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | AS-BUILT | RPT | MM-ZTK-1F-ZWP20-STR-WCR-1101 | ZWP20 TOPSIDES WEIGHT CONTROL REPORT (AS-BUILT) | 0% | 0% | 0% | 0% | 0.25
ZAWTIKA Z1F TS | AS-BUILT | RPT | MM-ZTK-1F-ZWP20-STR-CAL-1101 | ZWP20 TOPSIDE COMPUTER MODELLING WITH VENT BOOM AND LOAD FORMULATION REPORT (AS-BUILT) | 0% | 0% | 0% | 0% | 0.25
ZAWTIKA Z1F TS | AS-BUILT | RPT | MM-ZTK-1F-ZWP20-STR-CAL-2111 | ZWP20 PLATFORM IN-PLACE ANALYSIS REPORT (AS-BUILT) | 0% | 0% | 0% | 0% | 0.25
ZAWTIKA Z1F TS | AS-BUILT | RPT | MM-ZTK-1F-ZWP20-STR-CAL-2113 | ZWP20 PLATFORM IN-PLACE SPECTRAL FATIGUE ANLYSIS REPORT (AS-BUILT) | 0% | 0% | 0% | 0% | 0.25
ZAWTIKA Z1F TS | AS-BUILT | RPT | MM-ZTK-1F-ZWP21-STR-WCR-1101 | ZWP21 TOPSIDES WEIGHT CONTROL REPORT (AS-BUILT) | 0% | 0% | 0% | 0% | 0.25
ZAWTIKA Z1F TS | AS-BUILT | RPT | MM-ZTK-1F-ZWP21-STR-CAL-1101 | ZWP21 TOPSIDE COMPUTER MODELLING WITH VENT BOOM AND LOAD FORMULATION REPORT (AS-BUILT) | 0% | 0% | 0% | 0% | 0.25
ZAWTIKA Z1F TS | AS-BUILT | RPT | MM-ZTK-1F-ZWP21-STR-CAL-2111 | ZWP21 PLATFORM IN-PLACE ANALYSIS REPORT (AS-BUILT) | 0% | 0% | 0% | 0% | 0.25
ZAWTIKA Z1F TS | AS-BUILT | RPT | MM-ZTK-1F-ZWP21-STR-CAL-2113 | ZWP21 PLATFORM IN-PLACE SPECTRAL FATIGUE ANLYSIS REPORT (AS-BUILT) | 0% | 0% | 0% | 0% | 0.25
ZAWTIKA Z1F TS | AS-BUILT | RPT | MM-ZTK-1F-ZWP22-STR-WCR-1101 | ZWP22 TOPSIDES WEIGHT CONTROL REPORT (AS-BUILT) | 0% | 0% | 0% | 0% | 0.25
ZAWTIKA Z1F TS | AS-BUILT | RPT | MM-ZTK-1F-ZWP22-STR-CAL-1101 | ZWP22 TOPSIDE COMPUTER MODELLING WITH VENT BOOM AND LOAD FORMULATION REPORT (AS-BUILT) | 0% | 0% | 0% | 0% | 0.25
ZAWTIKA Z1F TS | AS-BUILT | RPT | MM-ZTK-1F-ZWP22-STR-CAL-2111 | ZWP22 PLATFORM IN-PLACE ANALYSIS REPORT (AS-BUILT) | 0% | 0% | 0% | 0% | 0.25
ZAWTIKA Z1F TS | AS-BUILT | RPT | MM-ZTK-1F-ZWP22-STR-CAL-2113 | ZWP22 PLATFORM IN-PLACE SPECTRAL FATIGUE ANLYSIS REPORT (AS-BUILT) | 0% | 0% | 0% | 0% | 0.25
ZAWTIKA Z1F TS | AS-BUILT | RPT | MM-ZTK-1F-ZWP23-STR-WCR-1101 | ZWP23 TOPSIDES WEIGHT CONTROL REPORT (AS-BUILT) | 0% | 0% | 0% | 0% | 0.25
ZAWTIKA Z1F TS | AS-BUILT | RPT | MM-ZTK-1F-ZWP23-STR-CAL-1101 | ZWP23 TOPSIDE COMPUTER MODELLING WITH VENT BOOM AND LOAD FORMULATION REPORT (AS-BUIL) | 0% | 0% | 0% | 0% | 0.25
ZAWTIKA Z1F TS | AS-BUILT | RPT | MM-ZTK-1F-ZWP23-STR-CAL-2111 | ZWP23 PLATFORM IN-PLACE ANALYSIS REPORT (AS-BUILT) | 0% | 0% | 0% | 0% | 0.25
ZAWTIKA Z1F TS | AS-BUILT | RPT | MM-ZTK-1F-ZWP23-STR-CAL-2113 | ZWP23 PLATFORM IN-PLACE SPECTRAL FATIGUE ANLYSIS REPORT (AS-BUILT) | 0% | 0% | 0% | 0% | 0.25
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-0001 | TOPSIDE - GENERAL NOTES SHEET 1 | 100% | 100% | 100% | 0% | 0.05 | 2026-05-15 | 2026-05-15 | 2026-04-23 | 2026-06-26 | 2026-06-26 | 2026-06-12 | 2026-08-07 | 2026-08-07 | 2026-06-12 | 2026-08-21 | 2026-08-21 | 2026-06-19 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-0002 | TOPSIDE - GENERAL NOTES SHEET 2 | 100% | 100% | 100% | 0% | 0.05 | 2026-05-15 | 2026-05-15 | 2026-04-23 | 2026-06-26 | 2026-06-26 | 2026-06-12 | 2026-08-07 | 2026-08-07 | 2026-06-12 | 2026-08-21 | 2026-08-21 | 2026-06-19 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-0011 | TOPSIDE - STANDARD DETAILS - DECK JOINTS - SHEET 1 | 100% | 100% | 100% | 0% | 0.1 | 2026-05-15 | 2026-05-15 | 2026-04-23 | 2026-06-26 | 2026-06-26 | 2026-06-12 | 2026-08-07 | 2026-08-07 | 2026-06-12 | 2026-08-21 | 2026-08-21 | 2026-06-19 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-0012 | TOPSIDE - STANDARD DETAILS - DECK JOINTS - SHEET 2 | 100% | 100% | 100% | 0% | 0.15 | 2026-05-15 | 2026-05-15 | 2026-04-23 | 2026-06-26 | 2026-06-26 | 2026-06-18 | 2026-08-07 | 2026-08-07 | 2026-08-07 | 2026-08-21 | 2026-08-21 | 2026-08-21 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-0013 | TOPSIDE - STANDARD DETAILS - DECK JOINTS - SHEET 3 | 100% | 100% | 100% | 0% | 0.15 | 2026-05-15 | 2026-05-15 | 2026-04-23 | 2026-06-26 | 2026-06-26 | 2026-06-12 | 2026-08-07 | 2026-08-07 | 2026-06-12 | 2026-08-21 | 2026-08-21 | 2026-06-19 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-0014 | TOPSIDE - STANDARD DETAILS - DECK JOINTS - SHEET 4 | 100% | 100% | 100% | 0% | 0.15 | 2026-05-15 | 2026-05-15 | 2026-04-23 | 2026-06-26 | 2026-06-26 | 2026-06-18 | 2026-08-07 | 2026-08-07 | 2026-08-07 | 2026-08-21 | 2026-08-21 | 2026-08-21 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-0015 | TOPSIDE - STANDARD DETAILS - HANDRAILS - SHEET 1 | 100% | 100% | 100% | 0% | 0.15 | 2026-05-15 | 2026-05-15 | 2026-04-23 | 2026-06-26 | 2026-06-26 | 2026-06-12 | 2026-08-07 | 2026-08-07 | 2026-06-12 | 2026-08-21 | 2026-08-21 | 2026-06-19 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-0016 | TOPSIDE - STANDARD DETAILS - HANDRAILS - SHEET 2 | 100% | 100% | 100% | 0% | 0.15 | 2026-05-15 | 2026-05-15 | 2026-04-23 | 2026-06-26 | 2026-06-26 | 2026-06-12 | 2026-08-07 | 2026-08-07 | 2026-06-12 | 2026-08-21 | 2026-08-21 | 2026-06-19 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-0017 | TOPSIDE - STANDARD DETAILS - STAIRS - SHEET 1 | 100% | 100% | 100% | 0% | 0.15 | 2026-05-15 | 2026-05-15 | 2026-04-23 | 2026-06-26 | 2026-06-26 | 2026-06-18 | 2026-08-07 | 2026-08-07 | 2026-08-07 | 2026-08-21 | 2026-08-21 | 2026-08-21 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-0018 | TOPSIDE - STANDARD DETAILS - STAIRS - SHEET 2 | 100% | 100% | 100% | 0% | 0.15 | 2026-05-15 | 2026-05-15 | 2026-04-23 | 2026-06-26 | 2026-06-26 | 2026-06-12 | 2026-08-07 | 2026-08-07 | 2026-06-12 | 2026-08-21 | 2026-08-21 | 2026-06-25 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-0019 | TOPSIDE - STANDARD DETAILS - LADDERS - SHEET 1 | 100% | 100% | 100% | 0% | 0.15 | 2026-05-15 | 2026-05-15 | 2026-04-23 | 2026-06-26 | 2026-06-26 | 2026-06-18 | 2026-08-07 | 2026-08-07 | 2026-08-07 | 2026-08-21 | 2026-08-21 | 2026-08-21 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-0020 | TOPSIDE - STANDARD DETAILS - LADDERS - SHEET 2 | 100% | 100% | 80% | -20% | 0.15 | 2026-05-15 | 2026-05-15 | 2026-04-23 | 2026-06-26 | 2026-06-26 | 2026-06-18 | 2026-08-07 | 2026-08-07 | 2026-08-07 | 2026-08-21 | 2026-08-21 |  |  | Completed | Completed | Completed | Overdue
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-0021 | TOPSIDE - STANDARD DETAILS - LADDERS - SHEET 3 | 100% | 100% | 100% | 0% | 0.15 | 2026-05-15 | 2026-05-15 | 2026-04-23 | 2026-06-26 | 2026-06-26 | 2026-08-07 | 2026-08-07 | 2026-08-07 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-0022 | TOPSIDE - STANDARD DETAILS - PLATING AND GRATING - SHEET 1 | 100% | 100% | 100% | 0% | 0.15 | 2026-05-15 | 2026-05-15 | 2026-04-23 | 2026-06-26 | 2026-06-26 | 2026-06-12 | 2026-08-07 | 2026-08-07 | 2026-06-12 | 2026-08-21 | 2026-08-21 | 2026-06-19 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-0023 | TOPSIDE - STANDARD DETAILS - PLATING AND GRATING - SHEET 2 | 100% | 100% | 100% | 0% | 0.15 | 2026-05-15 | 2026-05-15 | 2026-04-23 | 2026-06-26 | 2026-06-26 | 2026-06-12 | 2026-08-07 | 2026-08-07 | 2026-06-12 | 2026-08-21 | 2026-08-21 | 2026-06-25 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-0024 | TOPSIDE - STANDARD DETAILS - DECK DRAINS - SHEET 1 | 100% | 100% | 70% | -30% | 0.15 | 2026-05-15 | 2026-05-15 | 2026-04-23 | 2026-06-26 | 2026-06-26 | 2026-08-07 | 2026-08-07 | 2026-08-07 |  | 2026-08-21 | 2026-08-21 |  |  | Completed | Completed | Overdue | Overdue
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-0025 | TOPSIDE - STANDARD DETAILS - DECK DRAINS - SHEET 2 | 100% | 100% | 70% | -30% | 0.15 | 2026-05-15 | 2026-05-15 | 2026-04-23 | 2026-06-26 | 2026-06-26 | 2026-08-07 | 2026-08-07 | 2026-08-07 |  | 2026-08-21 | 2026-08-21 |  |  | Completed | Completed | Overdue | Overdue
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-0026 | TOPSIDE - STANDARD DETAILS - WELD PROFILE - SHEET 1 | 100% | 100% | 100% | 0% | 0.15 | 2026-05-15 | 2026-05-15 | 2026-04-23 | 2026-06-26 | 2026-06-26 | 2026-06-12 | 2026-08-07 | 2026-08-07 | 2026-06-12 | 2026-08-21 | 2026-08-21 | 2026-06-25 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-0027 | TOPSIDE - STANDARD DETAILS - WELD PROFILE - SHEET 2 | 100% | 100% | 100% | 0% | 0.15 | 2026-05-15 | 2026-05-15 | 2026-04-23 | 2026-06-26 | 2026-06-26 | 2026-06-12 | 2026-08-07 | 2026-08-07 | 2026-06-12 | 2026-08-21 | 2026-08-21 | 2026-06-25 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-0028 | TOPSIDE - STANDARD DETAILS - LOGO PAINTING | 100% | 100% | 100% | 0% | 0.15 | 2026-05-15 | 2026-05-15 | 2026-04-23 | 2026-06-26 | 2026-06-26 | 2026-06-12 | 2026-08-07 | 2026-08-07 | 2026-06-12 | 2026-08-21 | 2026-08-21 | 2026-06-19 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1001 | TOPSIDE - DRAWING INDEX - SHEET 1 | 70% | 70% | 50% | -20% | 0.05 | 2026-07-31 | 2026-07-31 | 2026-08-14 | 2026-09-11 | 2026-09-11 |  | 2026-10-23 | 2026-10-23 |  | 2026-11-06 | 2026-11-06 |  |  | Completed | Overdue
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1002 | TOPSIDE - DRAWING INDEX - SHEET 2 | 70% | 70% | 50% | -20% | 0.05 | 2026-07-31 | 2026-07-31 | 2026-08-14 | 2026-09-11 | 2026-09-11 |  | 2026-10-23 | 2026-10-23 |  | 2026-11-06 | 2026-11-06 |  |  | Completed | Overdue
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1003 | TOPSIDE - DRAWING INDEX - SHEET 3 | 70% | 70% | 50% | -20% | 0.05 | 2026-07-31 | 2026-07-31 | 2026-08-14 | 2026-09-11 | 2026-09-11 |  | 2026-10-23 | 2026-10-23 |  | 2026-11-06 | 2026-11-06 |  |  | Completed | Overdue
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1005 | TOPSIDE - DECK DESIGN LOADING DIAGRAMS | 70% | 70% | 70% | 0% | 0.15 | 2026-07-31 | 2026-07-31 | 2026-05-08 | 2026-09-11 | 2026-09-11 | 2026-07-24 | 2026-10-23 | 2026-10-23 |  | 2026-11-06 | 2026-11-06 |  |  | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1100 | TOPSIDE - UPPER DECK PRIMARY STEEL - FRAMING PLAN | 100% | 100% | 80% | -20% | 0.15 | 2026-05-29 | 2026-05-29 | 2026-05-08 | 2026-07-10 | 2026-07-10 | 2026-07-24 | 2026-08-21 | 2026-08-21 | 2026-09-21 | 2026-09-04 | 2026-09-04 |  | AWC | Completed | Completed | Completed | Overdue
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1101 | TOPSIDE - LOWER DECK PRIMARY STEEL - FRAMING PLAN | 100% | 100% | 100% | 0% | 0.15 | 2026-05-29 | 2026-05-29 | 2026-05-08 | 2026-07-10 | 2026-07-10 | 2026-07-24 | 2026-08-21 | 2026-08-21 | 2026-07-24 | 2026-09-04 | 2026-09-04 | 2026-09-25 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1102 | TOPSIDE - ELEVATION TRUSS ROW 'A' | 100% | 100% | 80% | -20% | 0.15 | 2026-05-29 | 2026-05-29 | 2026-05-08 | 2026-07-10 | 2026-07-10 | 2026-07-24 | 2026-08-21 | 2026-08-21 | 2026-10-05 | 2026-09-04 | 2026-09-04 |  |  | Completed | Completed | Completed | Overdue
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1103 | TOPSIDE - ELEVATION TRUSS ROW 'B' | 100% | 100% | 80% | -20% | 0.15 | 2026-05-29 | 2026-05-29 | 2026-05-08 | 2026-07-10 | 2026-07-10 | 2026-07-24 | 2026-08-21 | 2026-08-21 | 2026-10-05 | 2026-09-04 | 2026-09-04 |  |  | Completed | Completed | Completed | Overdue
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1104 | TOPSIDE - ELEVATION TRUSS ROW '1' | 100% | 100% | 100% | 0% | 0.15 | 2026-05-29 | 2026-05-29 | 2026-05-08 | 2026-07-10 | 2026-07-10 | 2026-07-24 | 2026-08-21 | 2026-08-21 | 2026-09-11 | 2026-09-04 | 2026-09-04 | 2026-09-25 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1105 | TOPSIDE - ELEVATION TRUSS ROW '2' | 100% | 100% | 80% | -20% | 0.15 | 2026-05-29 | 2026-05-29 | 2026-05-08 | 2026-07-10 | 2026-07-10 | 2026-07-24 | 2026-08-21 | 2026-08-21 | 2026-10-05 | 2026-09-04 | 2026-09-04 |  |  | Completed | Completed | Completed | Overdue
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1106 | TOPSIDE - SECTIONS | 100% | 100% | 70% | -30% | 0.15 | 2026-05-29 | 2026-05-29 | 2026-05-08 | 2026-07-10 | 2026-07-10 | 2026-07-24 | 2026-08-21 | 2026-08-21 |  | 2026-09-04 | 2026-09-04 |  |  | Completed | Completed | Overdue | Overdue
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1118 | TOPSIDE - UPPER DECK JOINT DETAIL MARKING PLAN | 100% | 100% | 80% | -20% | 0.15 | 2026-06-05 | 2026-06-05 | 2026-05-08 | 2026-07-17 | 2026-07-17 | 2026-07-24 | 2026-08-28 | 2026-08-28 | 2026-10-09 | 2026-09-11 | 2026-09-11 |  |  | Completed | Completed | Completed | Overdue
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1119 | TOPSIDE - LOWER DECK JOINT DETAIL MARKING PLAN | 100% | 100% | 80% | -20% | 0.15 | 2026-06-05 | 2026-06-05 | 2026-05-08 | 2026-07-17 | 2026-07-17 | 2026-07-24 | 2026-08-28 | 2026-08-28 | 2026-09-11 | 2026-09-11 | 2026-09-11 |  | AWC | Completed | Completed | Completed | Overdue
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1120 | TOPSIDE - MAIN JOINT DETAILS - SHEET 1 | 100% | 100% | 70% | -30% | 0.15 | 2026-06-05 | 2026-06-05 | 2026-05-08 | 2026-07-17 | 2026-07-17 | 2026-07-24 | 2026-08-28 | 2026-08-28 |  | 2026-09-11 | 2026-09-11 |  |  | Completed | Completed | Overdue | Overdue
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1121 | TOPSIDE - MAIN JOINT DETAILS - SHEET 2 | 100% | 100% | 80% | -20% | 0.15 | 2026-06-05 | 2026-06-05 | 2026-05-08 | 2026-07-17 | 2026-07-17 | 2026-07-24 | 2026-08-28 | 2026-08-28 | 2026-10-09 | 2026-09-11 | 2026-09-11 |  |  | Completed | Completed | Completed | Overdue
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1122 | TOPSIDE - MAIN JOINT DETAILS - SHEET 3 | 100% | 100% | 80% | -20% | 0.15 | 2026-06-05 | 2026-06-05 | 2026-05-08 | 2026-07-17 | 2026-07-17 | 2026-07-24 | 2026-08-28 | 2026-08-28 | 2026-10-09 | 2026-09-11 | 2026-09-11 |  |  | Completed | Completed | Completed | Overdue
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1123 | TOPSIDE - MAIN JOINT DETAILS - SHEET 4 | 100% | 100% | 80% | -20% | 0.15 | 2026-06-05 | 2026-06-05 | 2026-05-08 | 2026-07-17 | 2026-07-17 | 2026-07-24 | 2026-08-28 | 2026-08-28 | 2026-10-09 | 2026-09-11 | 2026-09-11 |  |  | Completed | Completed | Completed | Overdue
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1124 | TOPSIDE - MAIN JOINT DETAILS - SHEET 5 | 100% | 100% | 80% | -20% | 0.15 | 2026-06-05 | 2026-06-05 | 2026-05-08 | 2026-07-17 | 2026-07-17 | 2026-07-24 | 2026-08-28 | 2026-08-28 | 2026-10-09 | 2026-09-11 | 2026-09-11 |  |  | Completed | Completed | Completed | Overdue
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1125 | TOPSIDE - MAIN JOINT DETAILS - SHEET 6 | 100% | 100% | 80% | -20% | 0.15 | 2026-06-05 | 2026-06-05 | 2026-05-08 | 2026-07-17 | 2026-07-17 | 2026-07-24 | 2026-08-28 | 2026-08-28 | 2026-10-09 | 2026-09-11 | 2026-09-11 |  |  | Completed | Completed | Completed | Overdue
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1126 | TOPSIDE - MAIN JOINT DETAILS - SHEET 7 | 100% | 100% | 80% | -20% | 0.15 | 2026-06-05 | 2026-06-05 | 2026-05-08 | 2026-07-17 | 2026-07-17 | 2026-07-24 | 2026-08-28 | 2026-08-28 | 2026-10-09 | 2026-09-11 | 2026-09-11 |  |  | Completed | Completed | Completed | Overdue
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1127 | TOPSIDE - MAIN JOINT DETAILS - SHEET 8 | 100% | 100% | 80% | -20% | 0.15 | 2026-06-05 | 2026-06-05 | 2026-05-08 | 2026-07-17 | 2026-07-17 | 2026-07-24 | 2026-08-28 | 2026-08-28 | 2026-10-09 | 2026-09-11 | 2026-09-11 |  |  | Completed | Completed | Completed | Overdue
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1128 | TOPSIDE - MAIN JOINT DETAILS - SHEET 9 | 100% | 100% | 80% | -20% | 0.15 | 2026-06-05 | 2026-06-05 | 2026-05-08 | 2026-07-17 | 2026-07-17 | 2026-07-24 | 2026-08-28 | 2026-08-28 | 2026-10-09 | 2026-09-11 | 2026-09-11 |  |  | Completed | Completed | Completed | Overdue
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1129 | TOPSIDE - MAIN JOINT DETAILS - SHEET 10 | 100% | 100% | 80% | -20% | 0.15 | 2026-06-05 | 2026-06-05 | 2026-05-08 | 2026-07-17 | 2026-07-17 | 2026-07-24 | 2026-08-28 | 2026-08-28 | 2026-10-09 | 2026-09-11 | 2026-09-11 |  |  | Completed | Completed | Completed | Overdue
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1130 | TOPSIDE - MAIN JOINT DETAILS - SHEET 11 | 100% | 100% | 80% | -20% | 0.15 | 2026-06-05 | 2026-06-05 | 2026-05-08 | 2026-07-17 | 2026-07-17 | 2026-07-24 | 2026-08-28 | 2026-08-28 | 2026-10-09 | 2026-09-11 | 2026-09-11 |  |  | Completed | Completed | Completed | Overdue
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1131 | TOPSIDE - MAIN JOINT DETAILS - SHEET 12 | 100% | 100% | 100% | 0% | 0.15 | 2026-06-05 | 2026-06-05 | 2026-05-08 | 2026-07-17 | 2026-07-17 | 2026-07-24 | 2026-08-28 | 2026-08-28 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-25 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1132 | TOPSIDE - MAIN JOINT DETAILS - SHEET 13 | 100% | 100% | 100% | 0% | 0.15 | 2026-06-05 | 2026-06-05 | 2026-05-08 | 2026-07-17 | 2026-07-17 | 2026-07-24 | 2026-08-28 | 2026-08-28 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-10-02 | AWC - Minor | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1133 | TOPSIDE - MAIN JOINT DETAILS - SHEET 14 | 100% | 100% | 100% | 0% | 0.15 | 2026-06-05 | 2026-06-05 | 2026-05-08 | 2026-07-17 | 2026-07-17 | 2026-07-24 | 2026-08-28 | 2026-08-28 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-10-02 | AWC - Minor | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1134 | TOPSIDE - MAIN JOINT DETAILS - SHEET 15 | 100% | 100% | 100% | 0% | 0.15 | 2026-06-05 | 2026-06-05 | 2026-05-08 | 2026-07-17 | 2026-07-17 | 2026-07-24 | 2026-08-28 | 2026-08-28 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-10-02 | AWC - Minor | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1135 | TOPSIDE - MAIN JOINT DETAILS - SHEET 16 | 100% | 100% | 100% | 0% | 0.15 | 2026-06-05 | 2026-06-05 | 2026-05-08 | 2026-07-17 | 2026-07-17 | 2026-07-24 | 2026-08-28 | 2026-08-28 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-10-02 | AWC - Minor | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1136 | TOPSIDE - MAIN JOINT DETAILS - SHEET 17 | 100% | 100% | 100% | 0% | 0.15 | 2026-06-05 | 2026-06-05 | 2026-05-08 | 2026-07-17 | 2026-07-17 | 2026-07-24 | 2026-08-28 | 2026-08-28 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-25 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1137 | TOPSIDE - MAIN JOINT DETAILS - SHEET 18 | 100% | 100% | 100% | 0% | 0.15 | 2026-06-05 | 2026-06-05 | 2026-05-08 | 2026-07-17 | 2026-07-17 | 2026-07-24 | 2026-08-28 | 2026-08-28 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-10-02 | AWC - Minor | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1138 | TOPSIDE - MAIN JOINT DETAILS - SHEET 19 | 100% | 100% | 100% | 0% | 0.15 | 2026-06-05 | 2026-06-05 | 2026-05-08 | 2026-07-17 | 2026-07-17 | 2026-07-24 | 2026-08-28 | 2026-08-28 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-25 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1139 | TOPSIDE - MAIN JOINT DETAILS - SHEET 20 | 100% | 100% | 100% | 0% | 0.15 | 2026-06-05 | 2026-06-05 | 2026-05-08 | 2026-07-17 | 2026-07-17 | 2026-07-24 | 2026-08-28 | 2026-08-28 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-10-02 | AWC - Minor | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1140 | TOPSIDE - MAIN JOINT DETAILS - SHEET 21 | 100% | 100% | 100% | 0% | 0.15 | 2026-06-05 | 2026-06-05 | 2026-05-08 | 2026-07-17 | 2026-07-17 | 2026-07-24 | 2026-08-28 | 2026-08-28 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-25 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1141 | TOPSIDE - MAIN JOINT DETAILS - SHEET 22 (NEW) | [5 empty] | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-10-05 | 2026-10-05 | 2026-09-04 | 2026-11-16 | 2026-11-16 | 2026-10-09 | 2026-11-30 | 2026-11-30 |  |  | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1200 | TOPSIDE - UPPER DECK SECONDARY STEEL - FRAMING PLAN | 100% | 100% | 70% | -30% | 0.15 | 2026-06-12 | 2026-06-12 | 2026-05-29 | 2026-07-24 | 2026-07-24 | 2026-08-21 | 2026-09-04 | 2026-09-04 |  | 2026-09-18 | 2026-09-18 |  |  | Completed | Completed | Overdue | Overdue
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1201 | TOPSIDE - LOWER DECK SECONDARY STEEL - FRAMING PLAN | 100% | 100% | 70% | -30% | 0.15 | 2026-06-12 | 2026-06-12 | 2026-05-29 | 2026-07-24 | 2026-07-24 | 2026-08-21 | 2026-09-04 | 2026-09-04 |  | 2026-09-18 | 2026-09-18 |  |  | Completed | Completed | Overdue | Overdue
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1211 | TOPSIDE - MEZZANINE DECK FRAMING PLAN | 100% | 100% | 80% | -20% | 0.15 | 2026-06-12 | 2026-06-12 | 2026-05-19 | 2026-07-24 | 2026-07-24 | 2026-07-31 | 2026-09-04 | 2026-09-04 | 2026-10-09 | 2026-09-18 | 2026-09-18 |  |  | Completed | Completed | Completed | Overdue
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1212 | TOPSIDE - MEZZANINE DECK FRAMING SECTIONS - SHEET 1 | 100% | 100% | 80% | -20% | 0.15 | 2026-06-12 | 2026-06-12 | 2026-05-19 | 2026-07-24 | 2026-07-24 | 2026-07-31 | 2026-09-04 | 2026-09-04 | 2026-10-09 | 2026-09-18 | 2026-09-18 |  |  | Completed | Completed | Completed | Overdue
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1213 | TOPSIDE - MEZZANINE DECK FRAMING SECTIONS - SHEET 2 | 100% | 100% | 80% | -20% | 0.15 | 2026-06-12 | 2026-06-12 | 2026-05-19 | 2026-07-24 | 2026-07-24 | 2026-07-31 | 2026-09-04 | 2026-09-04 | 2026-10-09 | 2026-09-18 | 2026-09-18 |  |  | Completed | Completed | Completed | Overdue
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1214 | TOPSIDE - MEZZANINE DECK JOINT DETAILS - SHEET 1 | 100% | 100% | 80% | -20% | 0.15 | 2026-06-12 | 2026-06-12 | 2026-05-19 | 2026-07-24 | 2026-07-24 | 2026-07-31 | 2026-09-04 | 2026-09-04 | 2026-10-09 | 2026-09-18 | 2026-09-18 |  |  | Completed | Completed | Completed | Overdue
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1215 | TOPSIDE - MEZZANINE DECK JOINT DETAILS - SHEET 2 | 100% | 100% | 80% | -20% | 0.15 | 2026-06-12 | 2026-06-12 | 2026-05-19 | 2026-07-24 | 2026-07-24 | 2026-07-31 | 2026-09-04 | 2026-09-04 | 2026-10-09 | 2026-09-18 | 2026-09-18 |  |  | Completed | Completed | Completed | Overdue
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1216 | TOPSIDE - MEZZANINE DECK JOINT DETAILS - SHEET 3 | 100% | 100% | 80% | -20% | 0.15 | 2026-06-12 | 2026-06-12 | 2026-05-19 | 2026-07-24 | 2026-07-24 | 2026-07-31 | 2026-09-04 | 2026-09-04 | 2026-10-09 | 2026-09-18 | 2026-09-18 |  |  | Completed | Completed | Completed | Overdue
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1221 | TOPSIDE - SUMP DECK - FRAMING PLAN | 100% | 100% | 80% | -20% | 0.15 | 2026-06-12 | 2026-06-12 | 2026-05-19 | 2026-07-24 | 2026-07-24 | 2026-07-31 | 2026-09-04 | 2026-09-04 | 2026-09-28 | 2026-09-18 | 2026-09-18 |  | AWC | Completed | Completed | Completed | Overdue
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1222 | TOPSIDE - SUMP DECK SECTIONS | 100% | 100% | 100% | 0% | 0.15 | 2026-06-12 | 2026-06-12 | 2026-05-19 | 2026-07-24 | 2026-07-24 | 2026-07-31 | 2026-09-04 | 2026-09-04 | 2026-09-28 | 2026-09-18 | 2026-09-18 | 2026-10-01 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1223 | TOPSIDE - SUMP DECK JOINT DETAILS SHEET 1 | 100% | 100% | 100% | 0% | 0.15 | 2026-06-12 | 2026-06-12 | 2026-05-19 | 2026-07-24 | 2026-07-24 | 2026-07-31 | 2026-09-04 | 2026-09-04 | 2026-09-28 | 2026-09-18 | 2026-09-18 | 2026-10-01 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1224 | TOPSIDE - SUMP DECK JOINT DETAILS SHEET 2 | 100% | 100% | 100% | 0% | 0.15 | 2026-06-12 | 2026-06-12 | 2026-05-19 | 2026-07-24 | 2026-07-24 | 2026-07-31 | 2026-09-04 | 2026-09-04 | 2026-09-28 | 2026-09-18 | 2026-09-18 | 2026-10-01 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1225 | TOPSIDE - SUMP DECK JOINT DETAILS SHEET 3 | 100% | 100% | 100% | 0% | 0.15 | 2026-06-12 | 2026-06-12 | 2026-05-19 | 2026-07-24 | 2026-07-24 | 2026-07-31 | 2026-09-04 | 2026-09-04 | 2026-09-28 | 2026-09-18 | 2026-09-18 | 2026-10-01 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1226 | TOPSIDE - ACCESS PLATFORM FOR INSTRUMENT TUBING | 100% | 100% | 100% | 0% | 0.15 | 2026-06-12 | 2026-06-12 | 2026-05-19 | 2026-07-24 | 2026-07-24 | 2026-07-31 | 2026-09-04 | 2026-09-04 | 2026-09-28 | 2026-09-18 | 2026-09-18 | 2026-10-01 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1231 | TOPSIDE - CASING SLOT ARRANGEMENT | 100% | 100% | 80% | -20% | 0.15 | 2026-06-12 | 2026-06-12 | 2026-06-26 | 2026-07-24 | 2026-07-24 | 2026-08-21 | 2026-09-04 | 2026-09-04 | 2026-10-09 | 2026-09-18 | 2026-09-18 |  |  | Completed | Completed | Completed | Overdue
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1232 | TOPSIDE - UNIHEAD SPACER ARRANGEMENT AND DETAILS SHEET 1 | 100% | 100% | 80% | -20% | 0.15 | 2026-06-12 | 2026-06-12 | 2026-06-26 | 2026-07-24 | 2026-07-24 | 2026-08-21 | 2026-09-04 | 2026-09-04 | 2026-10-09 | 2026-09-18 | 2026-09-18 |  |  | Completed | Completed | Completed | Overdue
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1233 | TOPSIDE - UNIHEAD SPACER ARRANGEMENT AND DETAILS SHEET 2 - CANCELLED |  |  |  |  | 0.15 | 2026-06-12 | 2026-06-12 | 2026-08-14 | 2026-07-24 | 2026-07-24 | 2026-08-14 | 2026-09-04 | 2026-09-04 | 2026-08-14 | 2026-09-18 | 2026-09-18 | 2026-08-14 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1241 | TOPSIDE - VENT BOOM PLAND AND ELEVATION | 100% | 100% | 80% | -20% | 0.15 | 2026-06-26 | 2026-06-26 | 2026-05-29 | 2026-08-07 | 2026-08-07 | 2026-08-14 | 2026-09-18 | 2026-09-18 | 2026-10-09 | 2026-10-02 | 2026-10-02 |  |  | Completed | Completed | Completed | Overdue
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1242 | TOPSIDE - VENT BOOM SECTIONS | 100% | 100% | 80% | -20% | 0.15 | 2026-06-26 | 2026-06-26 | 2026-05-29 | 2026-08-07 | 2026-08-07 | 2026-08-14 | 2026-09-18 | 2026-09-18 | 2026-10-09 | 2026-10-02 | 2026-10-02 |  |  | Completed | Completed | Completed | Overdue
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1243 | TOPSIDE - VENT BOOM WALKWAY PLAN AND SECTIONS | 100% | 100% | 80% | -20% | 0.15 | 2026-06-26 | 2026-06-26 | 2026-05-29 | 2026-08-07 | 2026-08-07 | 2026-08-14 | 2026-09-18 | 2026-09-18 | 2026-10-09 | 2026-10-02 | 2026-10-02 |  |  | Completed | Completed | Completed | Overdue
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1244 | TOPSIDE - VENT BOOM WALKWAY SECTIONS AND DETAILS - SHEET 1 | 100% | 100% | 80% | -20% | 0.15 | 2026-06-26 | 2026-06-26 | 2026-05-29 | 2026-08-07 | 2026-08-07 | 2026-08-14 | 2026-09-18 | 2026-09-18 | 2026-10-09 | 2026-10-02 | 2026-10-02 |  |  | Completed | Completed | Completed | Overdue
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1245 | TOPSIDE - VENT BOOM WALKWAY SECTIONS AND DETAILS - SHEET 2 | 100% | 100% | 80% | -20% | 0.15 | 2026-06-26 | 2026-06-26 | 2026-05-29 | 2026-08-07 | 2026-08-07 | 2026-08-14 | 2026-09-18 | 2026-09-18 | 2026-10-09 | 2026-10-02 | 2026-10-02 |  |  | Completed | Completed | Completed | Overdue
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1246 | TOPSIDES - SOLAR PANEL SUPPORT DETAILS | 100% | 100% | 80% | -20% | 0.15 | 2026-06-26 | 2026-06-26 | 2026-06-05 | 2026-08-07 | 2026-08-07 | 2026-08-14 | 2026-09-18 | 2026-09-18 | 2026-10-09 | 2026-10-02 | 2026-10-02 |  |  | Completed | Completed | Completed | Overdue
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1247 | TOPSIDES - SOLAR PANEL SECTIONS | 100% | 100% | 80% | -20% | 0.1 | 2026-06-26 | 2026-06-26 | 2026-06-05 | 2026-08-07 | 2026-08-07 | 2026-08-14 | 2026-09-18 | 2026-09-18 | 2026-10-09 | 2026-10-02 | 2026-10-02 |  |  | Completed | Completed | Completed | Overdue
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1248 | TOPSIDES - SOLAR PANEL SUPPORT DETAILS - CANCELLED
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1300 | TOPSIDE - UPPER DECK FLOORING AND HANDRAIL - LAYOUT PLAN | 100% | 100% | 70% | -30% | 0.15 | 2026-06-26 | 2026-06-26 | 2026-06-26 | 2026-08-07 | 2026-08-07 | 2026-08-28 | 2026-09-18 | 2026-09-18 |  | 2026-10-02 | 2026-10-02 |  |  | Completed | Completed | Overdue | Overdue
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1301 | TOPSIDE - LOWER DECK FLOORING AND HANDRAIL - LAYOUT PLAN | 100% | 100% | 70% | -30% | 0.15 | 2026-06-26 | 2026-06-26 | 2026-06-26 | 2026-08-07 | 2026-08-07 | 2026-08-28 | 2026-09-18 | 2026-09-18 |  | 2026-10-02 | 2026-10-02 |  |  | Completed | Completed | Overdue | Overdue
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1302 | TOPSIDE - MEZZANINE DECK FLOORING AND HANDRAIL - LAYOUT PLAN | 100% | 100% | 70% | -30% | 0.15 | 2026-06-26 | 2026-06-26 | 2026-06-26 | 2026-08-07 | 2026-08-07 | 2026-08-28 | 2026-09-18 | 2026-09-18 |  | 2026-10-02 | 2026-10-02 |  |  | Completed | Completed | Overdue | Overdue
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1303 | TOPSIDE - SUMP DECK FLOORING AND HANDRAIL - LAYOUT PLAN | 100% | 100% | 70% | -30% | 0.15 | 2026-06-26 | 2026-06-26 | 2026-06-26 | 2026-08-07 | 2026-08-07 | 2026-08-28 | 2026-09-18 | 2026-09-18 |  | 2026-10-02 | 2026-10-02 |  |  | Completed | Completed | Overdue | Overdue
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1304 | TOPSIDES - FLOORING SECTION AND DETAILS - SHEET 1 | 100% | 100% | 50% | -50% | 0.1 | 2026-06-26 | 2026-06-26 | 2026-05-29 | 2026-08-07 | 2026-08-07 |  | 2026-09-18 | 2026-09-18 |  | 2026-10-02 | 2026-10-02 |  |  | Completed | Overdue | Overdue | Overdue
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1305 | TOPSIDES - FLOORING SECTION AND DETAILS - SHEET 2 - CANCELLED
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1306 | TOPSIDES - FLOORING SECTION AND DETAILS - SHEET 3 - CANCELLED
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1311 | TOPSIDE - STAIR LAYOUT & DETAILS - SHEET 1 | 80% | 80% | 70% | -10% | 0.1 | 2026-07-10 | 2026-07-10 | 2026-05-29 | 2026-08-21 | 2026-08-21 | 2026-08-07 | 2026-10-02 | 2026-10-02 |  | 2026-10-16 | 2026-10-16 |  |  | Completed | Completed | Overdue | Follow-Next Week
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1312 | TOPSIDE - STAIR LAYOUT & DETAILS - SHEET 2 | 80% | 80% | 70% | -10% | 0.1 | 2026-07-10 | 2026-07-10 | 2026-05-29 | 2026-08-21 | 2026-08-21 | 2026-08-07 | 2026-10-02 | 2026-10-02 |  | 2026-10-16 | 2026-10-16 |  |  | Completed | Completed | Overdue | Follow-Next Week
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1313 | TOPSIDE - STAIR LAYOUT & DETAILS - SHEET 3 | 80% | 80% | 70% | -10% | 0.1 | 2026-07-10 | 2026-07-10 | 2026-05-29 | 2026-08-21 | 2026-08-21 | 2026-08-07 | 2026-10-02 | 2026-10-02 |  | 2026-10-16 | 2026-10-16 |  |  | Completed | Completed | Overdue | Follow-Next Week
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1314 | TOPSIDE - STAIR LAYOUT & DETAILS - SHEET 4 | 80% | 80% | 80% | 0% | 0.1 | 2026-07-10 | 2026-07-10 | 2026-05-29 | 2026-08-21 | 2026-08-21 | 2026-06-18 | 2026-10-02 | 2026-10-02 | 2026-08-07 | 2026-10-16 | 2026-10-16 |  | AWC | Completed | Completed | Completed | Follow-Next Week
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1315 | TOPSIDE - STAIR LAYOUT & DETAILS - SHEET 5 | 80% | 80% | 80% | 0% | 0.1 | 2026-07-10 | 2026-07-10 | 2026-05-29 | 2026-08-21 | 2026-08-21 | 2026-08-07 | 2026-10-02 | 2026-10-02 | 2026-09-21 | 2026-10-16 | 2026-10-16 |  | AWC | Completed | Completed | Completed | Follow-Next Week
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1316 | TOPSIDE - STAIR LAYOUT & DETAILS - SHEET 6 | 80% | 80% | 80% | 0% | 0.1 | 2026-07-10 | 2026-07-10 | 2026-05-29 | 2026-08-21 | 2026-08-21 | 2026-06-18 | 2026-10-02 | 2026-10-02 | 2026-08-07 | 2026-10-16 | 2026-10-16 |  | AWC | Completed | Completed | Completed | Follow-Next Week
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1317 | TOPSIDE - STAIR LAYOUT & DETAILS - SHEET 7 | 80% | 80% | 70% | -10% | 0.1 | 2026-07-10 | 2026-07-10 | 2026-05-29 | 2026-08-21 | 2026-08-21 | 2026-08-07 | 2026-10-02 | 2026-10-02 |  | 2026-10-16 | 2026-10-16 |  |  | Completed | Completed | Overdue | Follow-Next Week
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1318 | TOPSIDE - STAIR LAYOUT & DETAILS - SHEET 8 | 80% | 80% | 70% | -10% | 0.1 | 2026-07-10 | 2026-07-10 | 2026-05-29 | 2026-08-21 | 2026-08-21 | 2026-08-07 | 2026-10-02 | 2026-10-02 |  | 2026-10-16 | 2026-10-16 |  |  | Completed | Completed | Overdue | Follow-Next Week
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1319 | TOPSIDE - STAIR LAYOUT & DETAILS - SHEET 9 | 80% | 80% | 70% | -10% | 0.1 | 2026-07-10 | 2026-07-10 | 2026-05-29 | 2026-08-21 | 2026-08-21 | 2026-08-07 | 2026-10-02 | 2026-10-02 |  | 2026-10-16 | 2026-10-16 |  |  | Completed | Completed | Overdue | Follow-Next Week
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1320 | TOPSIDES - LADDER DETAILS - FROM JACKET ACCESS PLATFORM TO SUMP DECK | 80% | 80% | 70% | -10% | 0.15 | 2026-07-10 | 2026-07-10 | 2026-06-26 | 2026-08-21 | 2026-08-21 | 2026-08-07 | 2026-10-02 | 2026-10-02 |  | 2026-10-16 | 2026-10-16 |  |  | Completed | Completed | Overdue | Follow-Next Week
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1321 | TOPSIDES - LADDER DETAILS - FROM LOWER DECK TO SUMP DECK |  | 80% | 70% | 70% | 0.15 | 2026-07-10 | 2026-07-10 | 2026-06-26 | 2026-08-21 | 2026-08-21 | 2026-07-02 | 2026-10-02 | 2026-10-02 |  | 2026-10-16 | 2026-10-16 |  |  | Completed | Completed | Overdue | Follow-Next Week
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1322 | TOPSIDES - LADDER DETAILS - FROM MEZZANINE DECK TO LOWER DECK SHEET 1 |  | 80% | 70% | 70% | 0.15 | 2026-07-10 | 2026-07-10 | 2026-06-26 | 2026-08-21 | 2026-08-21 | 2026-08-07 | 2026-10-02 | 2026-10-02 |  | 2026-10-16 | 2026-10-16 |  |  | Completed | Completed | Overdue | Follow-Next Week
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1323 | TOPSIDES - LADDER DETAILS - FROM MEZZANINE DECK TO LOWER DECK SHEET 2 |  | 80% | 70% | 70% | 0.15 | 2026-07-10 | 2026-07-10 | 2026-06-26 | 2026-08-21 | 2026-08-21 | 2026-08-07 | 2026-10-02 | 2026-10-02 |  | 2026-10-16 | 2026-10-16 |  |  | Completed | Completed | Overdue | Follow-Next Week
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1324 | TOPSIDES - LADDER DETAILS - FROM MEZZANINE DECK TO LOWER DECK SHEET 3 - CANCELLED
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1325 | TOPSIDES - LADDER DETAILS - FROM MEZZANINE DECK TO LOWER DECK SHEET 4 - CANCELLED
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1351 | TOPSIDE - UPPER DECK DRAIN LAYOUT PLAN | 80% | 80% | 70% | -10% | 0.1 | 2026-07-10 | 2026-07-10 | 2026-05-29 | 2026-08-21 | 2026-08-21 | 2026-08-14 | 2026-10-02 | 2026-10-02 |  | 2026-10-16 | 2026-10-16 |  |  | Completed | Completed | Overdue | Follow-Next Week
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1352 | TOPSIDE - LOWER DECK DRAIN LAYOUT PLAN | 80% | 80% | 70% | -10% | 0.1 | 2026-07-10 | 2026-07-10 | 2026-05-29 | 2026-08-21 | 2026-08-21 | 2026-08-14 | 2026-10-02 | 2026-10-02 |  | 2026-10-16 | 2026-10-16 |  |  | Completed | Completed | Overdue | Follow-Next Week
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1400 | TOPSIDE - DECK HATCH ARRANGEMENT AND DETAILS - SHEET 1 | 80% | 80% | 70% | -10% | 0.1 | 2026-07-10 | 2026-07-10 | 2026-05-29 | 2026-08-21 | 2026-08-21 | 2026-08-28 | 2026-10-02 | 2026-10-02 |  | 2026-10-16 | 2026-10-16 |  |  | Completed | Completed | Overdue | Follow-Next Week
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1401 | TOPSIDE - DECK HATCH ARRANGEMENT AND DETAILS - SHEET 2 | 80% | 80% | 70% | -10% | 0.1 | 2026-07-10 | 2026-07-10 | 2026-05-29 | 2026-08-21 | 2026-08-21 | 2026-08-28 | 2026-10-02 | 2026-10-02 |  | 2026-10-16 | 2026-10-16 |  |  | Completed | Completed | Overdue | Follow-Next Week
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1402 | TOPSIDE - DECK HATCH ARRANGEMENT AND DETAILS - SHEET 3 | 80% | 80% | 70% | -10% | 0.1 | 2026-07-10 | 2026-07-10 | 2026-05-29 | 2026-08-21 | 2026-08-21 | 2026-08-28 | 2026-10-02 | 2026-10-02 |  | 2026-10-16 | 2026-10-16 |  |  | Completed | Completed | Overdue | Follow-Next Week
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1403 | TOPSIDE - DECK HATCH ARRANGEMENT AND DETAILS - SHEET 4 | 80% | 80% | 70% | -10% | 0.1 | 2026-07-10 | 2026-07-10 | 2026-05-29 | 2026-08-21 | 2026-08-21 | 2026-08-28 | 2026-10-02 | 2026-10-02 |  | 2026-10-16 | 2026-10-16 |  |  | Completed | Completed | Overdue | Follow-Next Week
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1404 | TOPSIDE - DECK HATCH ARRANGEMENT AND DETAILS - SHEET 5 | 80% | 80% | 70% | -10% | 0.1 | 2026-07-10 | 2026-07-10 | 2026-05-29 | 2026-08-21 | 2026-08-21 | 2026-08-28 | 2026-10-02 | 2026-10-02 |  | 2026-10-16 | 2026-10-16 |  |  | Completed | Completed | Overdue | Follow-Next Week
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1405 | TOPSIDE - DECK HATCH ARRANGEMENT AND DETAILS - SHEET 6 | 80% | 80% | 70% | -10% | 0.1 | 2026-07-10 | 2026-07-10 | 2026-05-29 | 2026-08-21 | 2026-08-21 | 2026-08-28 | 2026-10-02 | 2026-10-02 |  | 2026-10-16 | 2026-10-16 |  |  | Completed | Completed | Overdue | Follow-Next Week
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1406 | TOPSIDE - DECK HATCH ARRANGEMENT AND DETAILS - SHEET 7 | 80% | 80% | 70% | -10% | 0.1 | 2026-07-10 | 2026-07-10 | 2026-05-29 | 2026-08-21 | 2026-08-21 | 2026-08-28 | 2026-10-02 | 2026-10-02 |  | 2026-10-16 | 2026-10-16 |  |  | Completed | Completed | Overdue | Follow-Next Week
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1407 | TOPSIDE - DECK HATCH ARRANGEMENT AND DETAILS - SHEET 8 | 80% | 80% | 70% | -10% | 0.1 | 2026-07-10 | 2026-07-10 | 2026-05-29 | 2026-08-21 | 2026-08-21 | 2026-08-28 | 2026-10-02 | 2026-10-02 |  | 2026-10-16 | 2026-10-16 |  |  | Completed | Completed | Overdue | Follow-Next Week
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1431 | TOPSIDES - LIFT POINT FOR STRETCHER - PLAN AND DETAIL - CANCELLED
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1500 | TOPSIDE - E&I ROOM PLAN | 80% | 80% | 70% | -10% | 0.1 | 2026-07-17 | 2026-07-17 | 2026-06-05 | 2026-08-28 | 2026-08-28 | 2026-08-14 | 2026-10-09 | 2026-10-09 |  | 2026-10-23 | 2026-10-23 |  |  | Completed | Completed | Overdue
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1501 | TOPSIDE - E&I ROOM ROOF PLAN | 80% | 80% | 70% | -10% | 0.1 | 2026-07-17 | 2026-07-17 | 2026-06-05 | 2026-08-28 | 2026-08-28 | 2026-08-14 | 2026-10-09 | 2026-10-09 |  | 2026-10-23 | 2026-10-23 |  |  | Completed | Completed | Overdue
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1502 | TOPSIDE - E&I ROOM SECTIONS AND DETAILS - SHEET 1 | 80% | 80% | 70% | -10% | 0.1 | 2026-07-17 | 2026-07-17 | 2026-06-05 | 2026-08-28 | 2026-08-28 | 2026-08-14 | 2026-10-09 | 2026-10-09 |  | 2026-10-23 | 2026-10-23 |  |  | Completed | Completed | Overdue
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1503 | TOPSIDE - E&I ROOM SECTIONS AND DETAILS - SHEET 2 | 80% | 80% | 70% | -10% | 0.1 | 2026-07-17 | 2026-07-17 | 2026-06-05 | 2026-08-28 | 2026-08-28 | 2026-08-14 | 2026-10-09 | 2026-10-09 |  | 2026-10-23 | 2026-10-23 |  |  | Completed | Completed | Overdue
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1504 | TOPSIDE - E&I ROOM ELEVATIONS | 80% | 80% | 70% | -10% | 0.1 | 2026-07-17 | 2026-07-17 | 2026-06-05 | 2026-08-28 | 2026-08-28 | 2026-08-14 | 2026-10-09 | 2026-10-09 |  | 2026-10-23 | 2026-10-23 |  |  | Completed | Completed | Overdue
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1505 | TOPSIDE - WIND DRIVEN VENTILATION FAN SECTIONS AND DETALS | 80% | 80% | 70% | -10% | 0.1 | 2026-07-17 | 2026-07-17 | 2026-06-05 | 2026-08-28 | 2026-08-28 | 2026-08-14 | 2026-10-09 | 2026-10-09 |  | 2026-10-23 | 2026-10-23 |  |  | Completed | Completed | Overdue
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1506 | TOPSIDES - LADDER DETAILS FOR E&I ROOM | 80% | 80% | 70% | -10% | 0.1 | 2026-07-17 | 2026-07-17 | 2026-06-12 | 2026-08-28 | 2026-08-28 | 2026-08-14 | 2026-10-09 | 2026-10-09 |  | 2026-10-23 | 2026-10-23 |  |  | Completed | Completed | Overdue
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1512 | TOPSIDE - CRANE BOOM REST DETAILS | 80% | 80% | 70% | -10% | 0.1 | 2026-07-17 | 2026-07-17 | 2026-05-29 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-10-09 | 2026-10-09 |  | 2026-10-23 | 2026-10-23 |  |  | Completed | Completed | Overdue
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1513 | TOPSIDE - DRILLING MUD RETURN LINE SUPPORT - PLAN, SECTION AND DETAILS - CANCELLED |  |  |  |  | 0.1 | 2026-07-17 | 2026-07-17 | 2026-08-14 | 2026-08-28 | 2026-08-28 | 2026-08-14 | 2026-10-09 | 2026-10-09 | 2026-08-14 | 2026-10-23 | 2026-10-23 | 2026-08-14 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1531 | TOPSIDE - CONDENSATE BURNER BOOM SUPPORT ARRANGEMENT AND DETAILS - SHEET 1 | 80% | 80% | 70% | -10% | 0.15 | 2026-07-17 | 2026-07-17 | 2026-06-26 | 2026-08-28 | 2026-08-28 | 2026-07-01 | 2026-10-09 | 2026-10-09 |  | 2026-10-23 | 2026-10-23 |  |  | Completed | Completed | Overdue
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1532 | TOPSIDE - CONDENSATE BURNER BOOM SUPPORT ARRANGEMENT AND DETAILS - SHEET 2 | 80% | 80% | 70% | -10% | 0.15 | 2026-07-17 | 2026-07-17 | 2026-06-26 | 2026-08-28 | 2026-08-28 | 2026-07-01 | 2026-10-09 | 2026-10-09 |  | 2026-10-23 | 2026-10-23 |  |  | Completed | Completed | Overdue
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1611 | TOPSIDE - TYPICAL EQUIPMENT SUPPORT DETAILS - SHEET 1 | 70% | 70% | 70% | 0% | 0.1 | 2026-07-24 | 2026-07-24 | 2026-06-05 | 2026-09-04 | 2026-09-04 | 2026-08-21 | 2026-10-16 | 2026-10-16 |  | 2026-10-30 | 2026-10-30 |  |  | Completed | Completed | Follow-Next Week
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1612 | TOPSIDE - TYPICAL EQUIPMENT SUPPORT DETAILS - SHEET 2 | 70% | 70% | 70% | 0% | 0.1 | 2026-07-24 | 2026-07-24 | 2026-06-05 | 2026-09-04 | 2026-09-04 | 2026-08-21 | 2026-10-16 | 2026-10-16 |  | 2026-10-30 | 2026-10-30 |  |  | Completed | Completed | Follow-Next Week
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1613 | TOPSIDE - TYPICAL EQUIPMENT SUPPORT DETAILS - SHEET 3 | 70% | 70% | 70% | 0% | 0.1 | 2026-07-24 | 2026-07-24 | 2026-06-05 | 2026-09-04 | 2026-09-04 | 2026-08-21 | 2026-10-16 | 2026-10-16 |  | 2026-10-30 | 2026-10-30 |  |  | Completed | Completed | Follow-Next Week
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1614 | TOPSIDE - TYPICAL EQUIPMENT SUPPORT DETAILS - SHEET 4 | 70% | 70% | 70% | 0% | 0.1 | 2026-07-24 | 2026-07-24 | 2026-06-05 | 2026-09-04 | 2026-09-04 | 2026-08-21 | 2026-10-16 | 2026-10-16 |  | 2026-10-30 | 2026-10-30 |  |  | Completed | Completed | Follow-Next Week
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1615 | TOPSIDE - TYPICAL EQUIPMENT SUPPORT DETAILS - SHEET 5 | 70% | 70% | 70% | 0% | 0.1 | 2026-07-24 | 2026-07-24 | 2026-06-05 | 2026-09-04 | 2026-09-04 | 2026-08-21 | 2026-10-16 | 2026-10-16 |  | 2026-10-30 | 2026-10-30 |  |  | Completed | Completed | Follow-Next Week
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1616 | TOPSIDE - TYPICAL EQUIPMENT SUPPORT DETAILS - SHEET 6 | 70% | 70% | 70% | 0% | 0.1 | 2026-07-24 | 2026-07-24 | 2026-06-05 | 2026-09-04 | 2026-09-04 | 2026-08-21 | 2026-10-16 | 2026-10-16 |  | 2026-10-30 | 2026-10-30 |  |  | Completed | Completed | Follow-Next Week
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1617 | TOPSIDE - TYPICAL EQUIPMENT SUPPORT DETAILS - SHEET 7 | 70% | 70% | 70% | 0% | 0.1 | 2026-07-24 | 2026-07-24 | 2026-06-05 | 2026-09-04 | 2026-09-04 | 2026-08-21 | 2026-10-16 | 2026-10-16 |  | 2026-10-30 | 2026-10-30 |  |  | Completed | Completed | Follow-Next Week
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1618 | TOPSIDE - TYPICAL EQUIPMENT SUPPORT DETAILS - SHEET 8 | 70% | 70% | 70% | 0% | 0.1 | 2026-07-24 | 2026-07-24 | 2026-06-05 | 2026-09-04 | 2026-09-04 | 2026-08-21 | 2026-10-16 | 2026-10-16 |  | 2026-10-30 | 2026-10-30 |  |  | Completed | Completed | Follow-Next Week
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1619 | TOPSIDE - TYPICAL EQUIPMENT SUPPORT DETAILS - SHEET 9 | 70% | 70% | 70% | 0% | 0.1 | 2026-07-24 | 2026-07-24 | 2026-06-05 | 2026-09-04 | 2026-09-04 | 2026-08-21 | 2026-10-16 | 2026-10-16 |  | 2026-10-30 | 2026-10-30 |  |  | Completed | Completed | Follow-Next Week
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1620 | TOPSIDE - TYPICAL EQUIPMENT SUPPORT DETAILS - SHEET 10 | 70% | 70% | 70% | 0% | 0.1 | 2026-07-24 | 2026-07-24 | 2026-06-05 | 2026-09-04 | 2026-09-04 | 2026-08-21 | 2026-10-16 | 2026-10-16 |  | 2026-10-30 | 2026-10-30 |  |  | Completed | Completed | Follow-Next Week
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1621 | TOPSIDE - TYPICAL EQUIPMENT SUPPORT DETAILS - SHEET 11 | 70% | 70% | 70% | 0% | 0.1 | 2026-07-24 | 2026-07-24 | 2026-06-12 | 2026-09-04 | 2026-09-04 | 2026-08-21 | 2026-10-16 | 2026-10-16 |  | 2026-10-30 | 2026-10-30 |  |  | Completed | Completed | Follow-Next Week
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1622 | TOPSIDE - TYPICAL EQUIPMENT SUPPORT DETAILS - SHEET 12 | 70% | 70% | 70% | 0% | 0.1 | 2026-07-24 | 2026-07-24 | 2026-06-05 | 2026-09-04 | 2026-09-04 | 2026-08-21 | 2026-10-16 | 2026-10-16 |  | 2026-10-30 | 2026-10-30 |  |  | Completed | Completed | Follow-Next Week
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1623 | TOPSIDES - TYPICAL EQUIPMENT SUPPORT DETAILS - SHEET 13 | 70% | 70% | 70% | 0% | 0.1 | 2026-07-24 | 2026-07-24 | 2026-06-12 | 2026-09-04 | 2026-09-04 | 2026-08-21 | 2026-10-16 | 2026-10-16 |  | 2026-10-30 | 2026-10-30 |  |  | Completed | Completed | Follow-Next Week
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1624 | TOPSIDES - TYPICAL EQUIPMENT SUPPORT DETAILS - SHEET 14 | 70% | 70% | 70% | 0% | 0.1 | 2026-07-24 | 2026-07-24 | 2026-06-12 | 2026-09-04 | 2026-09-04 | 2026-08-21 | 2026-10-16 | 2026-10-16 |  | 2026-10-30 | 2026-10-30 |  |  | Completed | Completed | Follow-Next Week
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1625 | TOPSIDES - TYPICAL EQUIPMENT SUPPORT DETAILS - SHEET 15 - CANCELLED |  |  |  |  | 0.1 | 2026-07-24 | 2026-07-24 | 2026-08-14 | 2026-09-04 | 2026-09-04 | 2026-08-14 | 2026-10-16 | 2026-10-16 | 2026-08-14 | 2026-10-30 | 2026-10-30 | 2026-08-14 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1625 | TOPSIDES - TYPICAL EQUIPMENT SUPPORT DETAILS - SHEET 15 | 70% | 70% | 50% | -20% |  | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-10-02 | 2026-10-02 |  | 2026-11-13 | 2026-11-13 |  | 2026-11-27 | 2026-11-27 |  |  | Completed | Overdue
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1626 | TOPSIDES - STEP LAYOUT AND SECTION | 70% | 70% | 70% | 0% | 0.1 | 2026-07-24 | 2026-07-24 | 2026-08-21 | 2026-09-04 | 2026-09-04 | 2026-09-04 | 2026-10-16 | 2026-10-16 |  | 2026-10-30 | 2026-10-30 |  |  | Completed | Completed | Follow-Next Week
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1627 | TOPSIDES - PADEYE COLUMN REMOVABLE, PLAN, SECTION AND DETAILS | 70% | 70% | 50% | -20% | 0.1 | 2026-07-24 | 2026-07-24 | 2026-10-09 | 2026-09-04 | 2026-09-04 |  | 2026-10-16 | 2026-10-16 |  | 2026-10-30 | 2026-10-30 |  |  | Completed | Overdue | Follow-Next Week
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1628 | TOPSIDES - TYPICAL EQUIPMENT SUPPORT IN E&I ROOM SECTIONS | 70% | 70% | 50% | -20% | 0.1 | 2026-07-24 | 2026-07-24 | 2026-10-09 | 2026-09-04 | 2026-09-04 |  | 2026-10-16 | 2026-10-16 |  | 2026-10-30 | 2026-10-30 |  |  | Completed | Overdue | Follow-Next Week
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1629 | TOPSIDES - TYPICAL EQUIPMENT SUPPORT FOG HORN CONTROL PANEL & FOG HORN SECTIONS |  |  |  |  | 0.1 | 2026-07-24 | 2026-07-24 | 2026-08-21 | 2026-09-04 | 2026-09-04 | 2026-08-21 | 2026-10-16 | 2026-10-16 | 2026-08-21 | 2026-10-30 | 2026-10-30 | 2026-08-21 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1641 | TOPSIDES - SAFETY SIGNS SUPPORT DETAILS SHEET 1 | 70% | 70% | 70% | 0% | 0.1 | 2026-07-24 | 2026-07-24 | 2026-08-03 | 2026-09-04 | 2026-09-04 | 2026-08-10 | 2026-10-16 | 2026-10-16 |  | 2026-10-30 | 2026-10-30 |  |  | Completed | Completed | Follow-Next Week
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1642 | TOPSIDES - SAFETY SIGNS SUPPORT DETAILS SHEET 2 | 70% | 70% | 70% | 0% | 0.1 | 2026-07-24 | 2026-07-24 | 2026-08-03 | 2026-09-04 | 2026-09-04 | 2026-08-10 | 2026-10-16 | 2026-10-16 |  | 2026-10-30 | 2026-10-30 |  |  | Completed | Completed | Follow-Next Week
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1643 | TOPSIDES - UPPER DECK FLOORING LAYOUT FOR SAFETY SIGN SUPPORT AT TOPL EL(+) 24820 - CANCELLED |  |  |  |  | 0.1 | 2026-07-24 | 2026-07-24 | 2026-08-14 | 2026-09-04 | 2026-09-04 | 2026-08-14 | 2026-10-16 | 2026-10-16 | 2026-08-14 | 2026-10-30 | 2026-10-30 | 2026-08-14 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1644 | TOPSIDES - MEZZANINE DECK FLOORING LAYOUT FOR SAFETY SIGN SUPPORT AT TOG EL(+) 21138 & 21338 | 70% | 70% | 70% | 0% | 0.1 | 2026-07-24 | 2026-07-24 | 2026-08-03 | 2026-09-04 | 2026-09-04 | 2026-08-10 | 2026-10-16 | 2026-10-16 |  | 2026-10-30 | 2026-10-30 |  |  | Completed | Completed | Follow-Next Week
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1645 | TOPSIDES - LOWER DECK FLOORING LAYOUT FOR SAFETY SIGN SUPPORT AT TOPL EL(+) 18310 | 70% | 70% | 70% | 0% | 0.1 | 2026-07-24 | 2026-07-24 | 2026-08-03 | 2026-09-04 | 2026-09-04 | 2026-08-10 | 2026-10-16 | 2026-10-16 |  | 2026-10-30 | 2026-10-30 |  |  | Completed | Completed | Follow-Next Week
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1646 | TOPSIDES - SUMP DECK FLOORING LAYOUT FOR SAFETY SIGN SUPPORT AT TOG EL(+) 14738 & 8488 | 70% | 70% | 70% | 0% | 0.1 | 2026-07-24 | 2026-07-24 | 2026-08-03 | 2026-09-04 | 2026-09-04 | 2026-08-10 | 2026-10-16 | 2026-10-16 |  | 2026-10-30 | 2026-10-30 |  |  | Completed | Completed | Follow-Next Week
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1654 | TOPSIDES - MEZZANINE DECK FLOORING LAYOUT FOR SAFETY EQUIPMENT SUPPORT AT TOG EL(+) 21138 & 21338 - SUPERSEDED |  |  |  |  | 0.1 | 2026-07-24 | 2026-07-24 | 2026-07-31 | 2026-09-04 | 2026-09-04 | 2026-07-31 | 2026-10-16 | 2026-10-16 | 2026-07-31 | 2026-10-30 | 2026-10-30 | 2026-07-31 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1655 | TOPSIDES - LOWER DECK FLOORING LAYOUT FOR SAFETY EQUIPMENT SUPPORT AT TOPL EL(+) 18310 - SUPERSEDED |  |  |  |  | 0.1 | 2026-07-24 | 2026-07-24 | 2026-07-31 | 2026-09-04 | 2026-09-04 | 2026-07-31 | 2026-10-16 | 2026-10-16 | 2026-07-31 | 2026-10-30 | 2026-10-30 | 2026-07-31 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1656 | TOPSIDES - SUMP DECK FLOORING LAYOUT FOR SAFETY EQUIPMENT SUPPORT AT TOG EL(+) 14738 & 8488 - SUPERSEDED |  |  |  |  | 0.1 | 2026-07-24 | 2026-07-24 | 2026-07-31 | 2026-09-04 | 2026-09-04 | 2026-07-31 | 2026-10-16 | 2026-10-16 | 2026-08-01 | 2026-10-30 | 2026-10-30 | 2026-07-31 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1657 | TOPSIDES - DRILLING MUD RETURN LINE SUPPORT - PLAN, SECTION AND DETAILS |  |  |  |  | 0 | 2026-07-24 | 2026-07-24 | 2026-07-31 | 2026-09-04 | 2026-09-04 | 2026-07-31 | 2026-10-16 | 2026-10-16 | 2026-08-02 | 2026-10-30 | 2026-10-30 | 2026-07-31 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1711 | TOPSIDE - AMENITIES CUBICLE DETAILS | 70% | 70% | 70% | 0% | 0.1 | 2026-07-24 | 2026-07-24 | 2026-06-12 | 2026-09-04 | 2026-09-04 | 2026-08-21 | 2026-10-16 | 2026-10-16 |  | 2026-10-30 | 2026-10-30 |  |  | Completed | Completed | Follow-Next Week
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1712 | TOPSIDE - PLATFORM NAME PLATE / IDENTIFICATION PANEL - SHEET 1 | 70% | 70% | 100% | 30% | 0.1 | 2026-07-24 | 2026-07-24 | 2026-06-12 | 2026-09-04 | 2026-09-04 | 2026-06-19 | 2026-10-16 | 2026-10-16 | 2026-08-21 | 2026-10-30 | 2026-10-30 | 2026-09-04 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1713 | TOPSIDE - PLATFORM NAME PLATE / IDENTIFICATION PANEL - SHEET 2 | 70% | 70% | 80% | 10% | 0.1 | 2026-07-24 | 2026-07-24 | 2026-06-12 | 2026-09-04 | 2026-09-04 | 2026-06-19 | 2026-10-16 | 2026-10-16 | 2026-08-21 | 2026-10-30 | 2026-10-30 |  | AWC | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1714 | TOPSIDE - SWING ROPE DETAILS - SHEET 1 | 70% | 70% | 70% | 0% | 0.1 | 2026-07-24 | 2026-07-24 | 2026-05-29 | 2026-09-04 | 2026-09-04 | 2026-08-21 | 2026-10-16 | 2026-10-16 |  | 2026-10-30 | 2026-10-30 |  |  | Completed | Completed | Follow-Next Week
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1715 | TOPSIDE - SWING ROPE DETAILS - SHEET 2 | 70% | 70% | 70% | 0% | 0.1 | 2026-07-24 | 2026-07-24 | 2026-05-29 | 2026-09-04 | 2026-09-04 | 2026-08-21 | 2026-10-16 | 2026-10-16 |  | 2026-10-30 | 2026-10-30 |  |  | Completed | Completed | Follow-Next Week
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1716 | TOPSIDE - LIFE RAFT AND DESCENDING DEVICES SUPPORT SHEET 1 | 70% | 70% | 70% | 0% | 0.1 | 2026-07-24 | 2026-07-24 | 2026-08-14 | 2026-09-04 | 2026-09-04 | 2026-09-04 | 2026-10-16 | 2026-10-16 |  | 2026-10-30 | 2026-10-30 |  |  | Completed | Completed | Follow-Next Week
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1717 | TOPSIDE - LIFE RAFT AND DESCENDING DEVICES SUPPORT SHEET 2 | 70% | 70% | 70% | 0% | 0.1 | 2026-07-24 | 2026-07-24 | 2026-08-14 | 2026-09-04 | 2026-09-04 | 2026-09-04 | 2026-10-16 | 2026-10-16 |  | 2026-10-30 | 2026-10-30 |  |  | Completed | Completed | Follow-Next Week
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1722 | TOPSIDE - SECURITY GATE DETAILS - SHEET 1 | 70% | 70% | 70% | 0% | 0.1 | 2026-07-24 | 2026-07-24 | 2026-06-12 | 2026-09-04 | 2026-09-04 | 2026-08-21 | 2026-10-16 | 2026-10-16 |  | 2026-10-30 | 2026-10-30 |  |  | Completed | Completed | Follow-Next Week
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1723 | TOPSIDE - SECURITY GATE DETAILS - SHEET 2 | 70% | 70% | 100% | 30% | 0.1 | 2026-07-24 | 2026-07-24 | 2026-06-12 | 2026-09-04 | 2026-09-04 | 2026-06-19 | 2026-10-16 | 2026-10-16 | 2026-08-21 | 2026-10-30 | 2026-10-30 | 2026-09-04 |  | Completed | Completed | Completed | Completed
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1801 | TOPSIDE - GENERAL MUD WALL - FRAMING PLAN & DETAILS | 70% | 70% | 70% | 0% | 0.1 | 2026-07-24 | 2026-07-24 | 2026-05-29 | 2026-09-04 | 2026-09-04 | 2026-08-21 | 2026-10-16 | 2026-10-16 |  | 2026-10-30 | 2026-10-30 |  |  | Completed | Completed | Follow-Next Week
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1802 | TOPSIDE - GENERAL MUD WALL - SECTIONS AND DETAILS - SHEET 1 | 70% | 70% | 70% | 0% | 0.1 | 2026-07-24 | 2026-07-24 | 2026-05-29 | 2026-09-04 | 2026-09-04 | 2026-08-21 | 2026-10-16 | 2026-10-16 |  | 2026-10-30 | 2026-10-30 |  |  | Completed | Completed | Follow-Next Week
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1803 | TOPSIDE - GENERAL MUD WALL - SECTIONS AND DETAILS - SHEET 2 | 70% | 70% | 70% | 0% | 0.1 | 2026-07-24 | 2026-07-24 | 2026-05-29 | 2026-09-04 | 2026-09-04 | 2026-08-21 | 2026-10-16 | 2026-10-16 |  | 2026-10-30 | 2026-10-30 |  |  | Completed | Completed | Follow-Next Week
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1804 | TOPSIDE - GENERAL MUD WALL - CANVAS PLAN | 70% | 70% | 70% | 0% | 0.1 | 2026-07-24 | 2026-07-24 | 2026-05-29 | 2026-09-04 | 2026-09-04 | 2026-08-21 | 2026-10-16 | 2026-10-16 |  | 2026-10-30 | 2026-10-30 |  |  | Completed | Completed | Follow-Next Week
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1901 | TOPSIDE - LIFTING ARRANGEMENT | 100% | 100% | 70% | -30% | 0.1 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-07-24 | 2026-07-24 | 2026-08-21 | 2026-09-04 | 2026-09-04 |  | 2026-09-18 | 2026-09-18 |  |  | Completed | Completed | Overdue | Overdue
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1902 | TOPSIDE - LIFTING PADEYE DETAILS | 100% | 100% | 70% | -30% | 0.1 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-07-24 | 2026-07-24 | 2026-08-21 | 2026-09-04 | 2026-09-04 |  | 2026-09-18 | 2026-09-18 |  |  | Completed | Completed | Overdue | Overdue
ZAWTIKA Z1F TS | GENERIC | DWG | MM-ZTK-1F-ZWPX-STR-DWG-1903 | TOPSIDE - LIFTING PADEYE DETAILS SHEET 2 | 100% | 100% | 70% | -30% | 0.1 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-07-24 | 2026-07-24 | 2026-08-21 | 2026-09-04 | 2026-09-04 |  | 2026-09-18 | 2026-09-18 |  |  | Completed | Completed | Overdue | Overdue
ZAWTIKA Z1F TS | AS-BUILT | DWG | ZWP20 AS-BUILT DRAWINGS | TBA | 0% | 0% | 0% | 0% | 1.5
ZAWTIKA Z1F TS | AS-BUILT | DWG | ZWP21 AS-BUILT DRAWINGS | TBA | 0% | 0% | 0% | 0% | 1.5
ZAWTIKA Z1F TS | AS-BUILT | DWG | ZWP22 AS-BUILT DRAWINGS | TBA | 0% | 0% | 0% | 0% | 1.5
ZAWTIKA Z1F TS | AS-BUILT | DWG | ZWP23 AS-BUILT DRAWINGS | TBA | 0% | 0% | 0% | 0% | 1.5
|  |  |  | Total |  |  |  |  | 100
Formulas:
Forecast = [IFR (50%)]
Forecast = [IFA (20%)]
IFA (20%) = [IFR (50%)]+42
AFC Sub (10%) = [IFA (20%)]+42
AFC App. (20%) = [AFC Sub (10%)]+14

## Overall S-Curves DDE Only (hidden)
Zawtika 1E
Topsides Detailed Design
|  |  | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98
Overall DDE Topsides |  | Description | time axis 2024-03-01 to 2025-12-05
0 |  | Cumulative Plan (Revised) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1 |  | Cumulative Forecast | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2 |  | Cumulative Actual | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | Period Plan (Early) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | Period Forecast | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Remaining Units | Period Actual | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!

## Progress Summary DDE Normalise (hidden)
[5 empty] | -1 | -1 | -1 | -1 |  |  |  |  | 0 | 0 | 0 | 0
Cut_Off Date
2025-09-19
Topsides DDE Progress by Platform
|  |  | Descriptions | % WT | Last Week Cumulative (%) |  |  |  | This Week Period (%) |  |  |  | Cumulative up to this week (%)
[5 empty] | Plan [A] | Forecast [B] | Actual [C] | Var. [C-A] | Plan [A] | Forecast [B] | Actual [C] | Var. [C-A] | Plan [A] | Forecast [B] | Actual [C] | Var. [C-A]
#REF! | #REF! | #REF! | ZWP-16 | 5.927% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | ZWP-17 | 5.927% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
7 | 8 | 9 | ZWP-18 | 82.22% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | ZWP-19 | 5.927% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | Overall Topsides DDE Progress | 100% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Click Here to Change the cut_off

## Review Cycle (hidden)
IFR |  | IFA | AFC Sub | AFC Approv.
| 14 | 14
21 Days
21 Days
14 Days
14 Days for COMPANY review, 7 Days to Incorporate the co
mments
14 Days for COMPANY review, 7 Days to Incorporate the co
mments
14 Days for COMPANY review

## Sheet4 (hidden)
Row Labels | Sum of Weight %
ZWP-16 | 22.075
ZWP-17 | 22.075
ZWP-18 | 22.075
ZWP-19 | 22.075
Grand Total | 88.3