## MDR-Detailed Design-A10
ENGINEERING, PROCUREMENT, CONSTRUCTION, AND INSTALLATION OF WELLHEAD PLATFORMS, ASSOCIATED PIPELINES AND BROWNFIELD MODIFICATIONS FOR ZAWTIKA DEVELOPMENT PROJECT PHASE 1F
MASTER DOCUMENT REGISTER
|  | COMPANY: | PTTEPI | [29 empty] | Document No:
|  | CONTRACT NO.: | MM25-5001 | [29 empty] | Date:
|  | Project Field | ZTK | [29 empty] | Rev.: | [18 empty] | PLAN | [120 empty] | PLAN | [120 empty] | PLAN
|  | Phase Code | 1F | [36 empty] | MM-ZTK-1F-GEN-PJM-MDR-0001 | [5 empty] | 2026-10-02 |  |  |  | 2026-10-09 |  | 2026 | [46 empty] | 2027 | [52 empty] | 2028 | [20 empty] | 2026 | [46 empty] | 2027 | [52 empty] | 2028 | [20 empty] | 2026 | [46 empty] | 2027 | [52 empty] | 2028
[40 empty] | Updated on : |  | 2026-10-09 |  |  | Progress | [6 empty] | February-2026 |  |  |  | March-2026 |  |  |  | April-2026 |  |  |  | May-2026 |  |  |  |  | June-2026 |  |  |  | July-2026 |  |  |  |  | August-2026 |  |  |  | September-2026 |  |  |  | October-2026 |  |  |  |  | November-2026 |  |  |  | December-2026 |  |  |  | January-2027 |  |  |  |  | February-2027 |  |  |  | March-2027 |  |  |  | April-2027 |  |  |  |  | May-2027 |  |  |  | June-2027 |  |  |  | July-2027 |  |  |  |  | August-2027 |  |  |  | September-2027 |  |  |  | October-2027 |  |  |  |  | November-2027 |  |  |  | December-2027 |  |  |  |  | January-2028 |  |  |  | February-2028 |  |  |  | March-2028 |  |  |  |  | April-2028 |  |  |  | May-2028 |  |  |  | February-2026 |  |  |  | March-2026 |  |  |  | April-2026 |  |  |  | May-2026 |  |  |  |  | June-2026 |  |  |  | July-2026 |  |  |  |  | August-2026 |  |  |  | September-2026 |  |  |  | October-2026 |  |  |  |  | November-2026 |  |  |  | December-2026 |  |  |  | January-2027 |  |  |  |  | February-2027 |  |  |  | March-2027 |  |  |  | April-2027 |  |  |  |  | May-2027 |  |  |  | June-2027 |  |  |  | July-2027 |  |  |  |  | August-2027 |  |  |  | September-2027 |  |  |  | October-2027 |  |  |  |  | November-2027 |  |  |  | December-2027 |  |  |  |  | January-2028 |  |  |  | February-2028 |  |  |  | March-2028 |  |  |  |  | April-2028 |  |  |  | May-2028 |  |  |  | February-2026 |  |  |  | March-2026 |  |  |  | April-2026 |  |  |  | May-2026 |  |  |  |  | June-2026 |  |  |  | July-2026 |  |  |  |  | August-2026 |  |  |  | September-2026 |  |  |  | October-2026 |  |  |  |  | November-2026 |  |  |  | December-2026 |  |  |  | January-2027 |  |  |  |  | February-2027 |  |  |  | March-2027 |  |  |  | April-2027 |  |  |  |  | May-2027 |  |  |  | June-2027 |  |  |  | July-2027 |  |  |  |  | August-2027 |  |  |  | September-2027 |  |  |  | October-2027 |  |  |  |  | November-2027 |  |  |  | December-2027 |  |  |  |  | January-2028 |  |  |  | February-2028 |  |  |  | March-2028 |  |  |  |  | April-2028 |  |  |  | May-2028
[11 empty] | IDC |  |  |  | IFR | [8 empty] | IFA | [8 empty] | AFC | [6 empty] | AP |  |  | Qty | % | Cummulative Last Week |  |  | Cummulative This Week |  |  |  | 06 | 13 | 20 | 27 | 06 | 13 | 20 | 27 | 03 | 10 | 17 | 24 | 01 | 08 | 15 | 22 | 29 | 05 | 12 | 19 | 26 | 03 | 10 | 17 | 24 | 31 | 07 | 14 | 21 | 28 | 04 | 11 | 18 | 25 | 02 | 09 | 16 | 23 | 30 | 06 | 13 | 20 | 27 | 04 | 11 | 18 | 25 | 01 | 08 | 15 | 22 | 29 | 05 | 12 | 19 | 26 | 05 | 12 | 19 | 26 | 02 | 09 | 16 | 23 | 30 | 07 | 14 | 21 | 28 | 04 | 11 | 18 | 25 | 02 | 09 | 16 | 23 | 30 | 06 | 13 | 20 | 27 | 03 | 10 | 17 | 24 | 01 | 08 | 15 | 22 | 29 | 05 | 12 | 19 | 26 | 03 | 10 | 17 | 24 | 31 | 07 | 14 | 21 | 28 | 04 | 11 | 18 | 25 | 03 | 10 | 17 | 24 | 31 | 07 | 14 | 21 | 28 | 05 | 12 | 19 | 26 | 06 | 13 | 20 | 27 | 06 | 13 | 20 | 27 | 03 | 10 | 17 | 24 | 01 | 08 | 15 | 22 | 29 | 05 | 12 | 19 | 26 | 03 | 10 | 17 | 24 | 31 | 07 | 14 | 21 | 28 | 04 | 11 | 18 | 25 | 02 | 09 | 16 | 23 | 30 | 06 | 13 | 20 | 27 | 04 | 11 | 18 | 25 | 01 | 08 | 15 | 22 | 29 | 05 | 12 | 19 | 26 | 05 | 12 | 19 | 26 | 02 | 09 | 16 | 23 | 30 | 07 | 14 | 21 | 28 | 04 | 11 | 18 | 25 | 02 | 09 | 16 | 23 | 30 | 06 | 13 | 20 | 27 | 03 | 10 | 17 | 24 | 01 | 08 | 15 | 22 | 29 | 05 | 12 | 19 | 26 | 03 | 10 | 17 | 24 | 31 | 07 | 14 | 21 | 28 | 04 | 11 | 18 | 25 | 03 | 10 | 17 | 24 | 31 | 07 | 14 | 21 | 28 | 05 | 12 | 19 | 26 | 06 | 13 | 20 | 27 | 06 | 13 | 20 | 27 | 03 | 10 | 17 | 24 | 01 | 08 | 15 | 22 | 29 | 05 | 12 | 19 | 26 | 03 | 10 | 17 | 24 | 31 | 07 | 14 | 21 | 28 | 04 | 11 | 18 | 25 | 02 | 09 | 16 | 23 | 30 | 06 | 13 | 20 | 27 | 04 | 11 | 18 | 25 | 01 | 08 | 15 | 22 | 29 | 05 | 12 | 19 | 26 | 05 | 12 | 19 | 26 | 02 | 09 | 16 | 23 | 30 | 07 | 14 | 21 | 28 | 04 | 11 | 18 | 25 | 02 | 09 | 16 | 23 | 30 | 06 | 13 | 20 | 27 | 03 | 10 | 17 | 24 | 01 | 08 | 15 | 22 | 29 | 05 | 12 | 19 | 26 | 03 | 10 | 17 | 24 | 31 | 07 | 14 | 21 | 28 | 04 | 11 | 18 | 25 | 03 | 10 | 17 | 24 | 31 | 07 | 14 | 21 | 28 | 05 | 12 | 19 | 26
| No. | Area | Disc | Type | Seq.no | Format | Document No. | Document Title | Class | Remarks | REV | Issue To TJE | TJE Return Comment | CRS submission Date | REV | Issue To TJE | TJE Return Comment | Re-Issue To TJE | PLAN | ACTUAL | Forecast | PTTEPI Return Comment | CRS submission Date | REV | Issue To TJE | TJE Return Comment | Re-Issue To TJE | PLAN | ACTUAL | Forecast | PTTEPI Return Comment | CRS submission Date | REV | Issue To TJE | PLAN | ACTUAL | PTTEPI return | Forecast | Forecast | PLAN | ACTUAL | Forecast |  |  | Plan | Actual | Deviation | Plan | Actual | Deviation | [122 empty] | 2026-02-06 | 2026-02-13 | 2026-02-20 | 2026-02-27 | 2026-03-06 | 2026-03-13 | 2026-03-20 | 2026-03-27 | 2026-04-03 | 2026-04-10 | 2026-04-17 | 2026-04-24 | 2026-05-01 | 2026-05-08 | 2026-05-15 | 2026-05-22 | 2026-05-29 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-26 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | 2026-09-25 | 2026-10-02 | 2026-10-09 | 2026-10-16 | 2026-10-23 | 2026-10-30 | 2026-11-06 | 2026-11-13 | 2026-11-20 | 2026-11-27 | 2026-12-04 | 2026-12-11 | 2026-12-18 | 2026-12-25 | 2027-01-01 | 2027-01-08 | 2027-01-15 | 2027-01-22 | 2027-01-29 | 2027-02-05 | 2027-02-12 | 2027-02-19 | 2027-02-26 | 2027-03-05 | 2027-03-12 | 2027-03-19 | 2027-03-26 | 2027-04-02 | 2027-04-09 | 2027-04-16 | 2027-04-23 | 2027-04-30 | 2027-05-07 | 2027-05-14 | 2027-05-21 | 2027-05-28 | 2027-06-04 | 2027-06-11 | 2027-06-18 | 2027-06-25 | 2027-07-02 | 2027-07-09 | 2027-07-16 | 2027-07-23 | 2027-07-30 | 2027-08-06 | 2027-08-13 | 2027-08-20 | 2027-08-27 | 2027-09-03 | 2027-09-10 | 2027-09-17 | 2027-09-24 | 2027-10-01 | 2027-10-08 | 2027-10-15 | 2027-10-22 | 2027-10-29 | 2027-11-05 | 2027-11-12 | 2027-11-19 | 2027-11-26 | 2027-12-03 | 2027-12-10 | 2027-12-17 | 2027-12-24 | 2027-12-31 | 2028-01-07 | 2028-01-14 | 2028-01-21 | 2028-01-28 | 2028-02-04 | 2028-02-11 | 2028-02-18 | 2028-02-25 | 2028-03-03 | 2028-03-10 | 2028-03-17 | 2028-03-24 | 2028-03-31 | 2028-04-07 | 2028-04-14 | 2028-04-21 | 2028-04-28 | 2028-05-05 | 2028-05-12 | 2028-05-19 | 2028-05-26 | 2026-02-06 | 2026-02-13 | 2026-02-20 | 2026-02-27 | 2026-03-06 | 2026-03-13 | 2026-03-20 | 2026-03-27 | 2026-04-03 | 2026-04-10 | 2026-04-17 | 2026-04-24 | 2026-05-01 | 2026-05-08 | 2026-05-15 | 2026-05-22 | 2026-05-29 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-26 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | 2026-09-25 | 2026-10-02 | 2026-10-09 | 2026-10-16 | 2026-10-23 | 2026-10-30 | 2026-11-06 | 2026-11-13 | 2026-11-20 | 2026-11-27 | 2026-12-04 | 2026-12-11 | 2026-12-18 | 2026-12-25 | 2027-01-01 | 2027-01-08 | 2027-01-15 | 2027-01-22 | 2027-01-29 | 2027-02-05 | 2027-02-12 | 2027-02-19 | 2027-02-26 | 2027-03-05 | 2027-03-12 | 2027-03-19 | 2027-03-26 | 2027-04-02 | 2027-04-09 | 2027-04-16 | 2027-04-23 | 2027-04-30 | 2027-05-07 | 2027-05-14 | 2027-05-21 | 2027-05-28 | 2027-06-04 | 2027-06-11 | 2027-06-18 | 2027-06-25 | 2027-07-02 | 2027-07-09 | 2027-07-16 | 2027-07-23 | 2027-07-30 | 2027-08-06 | 2027-08-13 | 2027-08-20 | 2027-08-27 | 2027-09-03 | 2027-09-10 | 2027-09-17 | 2027-09-24 | 2027-10-01 | 2027-10-08 | 2027-10-15 | 2027-10-22 | 2027-10-29 | 2027-11-05 | 2027-11-12 | 2027-11-19 | 2027-11-26 | 2027-12-03 | 2027-12-10 | 2027-12-17 | 2027-12-24 | 2027-12-31 | 2028-01-07 | 2028-01-14 | 2028-01-21 | 2028-01-28 | 2028-02-04 | 2028-02-11 | 2028-02-18 | 2028-02-25 | 2028-03-03 | 2028-03-10 | 2028-03-17 | 2028-03-24 | 2028-03-31 | 2028-04-07 | 2028-04-14 | 2028-04-21 | 2028-04-28 | 2028-05-05 | 2028-05-12 | 2028-05-19 | 2028-05-26 | IFR |  | IFA |  | IFC |  | APP | time axis 2026-02-06 to 2028-05-26
1 | Engineering - Pipeline Detailed Design | [17 empty] | 50% | [8 empty] | 20% | [6 empty] | 10% |  |  |  |  | 20% |  |  | 122
2 | General
3 | Basis of Design
4 | 1 | IPX | PLR | BOD | 9001 | docx | MM-ZTK-1F-IPX-PLR-BOD-9001 | Pipeline and Riser Design Basis and Design Criteria |  |  | R1 | 2026-04-11 | 2026-04-18 | 2026-04-21 | A1 | 2026-04-23 | 2026-04-25 | 2026-04-28 | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-05-13 | 2026-05-15 | B1 | 2026-05-19 | 2026-05-22 | 2026-05-26 | 2026-05-27 | 2026-06-19 | 2026-06-19 | 2026-06-10 | 2026-06-12 | C1 | 2026-06-16 | 2026-06-17 | 2026-07-20 | 2026-07-01 |  | 2026-07-03 | 2026-07-01 |  | 2026-07-01 | 1 | 0.8197% | 0.8197% | 0.6557% | -0.1639% | 0.8197% | 0.6557% | -0.1639% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0.08197% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0.2459% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IPX-PLR-BOD-9001 | 29-Apr-2026 19:02:47 | MM-ZTK-1F-IPX-PLR-BOD-9001 | 19-Jun-2026 16:41:03 | MM-ZTK-1F-IPX-PLR-BOD-9001 | 20-Jul-2026 12:12:38 | AFC | Approved with Comment | AWC | 27-Jul-2026 08:57:39
5 | 2 | IPX | PLR | BOD | 9002 | docx | MM-ZTK-1F-IPX-PLR-BOD-9002 | Seismic Consideration for Subsea Pipeline in Seismic Hazardous Area |  |  | R1 | 2026-04-11 | 2026-04-18 | 2026-04-21 | A1 | 2026-04-23 | 2026-04-25 | 2026-04-28 | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-05-13 | 2026-05-15 | B1 | 2026-05-19 | 2026-05-22 | 2026-05-26 | 2026-05-27 | 2026-06-26 | 2026-06-26 | 2026-06-10 | 2026-06-12 | C1 | 2026-06-16 | 2026-06-17 | 2026-07-23 | 2026-07-01 |  | 2026-07-10 | 2026-07-01 | 2026-07-24 | 2026-07-01 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0% | 0.2459% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1639% | 0.1639% | 0.08197% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IPX-PLR-BOD-9002 | 29-Apr-2026 19:03:14 | MM-ZTK-1F-IPX-PLR-BOD-9002 | 29-Jun-2026 22:07:17 | MM-ZTK-1F-IPX-PLR-BOD-9002 | 23-Jul-2026 09:33:12 | AFC | Approved with Comment | AWC | 30-Jul-2026 03:44:21
6 | 3 | IPX | PRO | BOD | 9001 | docx | MM-ZTK-1F-IPX-PRO-BOD-9001 | Design Basis for Pipeline and Riser Flow Assurance Studies |  |  | R1 | 2026-05-11 | 2026-05-18 | 2026-05-21 | A1 | 2026-05-23 | 2026-05-25 | 2026-05-28 | 2026-05-29 | 2026-05-22 | 2026-05-22 | 2026-06-12 | 2026-06-14 | B1 | 2026-06-18 | 2026-06-21 | 2026-06-25 | 2026-06-26 | 2026-06-25 | 2026-06-25 | 2026-07-10 | 2026-07-12 | C1 | 2026-07-16 | 2026-07-17 | 2026-07-17 | 2026-07-31 |  | 2026-07-17 | 2026-07-31 | 2026-07-24 | 2026-07-31 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IPX-PRO-BOD-9001 | 22-May-2026 10:58:25 | MM-ZTK-1F-IPX-PRO-BOD-9001 | 25-Jun-2026 23:17:58 | MM-ZTK-1F-IPX-PRO-BOD-9001 | 16-Jul-2026 21:16:11 | AFC | Approved | APPR | 27-Jul-2026 10:30:52
7 | [43 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [122 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | bar: 2026-02-06 to 2028-05-26
8 | General Reports | [6 empty] | General Reports | [164 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | bar: 2026-02-06 to 2028-05-26
9 | 4 | IPX | PLR | RPT | 9001 | docx | MM-ZTK-1F-IPX-PLR-RPT-9001 | Pipeline Wall Thickness Analysis Report (IP20, IP21, IP22, IP23) |  |  | R1 | 2026-04-26 | 2026-05-03 | 2026-05-06 | A1 | 2026-05-08 | 2026-05-10 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-15 | 2026-05-28 | 2026-05-30 | B1 | 2026-06-03 | 2026-06-06 | 2026-06-10 | 2026-06-11 | 2026-06-26 | 2026-06-26 | 2026-06-25 | 2026-06-27 | C1 | 2026-07-01 | 2026-07-02 | 2026-07-17 | 2026-07-16 |  | 2026-07-02 | 2026-07-16 |  | 2026-07-16 | 1 | 0.8197% | 0.8197% | 0.6557% | -0.1639% | 0.8197% | 0.6557% | -0.1639% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0% | 0.1639% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IPX-PLR-RPT-9001 | 15-May-2026 10:53:22 | MM-ZTK-1F-IPX-PLR-RPT-9001 | 26-Jun-2026 18:08:54 | MM-ZTK-1F-IPX-PLR-RPT-9001 | 17-Jul-2026 13:24:13 | AFC | Approved with Comment | AWC | 27-Jul-2026 10:46:22
10 | 5 | IPX | PLR | RPT | 9002 | docx | MM-ZTK-1F-IPX-PLR-RPT-9002 | Pipeline On-Bottom Stability Analysis (IP20, IP21, IP22, IP23) |  |  | R1 | 2026-05-11 | 2026-05-18 | 2026-05-21 | A1 | 2026-05-23 | 2026-05-25 | 2026-05-28 | 2026-05-29 | 2026-05-22 | 2026-05-22 | 2026-06-12 | 2026-06-14 | B1 | 2026-06-18 | 2026-06-21 | 2026-06-25 | 2026-06-26 | 2026-06-26 | 2026-06-26 | 2026-07-10 | 2026-07-12 | C1 | 2026-07-16 | 2026-07-17 | 2026-07-24 | 2026-07-31 |  | 2026-07-17 | 2026-07-31 | 2026-08-07 | 2026-07-31 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IPX-PLR-RPT-9002 | 22-May-2026 10:58:00 | MM-ZTK-1F-IPX-PLR-RPT-9002 | 27-Jun-2026 19:26:25 | MM-ZTK-1F-IPX-PLR-RPT-9002 | 24-Jul-2026 12:07:57 | AFC | Approved | APPR | 08-Aug-2026 04:11:05
11 | 6 | IPX | PLR | RPT | 9003 | docx | MM-ZTK-1F-IPX-PLR-RPT-9003 | Pipeline Fault Crossing Analysis |  |  | R1 | 2026-05-27 | 2026-06-03 | 2026-06-06 | A1 | 2026-06-08 | 2026-06-10 | 2026-06-13 | 2026-06-14 | 2026-06-11 | 2026-06-11 | 2026-06-28 | 2026-06-30 | B1 | 2026-07-04 | 2026-07-07 | 2026-07-11 | 2026-07-12 | 2026-07-10 | 2026-07-12 | 2026-07-26 | 2026-07-28 | C1 | 2026-08-01 | 2026-08-02 | 2026-08-04 | 2026-08-16 |  | 2026-08-02 | 2026-08-16 | 2026-08-07 | 2026-08-16 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0% | 0.2459% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IPX-PLR-RPT-9003 | 11-Jun-2026 15:27:02 | MM-ZTK-1F-IPX-PLR-RPT-9003 | 10-Jul-2026 16:57:27 | MM-ZTK-1F-IPX-PLR-RPT-9003 | 04-Aug-2026 17:36:04 | AFC | Approved | APPR | 17-Aug-2026 08:56:21
12 | 7 | IPX | PLR | RPT | 9004 | docx | MM-ZTK-1F-IPX-PLR-RPT-9004 | Pipeline External Anti-Corrosion Coating and Cathodic Protection Design (IP20, IP21, IP22, IP23) |  |  | R1 | 2026-05-08 | 2026-05-15 | 2026-05-18 | A1 | 2026-05-20 | 2026-05-22 | 2026-05-25 | 2026-05-26 | 2026-06-16 | 2026-06-16 | 2026-06-09 | 2026-06-11 | B1 | 2026-06-15 | 2026-06-18 | 2026-06-22 | 2026-06-23 | 2026-07-01 | 2026-06-30 | 2026-07-07 | 2026-07-09 | C1 | 2026-07-13 | 2026-07-14 | 2026-07-20 | 2026-07-28 |  | 2026-07-14 | 2026-07-28 | 2026-07-24 | 2026-07-28 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0.1639% | 0% | 0% | 0.2459% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0.1639% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IPX-PLR-RPT-9004 | 16-Jun-2026 09:35:32 | MM-ZTK-1F-IPX-PLR-RPT-9004 | 01-Jul-2026 18:00:45 | MM-ZTK-1F-IPX-PLR-RPT-9004 | 20-Jul-2026 13:16:00 | AFC | Approved | APPR | 27-Jul-2026 09:37:17
13 | 8 | IPX | PLR | RPT | 9005 | docx | MM-ZTK-1F-IPX-PLR-RPT-9005 | Pipeline End Expansion Analysis (IP20, IP21, IP22, IP23) |  |  | R1 | 2026-05-11 | 2026-05-18 | 2026-05-21 | A1 | 2026-05-23 | 2026-05-25 | 2026-05-28 | 2026-05-29 | 2026-05-25 | 2026-05-25 | 2026-06-12 | 2026-06-14 | B1 | 2026-06-18 | 2026-06-21 | 2026-06-25 | 2026-06-26 | 2026-06-26 | 2026-06-26 | 2026-07-10 | 2026-07-12 | C1 | 2026-07-16 | 2026-07-17 | 2026-07-17 | 2026-07-31 |  | 2026-07-17 | 2026-07-31 |  | 2026-07-31 | 1 | 0.8197% | 0.8197% | 0.6557% | -0.1639% | 0.8197% | 0.6557% | -0.1639% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IPX-PLR-RPT-9005 | 25-May-2026 12:01:31 | MM-ZTK-1F-IPX-PLR-RPT-9005 | 26-Jun-2026 20:39:09 | MM-ZTK-1F-IPX-PLR-RPT-9005 | 17-Jul-2026 13:24:44 | AFC | Approved with Comment | AWC | 27-Jul-2026 10:47:39
14 | 9 | IPX | PLR | RPT | 9006 | docx | MM-ZTK-1F-IPX-PLR-RPT-9006 | Pipeline Allowable Free Span Calculation (IP20, IP21, IP22, IP23) |  |  | R1 | 2026-05-27 | 2026-06-03 | 2026-06-06 | A1 | 2026-06-08 | 2026-06-10 | 2026-06-13 | 2026-06-14 | 2026-06-11 | 2026-06-11 | 2026-06-28 | 2026-06-30 | B1 | 2026-07-04 | 2026-07-07 | 2026-07-11 | 2026-07-12 | 2026-07-21 | 2026-07-12 | 2026-07-26 | 2026-07-28 | C1 | 2026-08-01 | 2026-08-02 | 2026-08-14 | 2026-08-16 |  | 2026-08-02 | 2026-08-16 |  | 2026-08-16 | 1 | 0.8197% | 0.8197% | 0.6557% | -0.1639% | 0.8197% | 0.6557% | -0.1639% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IPX-PLR-RPT-9006 | 11-Jun-2026 15:27:29 | MM-ZTK-1F-IPX-PLR-RPT-9006 | 21-Jul-2026 12:38:02 | MM-ZTK-1F-IPX-PLR-RPT-9006 | 14-Aug-2026 17:34:10 | AFC | Approved with Comment | AWC | 24-Aug-2026 13:25:54
15 | 10 | IPX | PLR | RPT | 9007 | docx | MM-ZTK-1F-IPX-PLR-RPT-9007 | Pipeline-Soil Interaction Study (IP20, IP21, IP22, IP23) |  |  | R1 | 2026-04-10 | 2026-04-17 | 2026-04-20 | A1 | 2026-04-22 | 2026-04-24 | 2026-04-27 | 2026-04-28 | 2026-04-30 | 2026-04-30 | 2026-05-12 | 2026-05-14 | B1 | 2026-05-18 | 2026-05-21 | 2026-05-25 | 2026-05-26 | 2026-06-19 | 2026-06-19 | 2026-06-09 | 2026-06-11 | C1 | 2026-06-15 | 2026-06-16 | 2026-07-10 | 2026-06-30 |  | 2026-07-07 | 2026-06-30 | 2026-08-14 | 2026-07-17 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IPX-PLR-RPT-9007 | 30-Apr-2026 13:22:37 | MM-ZTK-1F-IPX-PLR-RPT-9007 | 19-Jun-2026 16:41:42 | MM-ZTK-1F-IPX-PLR-RPT-9007 | 10-Jul-2026 18:47:54 | AFC | Approved with Comment | AWC | 20-Jul-2026 02:23:10
16 | 11 | IPX | PLR | RPT | 9008 | docx | MM-ZTK-1F-IPX-PLR-RPT-9008 | Riser Span Analysis (IP20, IP21, IP22, IP23) |  |  | R1 | 2026-05-04 | 2026-05-11 | 2026-05-14 | A1 | 2026-05-16 | 2026-05-18 | 2026-05-21 | 2026-05-22 | 2026-05-19 | 2026-05-19 | 2026-06-05 | 2026-06-07 | B1 | 2026-06-11 | 2026-06-14 | 2026-06-18 | 2026-06-19 | 2026-06-26 | 2026-06-26 | 2026-07-03 | 2026-07-05 | C1 | 2026-07-09 | 2026-07-10 | 2026-08-17 | 2026-07-24 |  | 2026-07-10 | 2026-07-24 |  | 2026-07-24 | 1 | 0.8197% | 0.8197% | 0.6557% | -0.1639% | 0.8197% | 0.6557% | -0.1639% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.08197% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IPX-PLR-RPT-9008 | 19-May-2026 11:11:11 | MM-ZTK-1F-IPX-PLR-RPT-9008 | 26-Jun-2026 20:39:40 | MM-ZTK-1F-IPX-PLR-RPT-9008 | 17-Aug-2026 18:41:55 | AFC | Approved with Comment | AWC | 21-Aug-2026 06:16:19
17 | 12 | IPX | PLR | RPT | 9009 | docx | MM-ZTK-1F-IPX-PLR-RPT-9009 | Riser Hanger Flange Design Report (IP20, IP21, IP22, IP23) |  |  | R1 | 2026-08-06 | 2026-08-13 | 2026-08-16 | A1 | 2026-08-18 | 2026-08-20 | 2026-08-23 | 2026-08-24 | 2026-09-15 | 2026-08-24 | 2026-09-07 | 2026-09-09 | B1 | 2026-09-13 | 2026-09-16 | 2026-09-20 | 2026-09-21 |  | 2026-09-21 | 2026-10-05 | 2026-10-07 | C1 | 2026-10-11 | 2026-10-12 |  | 2026-10-26 |  | 2026-10-12 | 2026-10-26 |  | 2026-10-26 | 1 | 0.8197% | 0.5738% | 0.4098% | -0.1639% | 0.5738% | 0.4098% | -0.1639% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IPX-PLR-RPT-9009 | 15-Sep-2026 16:14:55 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
18 | 13 | IPX | PRO | RPT | 9001 | docx | MM-ZTK-1F-IPX-PRO-RPT-9001 | Pipeline Flow Assurance - Steady State Analysis (IP20, IP21, IP22, IP23) |  |  | R1 | 2026-06-18 | 2026-06-25 | 2026-06-28 | A1 | 2026-06-30 | 2026-07-02 | 2026-07-05 | 2026-07-06 | 2026-06-26 | 2026-06-26 | 2026-07-20 | 2026-07-22 | B1 | 2026-07-26 | 2026-07-29 | 2026-08-02 | 2026-08-03 | 2026-07-17 | 2026-08-03 | 2026-08-17 | 2026-08-19 | C1 | 2026-08-23 | 2026-08-24 | 2026-08-17 | 2026-09-07 |  | 2026-08-24 | 2026-09-07 | 2026-08-28 | 2026-09-07 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0.08197% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IPX-PRO-RPT-9001 | 26-Jun-2026 10:00:01 | MM-ZTK-1F-IPX-PRO-RPT-9001 | 16-Jul-2026 21:16:42 | MM-ZTK-1F-IPX-PRO-RPT-9001 | 17-Aug-2026 17:20:32 | AFC | Approved | APPR | 30-Aug-2026 10:15:52
19 | 14 | IPX | PRO | RPT | 9002 | docx | MM-ZTK-1F-IPX-PRO-RPT-9002 | Pipeline Flow Assurance -Transient Analysis (IP20, IP21, IP22, IP23) |  |  | R1 | 2026-07-23 | 2026-07-30 | 2026-08-02 | A1 | 2026-08-04 | 2026-08-06 | 2026-08-09 | 2026-08-10 | 2026-07-09 | 2026-08-10 | 2026-08-24 | 2026-08-26 | B1 | 2026-08-30 | 2026-09-02 | 2026-09-06 | 2026-09-07 | 2026-08-10 | 2026-09-07 | 2026-09-21 | 2026-09-23 | C1 | 2026-09-27 | 2026-09-28 | 2026-08-27 | 2026-10-12 |  | 2026-09-28 | 2026-10-12 | 2026-09-07 | 2026-10-12 | 1 | 0.8197% | 0.6557% | 0.8197% | 0.1639% | 0.6557% | 0.8197% | 0.1639% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IPX-PRO-RPT-9002 | 09-Jul-2026 15:37:05 | MM-ZTK-1F-IPX-PRO-RPT-9002 | 10-Aug-2026 12:59:46 | MM-ZTK-1F-IPX-PRO-RPT-9002 | 27-Aug-2026 12:04:48 | AFC | Approved | APPR | 07-Sep-2026 11:22:35
20 | [43 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [122 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | bar: 2026-02-06 to 2028-05-26
21 | General Drawings | [6 empty] | General Drawings | [164 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | bar: 2026-02-06 to 2028-05-26
22 | 15 | IPX | PLR | DWG | 9000 | dwg | MM-ZTK-1F-IPX-PLR-DWG-9000 | Pipeline Drawing Index |  |  | R1 | 2026-06-04 | 2026-06-11 | 2026-06-14 | A1 | 2026-06-16 | 2026-06-18 | 2026-06-21 | 2026-06-22 | 2026-06-26 | 2026-06-26 | 2026-07-06 | 2026-07-08 | B1 | 2026-07-12 | 2026-07-15 | 2026-07-19 | 2026-07-20 | 2026-07-17 | 2026-07-20 | 2026-08-03 | 2026-08-05 | C1 | 2026-08-09 | 2026-08-10 | 2026-08-10 | 2026-08-24 |  | 2026-08-10 | 2026-08-24 | 2026-08-10 | 2026-08-24 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0.1639% | 0% | 0% | 0% | 0.2459% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IPX-PLR-DWG-9000 | 26-Jun-2026 20:37:23 | MM-ZTK-1F-IPX-PLR-DWG-9000 | 17-Jul-2026 20:47:08 | MM-ZTK-1F-IPX-PLR-DWG-9000 | 10-Aug-2026 12:03:58 | AFC | Approved | APPR | 24-Aug-2026 13:03:56
23 | 16 | IPX | PLR | DWG | 9001 | dwg | MM-ZTK-1F-IPX-PLR-DWG-9001 | Overall Field Layout |  |  | R1 | 2026-06-01 | 2026-06-08 | 2026-06-11 | A1 | 2026-06-13 | 2026-06-15 | 2026-06-18 | 2026-06-19 | 2026-06-26 | 2026-06-26 | 2026-07-03 | 2026-07-05 | B1 | 2026-07-09 | 2026-07-12 | 2026-07-16 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-07-31 | 2026-08-02 | C1 | 2026-08-06 | 2026-08-07 | 2026-07-17 | 2026-08-21 |  | 2026-08-07 | 2026-08-21 | 2026-07-24 | 2026-08-21 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0.2459% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IPX-PLR-DWG-9001 | 26-Jun-2026 20:37:48 | #N/A | #N/A | MM-ZTK-1F-IPX-PLR-DWG-9001 | 17-Jul-2026 20:47:32 | AFC | Approved | APPR | 27-Jul-2026 10:07:08
24 | 17 | IPX | PLR | DWG | 9002 | dwg | MM-ZTK-1F-IPX-PLR-DWG-9002 | Pipeline Field Joint Coating Details Drawing |  |  | R1 | 2026-05-25 | 2026-06-01 | 2026-06-04 | A1 | 2026-06-06 | 2026-06-08 | 2026-06-11 | 2026-06-12 | 2026-05-20 | 2026-05-20 | 2026-06-26 | 2026-06-28 | B1 | 2026-07-02 | 2026-07-05 | 2026-07-09 | 2026-07-10 | 2026-06-26 | 2026-06-26 | 2026-07-24 | 2026-07-26 | C1 | 2026-07-30 | 2026-07-31 | 2026-08-10 | 2026-08-14 |  | 2026-07-31 | 2026-08-14 | 2026-08-10 | 2026-08-14 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0.2459% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IPX-PLR-DWG-9002 | 20-May-2026 12:49:07 | MM-ZTK-1F-IPX-PLR-DWG-9002 | 26-Jun-2026 20:38:14 | MM-ZTK-1F-IPX-PLR-DWG-9002 | 10-Aug-2026 12:04:29 | AFC | Approved | APPR | 24-Aug-2026 13:02:47
25 | 18 | IPX | PLR | DWG | 9003 | dwg | MM-ZTK-1F-IPX-PLR-DWG-9003 | Pipeline Body and Coating Details Drawing |  |  | R1 | 2026-05-22 | 2026-05-29 | 2026-06-01 | A1 | 2026-06-03 | 2026-06-05 | 2026-06-08 | 2026-06-09 | 2026-05-26 | 2026-05-26 | 2026-06-23 | 2026-06-25 | B1 | 2026-06-29 | 2026-07-02 | 2026-07-06 | 2026-07-07 | 2026-06-25 | 2026-06-25 | 2026-07-21 | 2026-07-23 | C1 | 2026-07-27 | 2026-07-28 | 2026-07-08 | 2026-08-11 |  | 2026-07-28 | 2026-08-11 |  | 2026-08-11 | 1 | 0.8197% | 0.8197% | 0.6557% | -0.1639% | 0.8197% | 0.6557% | -0.1639% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0.08197% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IPX-PLR-DWG-9003 | 26-May-2026 16:52:17 | MM-ZTK-1F-IPX-PLR-DWG-9003 | 25-Jun-2026 14:28:21 | MM-ZTK-1F-IPX-PLR-DWG-9003 | 08-Jul-2026 17:27:39 | AFC | Approved with Comment | AWC | 20-Jul-2026 02:46:59
26 | 19 | IPX | PLR | DWG | 9004 | dwg | MM-ZTK-1F-IPX-PLR-DWG-9004 | Pipeline Hot Induction Bend Details Drawing |  |  | R1 | 2026-05-26 | 2026-06-02 | 2026-06-05 | A1 | 2026-06-07 | 2026-06-09 | 2026-06-12 | 2026-06-13 | 2026-05-26 | 2026-05-26 | 2026-06-27 | 2026-06-29 | B1 | 2026-07-03 | 2026-07-06 | 2026-07-10 | 2026-07-11 | 2026-06-23 | 2026-06-23 | 2026-07-25 | 2026-07-27 | C1 | 2026-07-31 | 2026-08-01 | 2026-07-08 | 2026-08-15 |  | 2026-08-01 | 2026-08-15 | 2026-08-14 | 2026-08-15 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0.08197% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IPX-PLR-DWG-9004 | 26-May-2026 16:52:43 | MM-ZTK-1F-IPX-PLR-DWG-9004 | 23-Jun-2026 16:46:15 | MM-ZTK-1F-IPX-PLR-DWG-9004 | 08-Jul-2026 17:28:14 | AFC | Approved with Comment | AWC | 20-Jul-2026 02:45:43
27 | 20 | IPX | PLR | DWG | 9005 | dwg | MM-ZTK-1F-IPX-PLR-DWG-9005 | Pipeline Anode Details Drawing |  |  | R1 | 2026-05-18 | 2026-05-25 | 2026-05-28 | A1 | 2026-05-30 | 2026-06-01 | 2026-06-04 | 2026-06-05 | 2026-05-26 | 2026-05-26 | 2026-06-19 | 2026-06-21 | B1 | 2026-06-25 | 2026-06-28 | 2026-07-02 | 2026-07-03 | 2026-07-03 | 2026-07-03 | 2026-07-17 | 2026-07-19 | C1 | 2026-07-23 | 2026-07-24 | 2026-07-24 | 2026-08-07 |  | 2026-07-24 | 2026-08-07 | 2026-07-25 | 2026-08-07 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IPX-PLR-DWG-9005 | 26-May-2026 16:53:10 | MM-ZTK-1F-IPX-PLR-DWG-9005 | 03-Jul-2026 09:51:25 | MM-ZTK-1F-IPX-PLR-DWG-9005 | 24-Jul-2026 12:07:28 | AFC | Approved | APPR | 30-Jul-2026 03:39:05
28 | 21 | IPX | PLR | DWG | 9006 | dwg | MM-ZTK-1F-IPX-PLR-DWG-9006 | Riser Hanger Flange Drawing (NPS18) |  |  | R1 | 2026-07-23 | 2026-07-30 | 2026-08-02 | A1 | 2026-08-04 | 2026-08-06 | 2026-08-09 | 2026-08-10 | 2026-08-17 | 2026-08-10 | 2026-08-24 | 2026-08-26 | B1 | 2026-08-30 | 2026-09-02 | 2026-09-06 | 2026-09-07 | 2026-08-28 | 2026-09-07 | 2026-09-21 | 2026-09-23 | C1 | 2026-09-27 | 2026-09-28 | 2026-08-28 | 2026-10-12 |  | 2026-09-28 | 2026-10-12 | 2026-09-07 | 2026-10-12 | 1 | 0.8197% | 0.6557% | 0.8197% | 0.1639% | 0.6557% | 0.8197% | 0.1639% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0.2459% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IPX-PLR-DWG-9006 | 17-Aug-2026 17:18:35 | #N/A | #N/A | MM-ZTK-1F-IPX-PLR-DWG-9006 | 28-Aug-2026 18:15:26 | AFC | Approved | APPR | 07-Sep-2026 11:47:17
29 | 22 | IPX | PLR | DWG | 9007 | dwg | MM-ZTK-1F-IPX-PLR-DWG-9007 | Riser Hanger Flange Drawing (NPS10) |  |  | R1 | 2026-07-30 | 2026-08-06 | 2026-08-09 | A1 | 2026-08-11 | 2026-08-13 | 2026-08-16 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-31 | 2026-09-02 | B1 | 2026-09-06 | 2026-09-09 | 2026-09-13 | 2026-09-14 | 2026-08-28 | 2026-09-14 | 2026-09-28 | 2026-09-30 | C1 | 2026-10-04 | 2026-10-05 | 2026-08-28 | 2026-10-19 |  | 2026-10-05 | 2026-10-19 | 2026-09-07 | 2026-10-19 | 1 | 0.8197% | 0.5738% | 0.8197% | 0.2459% | 0.6557% | 0.8197% | 0.1639% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0.2459% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IPX-PLR-DWG-9007 | 17-Aug-2026 17:19:02 | #N/A | #N/A | MM-ZTK-1F-IPX-PLR-DWG-9007 | 28-Aug-2026 18:15:52 | AFC | Approved | APPR | 07-Sep-2026 11:46:11
30 | 23 | IPX | PLR | DWG | 9008 | dwg | MM-ZTK-1F-IPX-PLR-DWG-9008 | Flange Protector Details Drawing (NPS18) |  |  | R1 | 2026-08-21 | 2026-08-28 | 2026-08-31 | A1 | 2026-09-02 | 2026-09-04 | 2026-09-07 | 2026-09-08 | 2026-09-11 | 2026-09-08 | 2026-09-22 | 2026-09-24 | B1 | 2026-09-28 | 2026-10-01 | 2026-10-05 | 2026-10-06 |  | 2026-10-06 | 2026-10-20 | 2026-10-22 | C1 | 2026-10-26 | 2026-10-27 |  | 2026-11-10 |  | 2026-10-27 | 2026-11-10 |  | 2026-11-10 | 1 | 0.8197% | 0.4098% | 0.4098% | 0% | 0.5738% | 0.4098% | -0.1639% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IPX-PLR-DWG-9008 | 11-Sep-2026 21:04:56 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
31 | [43 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [122 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | bar: 2026-02-06 to 2028-05-26
32 | Material Take-Offs | [6 empty] | Material Take-Offs | [164 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | bar: 2026-02-06 to 2028-05-26
33 | 24 | IPX | PLR | MTO | 9001 | docx | MM-ZTK-1F-IPX-PLR-MTO-9001 | Material Take Off for 18" LSAW Line Pipe and Bend Mother-Pipe |  |  | R1 | 2026-05-18 | 2026-05-21 | 2026-05-24 | A1 | 2026-05-26 | 2026-05-28 | 2026-05-31 | 2026-06-01 | 2026-06-09 | 2026-06-09 | 2026-06-11 | 2026-06-13 | B1 | 2026-06-16 | 2026-06-19 | 2026-06-22 | 2026-06-23 | 2026-06-26 | 2026-06-26 | 2026-07-07 | 2026-07-09 | C1 | 2026-07-12 | 2026-07-13 | 2026-07-13 | 2026-07-27 |  | 2026-07-13 | 2026-07-27 | 2026-07-13 | 2026-07-27 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0.1639% | 0% | 0% | 0.2459% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IPX-PLR-MTO-9001 | 09-Jun-2026 17:23:16 | MM-ZTK-1F-IPX-PLR-MTO-9001 | 29-Jun-2026 22:07:48 | MM-ZTK-1F-IPX-PLR-MTO-9001 | 13-Jul-2026 13:24:22 | AFC | Approved | APPR | 20-Jul-2026 02:06:07
34 | 25 | IPX | PLR | MTO | 9002 | docx | MM-ZTK-1F-IPX-PLR-MTO-9002 | Material Take Off for 10" Seamless Line Pipe and Bend Mother-Pipe |  |  | R1 | 2026-05-19 | 2026-05-22 | 2026-05-25 | A1 | 2026-05-27 | 2026-05-29 | 2026-06-01 | 2026-06-02 | 2026-06-08 | 2026-06-08 | 2026-06-12 | 2026-06-14 | B1 | 2026-06-17 | 2026-06-20 | 2026-06-23 | 2026-06-24 | 2026-06-26 | 2026-06-26 | 2026-07-08 | 2026-07-10 | C1 | 2026-07-13 | 2026-07-14 | 2026-07-13 | 2026-07-28 |  | 2026-07-14 | 2026-07-28 |  | 2026-07-28 | 1 | 0.8197% | 0.8197% | 0.6557% | -0.1639% | 0.8197% | 0.6557% | -0.1639% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IPX-PLR-MTO-9002 | 08-Jun-2026 14:32:21 | MM-ZTK-1F-IPX-PLR-MTO-9002 | 26-Jun-2026 20:38:42 | MM-ZTK-1F-IPX-PLR-MTO-9002 | 13-Jul-2026 13:24:52 | AFC | Approved with Comment | AWC | 20-Jul-2026 02:04:51
35 | 26 | IPX | PLR | MTO | 9003 | docx | MM-ZTK-1F-IPX-PLR-MTO-9003 | Material Take Off for Concrete Weight Coating |  |  | R1 | 2026-05-29 | 2026-06-05 | 2026-06-08 | A1 | 2026-06-10 | 2026-06-12 | 2026-06-15 | 2026-06-16 | 2026-06-24 | 2026-06-24 | 2026-06-30 | 2026-07-02 | B1 | 2026-07-06 | 2026-07-09 | 2026-07-13 | 2026-07-14 | 2026-07-09 | 2026-07-14 | 2026-07-28 | 2026-07-30 | C1 | 2026-08-03 | 2026-08-04 | 2026-07-17 | 2026-08-18 |  | 2026-08-04 | 2026-08-18 | 2026-07-24 | 2026-08-18 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0.1639% | 0.08197% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IPX-PLR-MTO-9003 | 24-Jun-2026 13:20:27 | MM-ZTK-1F-IPX-PLR-MTO-9003 | 09-Jul-2026 14:58:45 | MM-ZTK-1F-IPX-PLR-MTO-9003 | 17-Jul-2026 17:58:17 | AFC | Approved | APPR | 27-Jul-2026 09:33:27
36 | 27 | IPX | PLR | MTO | 9004 | docx | MM-ZTK-1F-IPX-PLR-MTO-9004 | Material Take Off for Hot Induction Bends |  |  | R1 | 2026-05-22 | 2026-05-29 | 2026-06-01 | A1 | 2026-06-03 | 2026-06-05 | 2026-06-08 | 2026-06-09 | 2026-06-26 | 2026-06-26 | 2026-06-23 | 2026-06-25 | B1 | 2026-06-29 | 2026-07-02 | 2026-07-06 | 2026-07-07 | 2026-07-17 | 2026-07-07 | 2026-07-21 | 2026-07-23 | C1 | 2026-07-27 | 2026-07-28 | 2026-07-25 | 2026-08-11 |  | 2026-07-28 | 2026-08-11 | 2026-07-25 | 2026-08-11 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0.1639% | 0% | 0.2459% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IPX-PLR-MTO-9004 | 26-Jun-2026 16:40:57 | MM-ZTK-1F-IPX-PLR-MTO-9004 | 14-Jul-2026 12:49:47 | MM-ZTK-1F-IPX-PLR-MTO-9004 | 25-Jul-2026 09:17:43 | AFC | Approved | APPR | 30-Jul-2026 04:33:09
37 | 28 | IPX | PLR | MTO | 9005 | docx | MM-ZTK-1F-IPX-PLR-MTO-9005 | Material Take Off for Pipeline/Riser External Anti-Corrosion Coating |  |  | R1 | 2026-05-27 | 2026-06-03 | 2026-06-06 | A1 | 2026-06-08 | 2026-06-10 | 2026-06-13 | 2026-06-14 | 2026-07-01 | 2026-06-26 | 2026-06-28 | 2026-06-30 | B1 | 2026-07-04 | 2026-07-07 | 2026-07-11 | 2026-07-12 | 2026-07-17 | 2026-07-12 | 2026-07-26 | 2026-07-28 | C1 | 2026-08-01 | 2026-08-02 | 2026-08-20 | 2026-08-16 |  | 2026-08-02 | 2026-08-16 | 2026-08-20 | 2026-08-16 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0.2459% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IPX-PLR-MTO-9005 | 01-Jul-2026 18:00:09 | MM-ZTK-1F-IPX-PLR-MTO-9005 | 17-Jul-2026 17:58:46 | MM-ZTK-1F-IPX-PLR-MTO-9005 | 20-Aug-2026 14:25:40 | AFC | Approved | APPR | 24-Aug-2026 13:00:19
38 | 29 | IPX | PLR | MTO | 9006 | docx | MM-ZTK-1F-IPX-PLR-MTO-9006 | Material Take Off for Sacrificial Bracelet Anode |  |  | R1 | 2026-05-18 | 2026-05-25 | 2026-05-28 | A1 | 2026-05-30 | 2026-06-01 | 2026-06-04 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-19 | 2026-06-21 | B1 | 2026-06-25 | 2026-06-28 | 2026-07-02 | 2026-07-03 | 2026-07-03 | 2026-07-03 | 2026-07-17 | 2026-07-19 | C1 | 2026-07-23 | 2026-07-24 | 2026-07-20 | 2026-08-07 |  | 2026-07-24 | 2026-08-07 | 2026-07-24 | 2026-08-07 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.2459% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IPX-PLR-MTO-9006 | 05-Jun-2026 13:52:48 | MM-ZTK-1F-IPX-PLR-MTO-9006 | 03-Jul-2026 09:51:55 | MM-ZTK-1F-IPX-PLR-MTO-9006 | 20-Jul-2026 13:15:16 | AFC | Approved | APPR | 27-Jul-2026 09:35:58
39 | 30 | IPX | PLR | MTO | 9007 | docx | MM-ZTK-1F-IPX-PLR-MTO-9007 | Material Take Off for Flanges, Fittings, Gaskets and Fasteners |  |  | R1 | 2026-05-19 | 2026-05-26 | 2026-05-29 | A1 | 2026-05-31 | 2026-06-02 | 2026-06-05 | 2026-06-06 | 2026-06-26 | 2026-06-26 | 2026-06-20 | 2026-06-22 | B1 | 2026-06-26 | 2026-06-29 | 2026-07-03 | 2026-07-04 | 2026-07-17 | 2026-07-04 | 2026-07-18 | 2026-07-20 | C1 | 2026-07-24 | 2026-07-25 | 2026-08-21 | 2026-08-08 |  | 2026-07-25 | 2026-08-08 | 2026-08-28 | 2026-08-08 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0.08197% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IPX-PLR-MTO-9007 | 26-Jun-2026 16:41:32 | MM-ZTK-1F-IPX-PLR-MTO-9007 | 17-Jul-2026 17:59:14 | MM-ZTK-1F-IPX-PLR-MTO-9007 | 21-Aug-2026 18:46:08 | AFC | Approved | APPR | 30-Aug-2026 10:33:27
40 | 31 | IPX | PLR | MTO | 9008 | docx | MM-ZTK-1F-IPX-PLR-MTO-9008 | Material Take Off for Field Joint Coating |  |  | R1 | 2026-06-01 | 2026-06-08 | 2026-06-11 | A1 | 2026-06-13 | 2026-06-15 | 2026-06-18 | 2026-06-19 | 2026-07-03 | 2026-06-26 | 2026-07-03 | 2026-07-05 | B1 | 2026-07-09 | 2026-07-12 | 2026-07-16 | 2026-07-17 | 2026-08-28 | 2026-07-17 | 2026-07-31 | 2026-08-02 | C1 | 2026-08-06 | 2026-08-07 | 2026-10-01 | 2026-08-21 |  | 2026-08-07 | 2026-08-21 | 2026-10-02 | 2026-08-21 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0.2459% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IPX-PLR-MTO-9008 | 03-Jul-2026 13:35:31 | MM-ZTK-1F-IPX-PLR-MTO-9008 | 28-Aug-2026 14:49:35 | MM-ZTK-1F-IPX-PLR-MTO-9008 | 01-Oct-2026 12:03:45 | AFC | 0 | APPR
41 | [43 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [122 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | bar: 2026-02-06 to 2028-05-26
42 | Technical Bid Evaluations | [6 empty] | Technical Bid Evaluations | [164 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | bar: 2026-02-06 to 2028-05-26
43 | 32 | IPX | PLR | TBE | 9001 | docx | MM-ZTK-1F-IPX-PLR-TBE-9001 | Technical Bid Evaluation for 18" LSAW Line Pipe and Bend Mother-Pipe |  |  | R1 | 2026-07-14 | [6 empty] | 2026-07-24 | 2026-07-30 | 2026-07-24 | 2026-08-03 | [6 empty] | 2026-08-19 | [5 empty] | 2026-08-13 | 2026-08-19 | 2026-08-27 |  | 2026-08-13 | 2026-08-27 |  | 2026-08-27 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [122 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IPX-PLR-TBE-9001 | 30-Jul-2026 09:53:08 | #N/A | #N/A | MM-ZTK-1F-IPX-PLR-TBE-9001 | 19-Aug-2026 10:09:25 | AFC | Approved with Comment | AWC | 24-Aug-2026 12:54:18 | bar: 2026-02-06 to 2028-05-26
44 | 33 | IPX | PLR | TBE | 9002 | docx | MM-ZTK-1F-IPX-PLR-TBE-9002 | Technical Bid Evaluation for 10" Seamless Line Pipe and Bend Mother-Pipe |  |  | R1 | 2026-07-15 | [6 empty] | 2026-07-25 | 2026-07-30 | 2026-07-25 | 2026-08-04 | [6 empty] | 2026-09-15 | [5 empty] | 2026-08-14 | 2026-09-15 | 2026-08-28 |  | 2026-08-14 | 2026-08-28 |  | 2026-08-28 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [122 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IPX-PLR-TBE-9002 | 30-Jul-2026 09:53:33 | #N/A | #N/A | MM-ZTK-1F-IPX-PLR-TBE-9002 | 15-Sep-2026 16:15:29 | AFC | Approved with Comment | AWC | 20-Sep-2026 11:11:31 | bar: 2026-02-06 to 2028-05-26
45 | 34 | IPX | PLR | TBE | 9003 | docx | MM-ZTK-1F-IPX-PLR-TBE-9003 | Technical Bid Evaluation for Concrete Weight Coating |  |  | R1 | 2026-08-04 | [6 empty] | 2026-08-14 | 2026-08-03 | 2026-08-14 | 2026-08-24 | [6 empty] | 2026-09-17 | [5 empty] | 2026-09-03 | 2026-09-17 | 2026-09-17 |  | 2026-09-03 | 2026-09-17 |  | 2026-09-17 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [122 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IPX-PLR-TBE-9003 | 03-Aug-2026 16:55:18 | #N/A | #N/A | MM-ZTK-1F-IPX-PLR-TBE-9003 | 17-Sep-2026 16:09:19 | AFC | Approved with Comment | AWC | 29-Sep-2026 04:58:58 | bar: 2026-02-06 to 2028-05-26
46 | 35 | IPX | PLR | TBE | 9004 | docx | MM-ZTK-1F-IPX-PLR-TBE-9004 | Technical Bid Evaluation for Hot Induction Bends |  |  | R1 | 2026-07-15 | [6 empty] | 2026-07-25 | 2026-07-30 | 2026-07-25 | 2026-08-04 | [6 empty] | 2026-08-19 | [5 empty] | 2026-08-14 | 2026-08-19 | 2026-08-28 |  | 2026-08-14 | 2026-08-28 |  | 2026-08-28 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [122 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IPX-PLR-TBE-9004 | 30-Jul-2026 09:54:00 | #N/A | #N/A | MM-ZTK-1F-IPX-PLR-TBE-9004 | 19-Aug-2026 10:09:54 | AFC | Approved with Comment | AWC | 24-Aug-2026 12:52:57 | bar: 2026-02-06 to 2028-05-26
47 | 36 | IPX | PLR | TBE | 9005 | docx | MM-ZTK-1F-IPX-PLR-TBE-9005 | Technical Bid Evaluation for Pipeline/Riser External Anti-Corrosion Coating |  |  | R1 | 2026-08-04 | [6 empty] | 2026-08-14 | 2026-08-03 | 2026-08-14 | 2026-08-24 | [12 empty] | 2026-09-03 |  | 2026-09-17 |  | 2026-09-03 | 2026-09-17 |  | 2026-09-17 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [122 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IPX-PLR-TBE-9005 | 03-Aug-2026 15:21:25 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | bar: 2026-02-06 to 2028-05-26
48 | 37 | IPX | PLR | TBE | 9006 | docx | MM-ZTK-1F-IPX-PLR-TBE-9006 | Technical Bid Evaluation for Sacrificial Bracelet Anode |  |  | R1 | 2026-07-24 | [6 empty] | 2026-08-03 | 2026-08-28 | 2026-08-03 | 2026-08-13 | [6 empty] | 2026-09-09 | [5 empty] | 2026-08-23 | 2026-09-09 | 2026-09-06 |  | 2026-08-23 | 2026-09-06 | 2026-09-25 | 2026-09-06 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [122 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IPX-PLR-TBE-9006 | 26-Aug-2026 18:38:21 | #N/A | #N/A | MM-ZTK-1F-IPX-PLR-TBE-9006 | 09-Sep-2026 10:17:21 | AFC | Approved | APPR | 20-Sep-2026 11:35:49 | bar: 2026-02-06 to 2028-05-26
49 | 38 | IPX | PLR | TBE | 9007 | docx | MM-ZTK-1F-IPX-PLR-TBE-9007 | Technical Bid Evaluation for Flanges |  |  | R1 | 2026-08-19 | [6 empty] | 2026-08-29 | 2026-08-28 | 2026-08-29 | 2026-09-12 | [6 empty] | 2026-09-07 | [5 empty] | 2026-09-22 | 2026-09-07 | 2026-10-06 |  | 2026-09-22 | 2026-10-06 | 2026-09-11 | 2026-10-06 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [122 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IPX-PLR-TBE-9007 | 28-Aug-2026 10:33:53 | #N/A | #N/A | MM-ZTK-1F-IPX-PLR-TBE-9007 | 07-Sep-2026 18:41:02 | AFC | Approved | APPR | 11-Sep-2026 01:55:25 | bar: 2026-02-06 to 2028-05-26
50 | 39 | [5 empty] | MM-ZTK-1F-IPX-PLR-TBE-9008 | Technical Bid Evaluation for Fittings |  |  | R1 | 2026-08-19 | [6 empty] | 2026-08-29 |  | 2026-08-29 | 2026-09-12 | [12 empty] | 2026-09-22 |  | 2026-10-06 |  | 2026-09-22 | 2026-10-06 |  | 2026-10-06 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [122 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | bar: 2026-02-06 to 2028-05-26
51 | 40 | [5 empty] | MM-ZTK-1F-IPX-PLR-TBE-9009 | Technical Bid Evaluation for Gaskets |  |  | R1 | 2026-08-19 | [6 empty] | 2026-08-29 |  | 2026-08-29 | 2026-09-12 | [12 empty] | 2026-09-22 |  | 2026-10-06 |  | 2026-09-22 | 2026-10-06 |  | 2026-10-06 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [122 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | bar: 2026-02-06 to 2028-05-26
52 | 41 | [5 empty] | MM-ZTK-1F-IPX-PLR-TBE-9010 | Technical Bid Evaluation for Fasteners |  |  | R1 | 2026-08-19 | [6 empty] | 2026-08-29 |  | 2026-08-29 | 2026-09-12 | [12 empty] | 2026-09-22 |  | 2026-10-06 |  | 2026-09-22 | 2026-10-06 |  | 2026-10-06 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [122 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | bar: 2026-02-06 to 2028-05-26
53 | 42 | IPX | PLR | TBE | 9008 | docx | MM-ZTK-1F-IPX-PLR-TBE-9011 | Technical Bid Evaluation for Field Joint Coating |  |  | R1 | 2026-09-01 | [6 empty] | 2026-09-11 | 2026-08-25 | 2026-09-11 | 2026-09-25 | [6 empty] | 2026-09-18 | [5 empty] | 2026-10-05 | 2026-09-18 | 2026-10-19 |  | 2026-10-05 | 2026-10-19 | 2026-09-30 | 2026-10-19 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [122 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IPX-PLR-TBE-9011 | 25-Aug-2026 11:58:20 | #N/A | #N/A | MM-ZTK-1F-IPX-PLR-TBE-9011 | 18-Sep-2026 17:30:02 | AFC | Approved | APPR | 30-Sep-2026 06:35:16 | bar: 2026-02-06 to 2028-05-26
54 | [43 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [122 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | bar: 2026-02-06 to 2028-05-26
55 | Material Requisition Packages | [6 empty] | Material Requisition Packages | [164 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | bar: 2026-02-06 to 2028-05-26
56 | 43 | IPX | PLR | MR | 9001 | docx | MM-ZTK-1F-IPX-PLR-MR-9001 | Material Requisition For 18" LSAW Line Pipe, Bend Mother Pipe And Hot Induction Bend |  |  | R1 | 2026-06-13 | [6 empty] | 2026-06-23 | 2026-06-26 | 2026-06-26 | 2026-07-03 | [6 empty] | 2026-07-10 | [5 empty] | 2026-07-13 | 2026-07-10 | 2026-07-27 |  | 2026-07-13 | 2026-07-27 | 2026-07-17 | 2026-07-27 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [122 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IPX-PLR-MR-9001 | 26-Jun-2026 19:50:31 | #N/A | #N/A | MM-ZTK-1F-IPX-PLR-MR-9001 | 12-Jul-2026 11:45:51 | AFC | Approved | APPR | 17-Jul-2026 03:26:18 | bar: 2026-02-06 to 2028-05-26
57 | 44 | IPX | PLR | MR | 9002 | docx | MM-ZTK-1F-IPX-PLR-MR-9002 | Material Requisition For 10” SMLS Line Pipe, Bend Mother Pipe And Hot Induction Bend |  |  | R1 | 2026-06-14 | [6 empty] | 2026-06-24 | 2026-06-26 | 2026-06-26 | 2026-07-04 | [6 empty] | 2026-07-10 | [5 empty] | 2026-07-14 | 2026-07-10 | 2026-07-28 |  | 2026-07-14 | 2026-07-28 | 2026-07-17 | 2026-07-28 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [122 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IPX-PLR-MR-9002 | 26-Jun-2026 19:51:01 | #N/A | #N/A | MM-ZTK-1F-IPX-PLR-MR-9002 | 12-Jul-2026 11:46:27 | AFC | Approved | APPR | 20-Jul-2026 03:05:26 | bar: 2026-02-06 to 2028-05-26
58 | 45 | IPX | PLR | MR | 9003 | docx | MM-ZTK-1F-IPX-PLR-MR-9003 | Material Requisition For Pipeline External Anticorrosion Coating & Concrete Weight Coating & Bend Coating & Riser/Spool External Anticorrosion Coating |  |  | R1 | 2026-07-04 | [6 empty] | 2026-07-14 | 2026-07-10 | 2026-07-14 | 2026-07-24 | [6 empty] | 2026-07-24 | [5 empty] | 2026-08-03 | 2026-07-24 | 2026-08-17 |  | 2026-08-03 | 2026-08-17 | 2026-07-25 | 2026-08-17 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [122 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IPX-PLR-MR-9003 | 10-Jul-2026 18:47:26 | #N/A | #N/A | MM-ZTK-1F-IPX-PLR-MR-9003 | 24-Jul-2026 09:59:37 | AFC | Approved | APPR | 03-Aug-2026 02:18:39 | bar: 2026-02-06 to 2028-05-26
59 | 46 | [5 empty] | MM-ZTK-1F-IPX-PLR-MR-9004 | Material Requisition For Neoprene Coating For Riser Splash Zone |  |  | R1 | 2026-07-02 | [6 empty] | 2026-07-12 | 2026-07-24 | 2026-07-12 | 2026-07-22 | [6 empty] | 2026-08-07 | [5 empty] | 2026-08-01 | 2026-07-25 | 2026-08-15 |  | 2026-08-01 | 2026-08-15 | 2026-07-25 | 2026-08-15 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [122 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IPX-PLR-MR-9004 | 14-Jul-2026 18:12:24 | #N/A | #N/A | MM-ZTK-1F-IPX-PLR-MR-9004 | 25-Jul-2026 09:17:17 | AFC | Approved | APPR | 03-Aug-2026 02:16:09 | bar: 2026-02-06 to 2028-05-26
60 | 47 | IPX | PLR | MR | 9004 | docx | MM-ZTK-1F-IPX-PLR-MR-9005 | Material Requisition for Sacrificial Bracelet Anodes |  |  | R1 | 2026-06-23 | [6 empty] | 2026-07-03 | 2026-07-03 | 2026-07-03 | 2026-07-13 | [6 empty] | 2026-07-24 | [5 empty] | 2026-07-23 | 2026-07-24 | 2026-08-06 |  | 2026-07-23 | 2026-08-06 |  | 2026-08-06 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [122 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IPX-PLR-MR-9005 | 03-Jul-2026 18:24:58 | #N/A | #N/A | MM-ZTK-1F-IPX-PLR-MR-9005 | 24-Jul-2026 17:38:38 | AFC | Approved with Comment | AWC | 03-Aug-2026 02:14:54 | bar: 2026-02-06 to 2028-05-26
61 | 48 | IPX | PLR | MR | 9005 | docx | MM-ZTK-1F-IPX-PLR-MR-9006 | Material Requisition for Flanges |  |  | R1 | 2026-06-24 | [6 empty] | 2026-07-04 | 2026-07-03 | 2026-07-04 | 2026-07-18 | [6 empty] | 2026-08-07 | [5 empty] | 2026-07-28 | 2026-08-07 | 2026-08-11 |  | 2026-07-28 | 2026-08-11 | 2026-08-10 | 2026-08-11 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [122 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IPX-PLR-MR-9006 | 03-Jul-2026 18:25:24 | #N/A | #N/A | MM-ZTK-1F-IPX-PLR-MR-9006 | 07-Aug-2026 17:33:47 | AFC | Approved | APPR | 17-Aug-2026 08:59:58 | bar: 2026-02-06 to 2028-05-26
62 | 49 | IPX | PLR | MR | 9006 | docx | MM-ZTK-1F-IPX-PLR-MR-9007 | Material Requisition for Fittings |  |  | R1 | 2026-06-24 | [6 empty] | 2026-07-04 | 2026-07-03 | 2026-07-04 | 2026-07-18 | [6 empty] | 2026-08-07 | [5 empty] | 2026-07-28 | 2026-08-07 | 2026-08-11 |  | 2026-07-28 | 2026-08-11 |  | 2026-08-11 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [122 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IPX-PLR-MR-9007 | 03-Jul-2026 18:25:50 | #N/A | #N/A | MM-ZTK-1F-IPX-PLR-MR-9007 | 07-Aug-2026 17:34:25 | AFC | Approved with Comment | AWC | 24-Aug-2026 12:37:05 | bar: 2026-02-06 to 2028-05-26
63 | 50 | IPX | PLR | MR | 9007 | docx | MM-ZTK-1F-IPX-PLR-MR-9008 | Material Requisition for Gaskets |  |  | R1 | 2026-06-24 | [6 empty] | 2026-07-04 | 2026-07-03 | 2026-07-04 | 2026-07-18 | [6 empty] | 2026-08-07 | [5 empty] | 2026-07-28 | 2026-08-07 | 2026-08-11 |  | 2026-07-28 | 2026-08-11 | 2026-08-10 | 2026-08-11 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [122 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IPX-PLR-MR-9008 | 03-Jul-2026 18:26:16 | #N/A | #N/A | MM-ZTK-1F-IPX-PLR-MR-9008 | 13-Aug-2026 12:37:16 | AFC | Approved | APPR | 17-Aug-2026 08:45:09 | bar: 2026-02-06 to 2028-05-26
64 | 51 | IPX | PLR | MR | 9008 | docx | MM-ZTK-1F-IPX-PLR-MR-9009 | Material Requisition for Fasteners |  |  | R1 | 2026-06-24 | [6 empty] | 2026-07-04 | 2026-07-03 | 2026-07-04 | 2026-07-18 | [6 empty] | 2026-08-07 | [5 empty] | 2026-07-28 | 2026-08-07 | 2026-08-11 |  | 2026-07-28 | 2026-08-11 | 2026-08-10 | 2026-08-11 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [122 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IPX-PLR-MR-9009 | 03-Jul-2026 18:26:44 | #N/A | #N/A | MM-ZTK-1F-IPX-PLR-MR-9009 | 07-Aug-2026 17:35:33 | AFC | Approved | APPR | 17-Aug-2026 08:55:01 | bar: 2026-02-06 to 2028-05-26
65 | 52 | [5 empty] | MM-ZTK-1F-IPX-PLR-MR-9010 | Material Requisition for Field Joint Coating |  |  | R1 | 2026-07-07 | [6 empty] | 2026-07-17 | 2026-07-16 | 2026-07-17 | 2026-07-31 | [6 empty] | 2026-08-07 | [5 empty] | 2026-08-10 | 2026-08-03 | 2026-08-24 |  | 2026-08-10 | 2026-08-24 |  | 2026-08-24 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [122 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IPX-PLR-MR-9010 | 16-Jul-2026 18:48:03 | #N/A | #N/A | MM-ZTK-1F-IPX-PLR-MR-9010 | 03-Aug-2026 16:54:50 | AFC | Approved with Comment | AWC | 13-Aug-2026 05:40:25 | bar: 2026-02-06 to 2028-05-26
66 | [43 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [122 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | bar: 2026-02-06 to 2028-05-26
67 | Particular Specifications | [6 empty] | Particular Specifications | [164 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | bar: 2026-02-06 to 2028-05-26
68 | 53 | IPX | PLR | SPE | 9001 | docx | MM-ZTK-1F-IPX-PLR-SPE-9001 | Project Particular Specification & Datasheet for 18" LSAW Line Pipe and Bend Mother-Pipe |  |  | R1 | 2026-05-08 | 2026-05-15 | 2026-05-18 | A1 | 2026-05-20 | 2026-05-22 | 2026-05-25 | 2026-05-26 | 2026-05-25 | 2026-05-25 | 2026-06-09 | 2026-06-11 |  |  |  |  | 2026-05-26 | 2026-06-26 | 2026-06-26 |  |  | C1 | 2026-06-15 | 2026-06-16 | 2026-07-01 | 2026-06-30 |  | 2026-07-10 | 2026-06-30 | 2026-07-17 | 2026-07-20 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.5738% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IPX-PLR-SPE-9001 | 25-May-2026 12:01:59 | #N/A | #N/A | MM-ZTK-1F-IPX-PLR-SPE-9001 | 01-Jul-2026 08:43:59 | AFC | Approved | APPR | 15-Jul-2026 05:21:25
69 | 54 | IPX | PLR | SPE | 9002 | docx | MM-ZTK-1F-IPX-PLR-SPE-9002 | Project Particular Specification & Datasheet for 10" Seamless Line Pipe and Bend Mother-Pipe |  |  | R1 | 2026-05-08 | 2026-05-15 | 2026-05-18 | A1 | 2026-05-20 | 2026-05-22 | 2026-05-25 | 2026-05-26 | 2026-05-25 | 2026-05-25 | 2026-06-09 | 2026-06-11 |  |  |  |  | 2026-05-26 | 2026-06-26 | 2026-06-26 |  |  | C1 | 2026-06-15 | 2026-06-16 | 2026-06-30 | 2026-06-30 |  | 2026-07-10 | 2026-06-30 | 2026-08-14 | 2026-07-20 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.5738% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0.08197% | 0% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IPX-PLR-SPE-9002 | 25-May-2026 12:02:26 | #N/A | #N/A | MM-ZTK-1F-IPX-PLR-SPE-9002 | 30-Jun-2026 18:40:13 | AFC | Approved with Comment | AWC | 15-Jul-2026 04:56:03
70 | 55 | IPX | PLR | SPE | 9003 | docx | MM-ZTK-1F-IPX-PLR-SPE-9003 | Project Particular Specification & Datasheet for Concrete Weight Coating |  |  | R1 | 2026-05-15 | 2026-05-22 | 2026-05-25 | A1 | 2026-05-27 | 2026-05-29 | 2026-06-01 | 2026-06-02 | 2026-06-16 | 2026-06-16 | 2026-06-16 | 2026-06-18 |  |  |  |  | 2026-06-02 | 2026-06-26 | 2026-06-26 |  |  | C1 | 2026-06-22 | 2026-06-23 | 2026-07-01 | 2026-07-07 |  | 2026-07-10 | 2026-07-07 | 2026-07-17 | 2026-07-07 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.5738% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0.1639% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0.1639% | 0% | 0.2459% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IPX-PLR-SPE-9003 | 16-Jun-2026 09:36:09 | #N/A | #N/A | MM-ZTK-1F-IPX-PLR-SPE-9003 | 01-Jul-2026 18:01:19 | AFC | Approved | APPR | 15-Jul-2026 05:08:53
71 | 56 | IPX | PLR | SPE | 9004 | docx | MM-ZTK-1F-IPX-PLR-SPE-9004 | Project Particular Specification & Datasheet for Hot Induction Bends |  |  | R1 | 2026-05-22 | 2026-05-29 | 2026-06-01 | A1 | 2026-06-03 | 2026-06-05 | 2026-06-08 | 2026-06-09 | 2026-06-16 | 2026-06-16 | 2026-06-23 | 2026-06-25 |  |  |  |  | 2026-06-09 | 2026-06-26 | 2026-06-26 |  |  | C1 | 2026-06-29 | 2026-06-30 | 2026-07-01 | 2026-07-14 |  | 2026-07-10 | 2026-07-14 | 2026-08-14 | 2026-07-14 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.5738% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0.1639% | 0.08197% | 0% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0.1639% | 0% | 0.08197% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IPX-PLR-SPE-9004 | 16-Jun-2026 18:43:02 | #N/A | #N/A | MM-ZTK-1F-IPX-PLR-SPE-9004 | 01-Jul-2026 18:01:53 | AFC | Approved with Comment | AWC | 15-Jul-2026 05:10:22
72 | 57 | IPX | PLR | SPE | 9005 | docx | MM-ZTK-1F-IPX-PLR-SPE-9005 | Project Particular Specification & Datasheet for Pipeline/Riser External Anti-Corrosion Coating |  |  | R1 | 2026-05-29 | 2026-06-05 | 2026-06-08 | A1 | 2026-06-10 | 2026-06-12 | 2026-06-15 | 2026-06-16 | 2026-06-26 | 2026-06-26 | 2026-06-30 | 2026-07-02 |  |  |  |  | 2026-06-16 | 2026-06-26 | 2026-06-26 |  |  | C1 | 2026-07-06 | 2026-07-07 | 2026-07-27 | 2026-07-21 |  | 2026-07-07 | 2026-07-21 | 2026-07-27 | 2026-07-21 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.5738% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.5738% | 0% | 0% | 0% | 0% | 0.2459% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.5738% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IPX-PLR-SPE-9005 | 26-Jun-2026 09:59:28 | #N/A | #N/A | MM-ZTK-1F-IPX-PLR-SPE-9005 | 27-Jul-2026 08:50:24 | AFC | Approved | APPR | 07-Aug-2026 02:17:22
73 | 58 | IPX | PLR | SPE | 9006 | docx | MM-ZTK-1F-IPX-PLR-SPE-9006 | Project Particular Specification & Datasheet for Sacrificial Bracelet Anode |  |  | R1 | 2026-05-25 | 2026-06-01 | 2026-06-04 | A1 | 2026-06-06 | 2026-06-08 | 2026-06-11 | 2026-06-12 | 2026-06-22 | 2026-06-22 | 2026-06-26 | 2026-06-28 |  |  |  |  | 2026-06-12 | 2026-06-26 | 2026-06-26 |  |  | C1 | 2026-07-02 | 2026-07-03 | 2026-07-03 | 2026-07-17 |  | 2026-07-03 | 2026-07-17 | 2026-08-14 | 2026-07-17 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.5738% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.5738% | 0.08197% | 0% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.5738% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IPX-PLR-SPE-9006 | 22-Jun-2026 13:24:01 | #N/A | #N/A | MM-ZTK-1F-IPX-PLR-SPE-9006 | 03-Jul-2026 09:52:29 | AFC | Approved with Comment | AWC | 15-Jul-2026 05:07:32
74 | 59 | IPX | PLR | SPE | 9007 | docx | MM-ZTK-1F-IPX-PLR-SPE-9007 | Project Particular Specification & Datasheet for Flanges, Fittings, Gaskets and Fasteners |  |  | R1 | 2026-05-29 | 2026-06-05 | 2026-06-08 | A1 | 2026-06-10 | 2026-06-12 | 2026-06-15 | 2026-06-16 | 2026-06-26 | 2026-06-26 | 2026-06-30 | 2026-07-02 |  |  |  |  | 2026-06-16 | 2026-06-26 | 2026-06-26 |  |  | C1 | 2026-07-06 | 2026-07-07 | 2026-07-21 | 2026-07-21 |  | 2026-07-07 | 2026-07-21 | 2026-07-24 | 2026-07-21 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.5738% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.5738% | 0% | 0% | 0% | 0.2459% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.5738% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IPX-PLR-SPE-9007 | 26-Jun-2026 20:40:07 | #N/A | #N/A | MM-ZTK-1F-IPX-PLR-SPE-9007 | 21-Jul-2026 12:38:57 | AFC | Approved | APPR | 30-Jul-2026 03:50:52
75 | 60 | IPX | PLR | SPE | 9008 | docx | MM-ZTK-1F-IPX-PLR-SPE-9008 | Project Particular Specification & Datasheet for Field Joint Coating |  |  | R1 | 2026-06-08 | 2026-06-15 | 2026-06-18 | A1 | 2026-06-20 | 2026-06-22 | 2026-06-25 | 2026-06-26 | 2026-06-30 | 2026-06-29 | 2026-07-10 | 2026-07-12 |  |  |  |  | 2026-06-26 | 2026-07-10 | 2026-06-29 |  |  | C1 | 2026-07-16 | 2026-07-17 | 2026-07-21 | 2026-07-31 |  | 2026-07-17 | 2026-07-31 | 2026-07-24 | 2026-07-31 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.5738% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0.1639% | 0% | 0.2459% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.5738% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IPX-PLR-SPE-9008 | 30-Jun-2026 18:40:42 | #N/A | #N/A | MM-ZTK-1F-IPX-PLR-SPE-9008 | 21-Jul-2026 12:39:24 | AFC | Approved | APPR | 30-Jul-2026 03:49:36
76 | 61 | IPX | PLR | SPE | 9009 | docx | MM-ZTK-1F-IPX-PLR-SPE-9009 | Project Particular Specification & Datasheet for Pre-commissioning |  |  | R1 | 2026-07-06 | 2026-07-13 | 2026-07-16 | A1 | 2026-07-18 | 2026-07-20 | 2026-07-23 | 2026-07-24 | 2026-08-21 | 2026-06-30 | 2026-08-07 | 2026-08-09 |  |  |  |  | 2026-07-24 | 2026-07-10 | 2026-06-30 |  |  | C1 | 2026-08-13 | 2026-08-14 | 2026-09-28 | 2026-08-28 |  | 2026-08-14 | 2026-08-28 |  | 2026-08-28 | 1 | 0.8197% | 0.8197% | 0.6557% | -0.1639% | 0.8197% | 0.6557% | -0.1639% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.5738% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0% | 0.08197% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.5738% | 0% | 0% | 0% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IPX-PLR-SPE-9009 | 21-Aug-2026 10:32:03 | #N/A | #N/A | MM-ZTK-1F-IPX-PLR-SPE-9009 | 28-Sep-2026 15:21:44 | AFC | 0
77 | 62 | IPX | PLR | SPE | 9010 | docx | MM-ZTK-1F-IPX-PLR-SPE-9010 | Project Particular Specification & Datasheet for Welding of Pipeline according to API 1104 |  |  | R1 | 2026-06-22 | 2026-06-29 | 2026-07-02 | A1 | 2026-07-04 | 2026-07-06 | 2026-07-09 | 2026-07-10 | 2026-07-08 | 2026-07-10 | 2026-07-24 | 2026-07-26 |  |  |  |  | 2026-07-10 | 2026-07-10 | 2026-07-10 |  |  | C1 | 2026-07-30 | 2026-07-31 | 2026-07-31 | 2026-08-14 |  | 2026-07-31 | 2026-08-14 | 2026-08-07 | 2026-08-14 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.5738% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.5738% | 0% | 0% | 0.08197% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.5738% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IPX-PLR-SPE-9010 | 08-Jul-2026 17:28:53 | #N/A | #N/A | MM-ZTK-1F-IPX-PLR-SPE-9010 | 03-Aug-2026 11:04:53 | AFC | Approved | APPR | 17-Aug-2026 08:48:55
78 | 63 | IPX | PLR | SPE | 9011 | docx | MM-ZTK-1F-IPX-PLR-SPE-9011 | Project Particular Specification & Datasheet for Bend Anti-Corrosion Coating |  |  | R1 | 2026-06-01 | 2026-06-08 | 2026-06-11 | A1 | 2026-06-13 | 2026-06-15 | 2026-06-18 | 2026-06-19 | 2026-06-16 | 2026-06-16 | 2026-07-03 | 2026-07-05 |  |  |  |  | 2026-06-19 | 2026-06-26 | 2026-06-26 |  |  | C1 | 2026-07-09 | 2026-07-10 | 2026-07-01 | 2026-07-24 |  | 2026-07-10 | 2026-07-24 | 2026-08-14 | 2026-07-24 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.5738% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0.1639% | 0.08197% | 0% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0.1639% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IPX-PLR-SPE-9011 | 16-Jun-2026 09:36:41 | #N/A | #N/A | MM-ZTK-1F-IPX-PLR-SPE-9011 | 01-Jul-2026 16:41:50 | AFC | Approved with Comment | AWC | 15-Jul-2026 05:20:15
79 | [43 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [122 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | bar: 2026-02-06 to 2028-05-26
80 | IP20 Pipeline Design from ZWP20 to ZWP16 |  |  | IP20 | ZWP20 | ZWP16 |  | IP20 Pipeline Design from ZWP20 to ZWP16 | [164 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | bar: 2026-02-06 to 2028-05-26
81 | Reports: IP20 Pipeline | [6 empty] | Reports: IP20 Pipeline | [164 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | bar: 2026-02-06 to 2028-05-26
82 | 64 | IP20 | PLR | RPT | 9001 | docx | MM-ZTK-1F-IP20-PLR-RPT-9001 | IP20 Pipeline Routing Study and Design |  |  | R1 | 2026-04-05 | 2026-04-12 | 2026-04-15 | A1 | 2026-04-17 | 2026-04-19 | 2026-04-22 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-05-07 | 2026-05-09 | B1 | 2026-05-13 | 2026-05-16 | 2026-05-20 | 2026-05-21 | 2026-06-25 | 2026-06-25 | 2026-06-04 | 2026-06-06 | C1 | 2026-06-10 | 2026-06-11 | 2026-07-16 | 2026-06-25 |  | 2026-07-09 | 2026-06-25 | 2026-07-17 | 2026-07-19 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.2459% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP20-PLR-RPT-9001 | 23-Apr-2026 15:02:49 | MM-ZTK-1F-IP20-PLR-RPT-9001 | 25-Jun-2026 14:26:38 | MM-ZTK-1F-IP20-PLR-RPT-9001 | 16-Jul-2026 21:15:07 | AFC | Approved | APPR | 20-Jul-2026 02:54:02
83 | 65 | IP20 | PLR | RPT | 9002 | docx | MM-ZTK-1F-IP20-PLR-RPT-9002 | IP20 Pipeline On-Bottom Roughness and In-place Stress Analysis |  |  | R1 | 2026-06-05 | 2026-06-12 | 2026-06-15 | A1 | 2026-06-17 | 2026-06-19 | 2026-06-22 | 2026-06-23 | 2026-06-26 | 2026-06-26 | 2026-07-07 | 2026-07-09 | B1 | 2026-07-13 | 2026-07-16 | 2026-07-20 | 2026-07-21 | 2026-08-06 | 2026-07-21 | 2026-08-04 | 2026-08-06 | C1 | 2026-08-10 | 2026-08-11 | 2026-08-29 | 2026-08-25 |  | 2026-08-11 | 2026-08-25 | 2026-09-30 | 2026-08-25 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0% | 0.08197% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP20-PLR-RPT-9002 | 26-Jun-2026 16:40:25 | MM-ZTK-1F-IP20-PLR-RPT-9002 | 06-Aug-2026 12:10:16 | MM-ZTK-1F-IP20-PLR-RPT-9002 | 29-Aug-2026 14:06:46 | AFC | Approved (Proceed to Rev.C) | APPR-C | 07-Sep-2026 06:31:31
84 | 66 | IP20 | PLR | RPT | 9003 | docx | MM-ZTK-1F-IP20-PLR-RPT-9003 | IP20 Pipeline Lateral Buclking Analysis |  |  | R1 | 2026-07-02 | 2026-07-09 | 2026-07-12 | A1 | 2026-07-14 | 2026-07-16 | 2026-07-19 | 2026-07-20 | 2026-07-10 | 2026-07-20 | 2026-08-03 | 2026-08-05 | B1 | 2026-08-09 | 2026-08-12 | 2026-08-16 | 2026-08-17 | 2026-08-14 | 2026-08-17 | 2026-08-31 | 2026-09-02 | C1 | 2026-09-06 | 2026-09-07 | 2026-08-02 | 2026-09-21 |  | 2026-09-07 | 2026-09-21 | 2026-09-07 | 2026-09-21 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.08197% | 0.1639% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP20-PLR-RPT-9003 | 12-Jul-2026 11:42:19 | MM-ZTK-1F-IP20-PLR-RPT-9003 | 17-Aug-2026 14:43:56 | MM-ZTK-1F-IP20-PLR-RPT-9003 | 02-Sep-2026 18:24:13 | AFC | Approved | APPR | 07-Sep-2026 06:32:43
85 | 67 | IP20 | PLR | RPT | 9004 | docx | MM-ZTK-1F-IP20-PLR-RPT-9004 | IP20 Pipeline Walking Analysis |  |  | R1 | 2026-08-06 | 2026-08-13 | 2026-08-16 | A1 | 2026-08-18 | 2026-08-20 | 2026-08-23 | 2026-08-24 | 2026-08-17 | 2026-08-24 | 2026-09-07 | 2026-09-09 | B1 | 2026-09-13 | 2026-09-16 | 2026-09-20 | 2026-09-21 | 2026-09-08 | 2026-09-21 | 2026-10-05 | 2026-10-07 | C1 | 2026-10-11 | 2026-10-12 | 2026-09-18 | 2026-10-26 |  | 2026-10-12 | 2026-10-26 | 2026-09-25 | 2026-10-26 | 1 | 0.8197% | 0.5738% | 0.8197% | 0.2459% | 0.5738% | 0.8197% | 0.2459% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0.1639% | 0.08197% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP20-PLR-RPT-9004 | 17-Aug-2026 18:03:50 | MM-ZTK-1F-IP20-PLR-RPT-9004 | 08-Sep-2026 18:34:15 | MM-ZTK-1F-IP20-PLR-RPT-9004 | 18-Sep-2026 17:28:29 | AFC | Approved | APPR | 26-Sep-2026 07:58:34
86 | [43 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [122 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | bar: 2026-02-06 to 2028-05-26
87 | Reports: IP20 Risers and Tie-In Spools | [6 empty] | Reports: IP20 Risers and Tie-In Spools | [164 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | bar: 2026-02-06 to 2028-05-26
88 | 68 | IP20 | PLR | RPT | 9005 | docx | MM-ZTK-1F-IP20-PLR-RPT-9005 | IP20 at ZWP20 : Riser and Tie-In Spool Stress Analysis |  |  | R1 | 2026-05-25 | 2026-06-01 | 2026-06-04 | A1 | 2026-06-06 | 2026-06-08 | 2026-06-11 | 2026-06-12 | 2026-07-31 | 2026-07-24 | 2026-06-26 | 2026-06-28 | B1 | 2026-07-02 | 2026-07-05 | 2026-07-09 | 2026-07-10 | 2026-08-28 | 2026-07-10 | 2026-07-24 | 2026-07-26 | C1 | 2026-07-30 | 2026-07-31 | 2026-09-22 | 2026-08-14 |  | 2026-07-31 | 2026-08-14 | 2026-09-25 | 2026-08-14 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0% | 0.2459% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0.4098% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP20-PLR-RPT-9005 | 03-Aug-2026 11:01:38 | MM-ZTK-1F-IP20-PLR-RPT-9005 | 28-Aug-2026 18:11:49 | MM-ZTK-1F-IP20-PLR-RPT-9005 | 22-Sep-2026 11:58:40 | AFC | Approved | APPR | 26-Sep-2026 08:07:00
89 | 69 | IP20 | PLR | RPT | 9006 | docx | MM-ZTK-1F-IP20-PLR-RPT-9006 | IP20 at ZWP16 : Riser and Tie-In Spool Stress Analysis |  |  | R1 | 2026-06-01 | 2026-06-08 | 2026-06-11 | A1 | 2026-06-13 | 2026-06-15 | 2026-06-18 | 2026-06-19 | 2026-07-10 | 2026-07-02 | 2026-07-03 | 2026-07-05 | B1 | 2026-07-09 | 2026-07-12 | 2026-07-16 | 2026-07-17 | 2026-08-21 | 2026-07-17 | 2026-07-31 | 2026-08-02 | C1 | 2026-08-06 | 2026-08-07 | 2026-09-22 | 2026-08-21 |  | 2026-08-07 | 2026-08-21 |  | 2026-08-21 | 1 | 0.8197% | 0.8197% | 0.6557% | -0.1639% | 0.8197% | 0.6557% | -0.1639% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0.08197% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP20-PLR-RPT-9006 | 12-Jul-2026 11:42:46 | MM-ZTK-1F-IP20-PLR-RPT-9006 | 21-Aug-2026 09:42:52 | MM-ZTK-1F-IP20-PLR-RPT-9006 | 22-Sep-2026 11:59:12 | AFC | Approved with Comment | AWC | 26-Sep-2026 08:09:23
90 | 70 | IP20 | PLR | RPT | 9007 | docx | MM-ZTK-1F-IP20-PLR-RPT-9007 | IP20 at ZWP20 : Riser and Tie-In Spool Seismic Analysis |  |  | R1 | 2026-09-09 | 2026-09-16 | 2026-09-19 | A1 | 2026-09-21 | 2026-09-23 | 2026-09-26 | 2026-09-27 | 2026-09-04 | 2026-09-27 | 2026-10-11 | 2026-10-13 | B1 | 2026-10-17 | 2026-10-20 | 2026-10-24 | 2026-10-25 |  | 2026-10-25 | 2026-11-08 | 2026-11-10 | C1 | 2026-11-14 | 2026-11-15 |  | 2026-11-29 |  | 2026-11-15 | 2026-11-29 |  | 2026-11-29 | 1 | 0.8197% | 0.4098% | 0.4098% | 0% | 0.4098% | 0.4098% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP20-PLR-RPT-9007 | 04-Sep-2026 16:18:11 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
91 | 71 | IP20 | PLR | RPT | 9008 | docx | MM-ZTK-1F-IP20-PLR-RPT-9008 | IP20 at ZWP16 : Riser and Tie-In Spool Seismic Analysis |  |  | R1 | 2026-09-17 | 2026-09-24 | 2026-09-27 | A1 | 2026-09-29 | 2026-10-01 | 2026-10-04 | 2026-10-05 | 2026-09-04 | 2026-10-05 | 2026-10-19 | 2026-10-21 | B1 | 2026-10-25 | 2026-10-28 | 2026-11-01 | 2026-11-02 |  | 2026-11-02 | 2026-11-16 | 2026-11-18 | C1 | 2026-11-22 | 2026-11-23 |  | 2026-12-07 |  | 2026-11-23 | 2026-12-07 |  | 2026-12-07 | 1 | 0.8197% | 0% | 0.4098% | 0.4098% | 0.4098% | 0.4098% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP20-PLR-RPT-9008 | 04-Sep-2026 16:18:43 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
91 | 72 | 0 | PLR | RPT | 9008 | docx | MM-ZTK-1F-IP20-PLR-RPT-9009 | IP20 Pipeline On-Bottom Stability and Stress Analysis (Seismic) |  |  | R1 | 2026-07-03 | 2026-07-10 | 2026-07-13 | A1 | 2026-07-15 | 2026-07-17 | 2026-07-20 | 2026-07-21 | 2026-04-23 | 2026-04-23 | 2026-08-04 | 2026-08-06 | B1 | 2026-08-10 | 2026-08-13 | 2026-08-17 | 2026-08-18 | 2026-06-08 | 2026-06-08 | 2026-09-01 | 2026-09-03 | C1 | 2026-09-07 | 2026-09-08 | 2026-08-28 | 2026-09-22 |  | 2026-09-08 | 2026-09-22 | 2026-09-07 | 2026-09-22 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP20-PLR-RPT-9009 | 16-Jul-2026 21:15:37 | MM-ZTK-1F-IP20-PLR-RPT-9009 | 21-Aug-2026 13:58:51 | MM-ZTK-1F-IP20-PLR-RPT-9009 | 28-Aug-2026 16:51:56 | AFC | Approved | APPR | 07-Sep-2026 05:30:46
92 | [43 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [122 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | bar: 2026-02-06 to 2028-05-26
93 | Drawings: IP20 Pipeline | [6 empty] | Drawings: IP20 Pipeline | [164 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | bar: 2026-02-06 to 2028-05-26
94 | 73 | IP20 | PLR | DWG | 9001 | dwg | MM-ZTK-1F-IP20-PLR-DWG-9001 | IP20 Pipeline Route Drawing from ZWP20 to ZWP16 |  |  | R1 | 2026-04-05 | 2026-04-12 | 2026-04-15 | A1 | 2026-04-17 | 2026-04-19 | 2026-04-22 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-05-07 | 2026-05-09 | B1 | 2026-05-13 | 2026-05-16 | 2026-05-20 | 2026-05-21 | 2026-06-08 | 2026-06-08 | 2026-06-04 | 2026-06-06 | C1 | 2026-06-10 | 2026-06-11 | 2026-07-07 | 2026-06-25 |  | 2026-06-29 | 2026-06-25 | 2026-07-07 | 2026-07-09 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0% | 0.2459% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP20-PLR-DWG-9001 | 23-Apr-2026 17:37:44 | MM-ZTK-1F-IP20-PLR-DWG-9001 | 08-Jun-2026 18:38:08 | MM-ZTK-1F-IP20-PLR-DWG-9001 | 07-Jul-2026 18:44:37 | AFC | Approved | APPR | 20-Jul-2026 02:55:12
95 | 74 | IP20 | PLR | DWG | 9002 | dwg | MM-ZTK-1F-IP20-PLR-DWG-9002 | IP20 Pipeline Alignment Sheets: ZWP20 to ZWP16 |  |  | R1 | 2026-07-09 | 2026-07-16 | 2026-07-19 | A1 | 2026-07-21 | 2026-07-23 | 2026-07-26 | 2026-07-27 | 2026-08-14 | 2026-07-27 | 2026-08-10 | 2026-08-12 | B1 | 2026-08-16 | 2026-08-19 | 2026-08-23 | 2026-08-24 | 2026-08-31 | 2026-08-24 | 2026-09-07 | 2026-09-09 | C1 | 2026-09-13 | 2026-09-14 | 2026-09-14 | 2026-09-28 |  | 2026-09-14 | 2026-09-28 | 2026-09-25 | 2026-09-28 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0.1639% | 0% | 0.08197% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP20-PLR-DWG-9002 | 17-Aug-2026 14:42:01 | MM-ZTK-1F-IP20-PLR-DWG-9002 | 31-Aug-2026 14:01:43 | MM-ZTK-1F-IP20-PLR-DWG-9002 | 14-Sep-2026 20:09:27 | AFC | Approved | APPR | 20-Sep-2026 11:12:40
96 | 75 | IP20 | PLR | DWG | 9003 | dwg | MM-ZTK-1F-IP20-PLR-DWG-9003 | IP20 Pipeline Schematic Diagram |  |  | R1 | 2026-07-15 | 2026-07-22 | 2026-07-25 | A1 | 2026-07-27 | 2026-07-29 | 2026-08-01 | 2026-08-02 | 2026-08-24 | 2026-08-02 | 2026-08-16 | 2026-08-18 | B1 | 2026-08-22 | 2026-08-25 | 2026-08-29 | 2026-08-30 | 2026-09-11 | 2026-08-30 | 2026-09-13 | 2026-09-15 | C1 | 2026-09-19 | 2026-09-20 | 2026-09-25 | 2026-10-04 |  | 2026-09-20 | 2026-10-04 | 2026-09-29 | 2026-10-04 | 1 | 0.8197% | 0.6557% | 0.8197% | 0.1639% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0.1639% | 0% | 0.08197% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP20-PLR-DWG-9003 | 24-Aug-2026 11:04:20 | MM-ZTK-1F-IP20-PLR-DWG-9003 | 11-Sep-2026 20:59:24 | MM-ZTK-1F-IP20-PLR-DWG-9003 | 25-Sep-2026 16:15:19 | AFC | Approved | APPR | 29-Sep-2026 08:32:26
97 | 76 | IP20 | PLR | DWG | 9004 | dwg | MM-ZTK-1F-IP20-PLR-DWG-9004 | IP20 Pipeline Platform Approach at ZWP20 |  |  | R1 | 2026-05-15 | 2026-05-22 | 2026-05-25 | A1 | 2026-05-27 | 2026-05-29 | 2026-06-01 | 2026-06-02 | 2026-05-21 | 2026-05-21 | 2026-06-16 | 2026-06-18 | B1 | 2026-06-22 | 2026-06-25 | 2026-06-29 | 2026-06-30 | 2026-06-26 | 2026-06-26 | 2026-07-14 | 2026-07-16 | C1 | 2026-07-20 | 2026-07-21 | 2026-07-10 | 2026-08-04 |  | 2026-07-21 | 2026-08-04 | 2026-07-10 | 2026-08-04 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0.2459% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP20-PLR-DWG-9004 | 21-May-2026 09:40:12 | MM-ZTK-1F-IP20-PLR-DWG-9004 | 26-Jun-2026 20:34:21 | MM-ZTK-1F-IP20-PLR-DWG-9004 | 10-Jul-2026 12:59:32 | AFC | Approved | APPR | 12-Jul-2026 05:42:42
98 | 77 | IP20 | PLR | DWG | 9005 | dwg | MM-ZTK-1F-IP20-PLR-DWG-9005 | IP20 Pipeline Platform Approach at ZWP16 |  |  | R1 | 2026-05-21 | 2026-05-28 | 2026-05-31 | A1 | 2026-06-02 | 2026-06-04 | 2026-06-07 | 2026-06-08 | 2026-05-21 | 2026-05-21 | 2026-06-22 | 2026-06-24 | B1 | 2026-06-28 | 2026-07-01 | 2026-07-05 | 2026-07-06 | 2026-06-26 | 2026-06-26 | 2026-07-20 | 2026-07-22 | C1 | 2026-07-26 | 2026-07-27 | 2026-07-10 | 2026-08-10 |  | 2026-07-27 | 2026-08-10 | 2026-08-14 | 2026-08-10 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0.08197% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP20-PLR-DWG-9005 | 21-May-2026 09:40:52 | MM-ZTK-1F-IP20-PLR-DWG-9005 | 26-Jun-2026 20:34:45 | MM-ZTK-1F-IP20-PLR-DWG-9005 | 10-Jul-2026 13:00:01 | AFC | Approved with Comment | AWC | 12-Jul-2026 05:43:57
99 | [43 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [122 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | bar: 2026-02-06 to 2028-05-26
100 | GA: IP20 Risers and Tie-in Spools | [6 empty] | GA: IP20 Risers and Tie-in Spools | [164 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | bar: 2026-02-06 to 2028-05-26
101 | 78 | IP20 | PLR | GA | 9001 | dwg | MM-ZTK-1F-IP20-PLR-GA-9001 | Riser GA Drawings at ZWP20 |  |  | R1 | 2026-05-19 | 2026-05-26 | 2026-05-29 | A1 | 2026-05-31 | 2026-06-02 | 2026-06-05 | 2026-06-06 | 2026-05-20 | 2026-05-20 | 2026-06-20 | 2026-06-22 | B1 | 2026-06-26 | 2026-06-29 | 2026-07-03 | 2026-07-04 | 2026-07-07 | 2026-07-04 | 2026-07-18 | 2026-07-20 | C1 | 2026-07-24 | 2026-07-25 | 2026-07-31 | 2026-08-08 |  | 2026-07-25 | 2026-08-08 | 2026-08-07 | 2026-08-08 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP20-PLR-GA-9001 | 20-May-2026 12:48:09 | MM-ZTK-1F-IP20-PLR-GA-9001 | 07-Jul-2026 21:21:12 | MM-ZTK-1F-IP20-PLR-GA-9001 | 03-Aug-2026 11:01:12 | AFC | Approved | APPR | 10-Aug-2026 10:58:08
102 | 79 | IP20 | PLR | GA | 9002 | dwg | MM-ZTK-1F-IP20-PLR-GA-9002 | IP20 Tie-in Spool GA Drawing at ZWP20 |  |  | R1 | 2026-06-29 | 2026-07-06 | 2026-07-09 | A1 | 2026-07-11 | 2026-07-13 | 2026-07-16 | 2026-07-17 | 2026-07-24 | 2026-07-17 | 2026-07-31 | 2026-08-02 | B1 | 2026-08-06 | 2026-08-09 | 2026-08-13 | 2026-08-14 | 2026-08-20 | 2026-08-14 | 2026-08-28 | 2026-08-30 | C1 | 2026-09-03 | 2026-09-04 | 2026-08-29 | 2026-09-18 |  | 2026-09-04 | 2026-09-18 | 2026-09-07 | 2026-09-18 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0.08197% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP20-PLR-GA-9002 | 24-Jul-2026 17:07:15 | MM-ZTK-1F-IP20-PLR-GA-9002 | 20-Aug-2026 09:35:12 | MM-ZTK-1F-IP20-PLR-GA-9002 | 29-Aug-2026 14:05:48 | AFC | Approved | APPR | 07-Sep-2026 06:28:48
103 | 80 | IP20 | PLR | GA | 9003 | dwg | MM-ZTK-1F-IP20-PLR-GA-9003 | IP20 Tie-in Spool GA Drawing at ZWP16 |  |  | R1 | 2026-07-06 | 2026-07-13 | 2026-07-16 | A1 | 2026-07-18 | 2026-07-20 | 2026-07-23 | 2026-07-24 | 2026-07-24 | 2026-07-24 | 2026-08-07 | 2026-08-09 | B1 | 2026-08-13 | 2026-08-16 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | 2026-09-04 | 2026-09-06 | C1 | 2026-09-10 | 2026-09-11 | 2026-08-29 | 2026-09-25 |  | 2026-09-11 | 2026-09-25 | 2026-09-07 | 2026-09-25 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0.08197% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP20-PLR-GA-9003 | 24-Jul-2026 17:07:39 | MM-ZTK-1F-IP20-PLR-GA-9003 | 20-Aug-2026 09:36:16 | MM-ZTK-1F-IP20-PLR-GA-9003 | 29-Aug-2026 14:06:15 | AFC | Approved | APPR | 07-Sep-2026 06:30:03
104 | [43 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [122 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | bar: 2026-02-06 to 2028-05-26
105 | Isometric: IP20 Risers and Tie-in Spools | [6 empty] | Isometric: IP20 Risers and Tie-in Spools | [164 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | bar: 2026-02-06 to 2028-05-26
106 | 81 | IP20 | PLR | ISO | 9001 | dwg | MM-ZTK-1F-IP20-PLR-ISO-9001 | IP20 Riser Isometric at ZWP20 |  |  | R1 | 2026-05-16 | 2026-05-23 | 2026-05-26 | A1 | 2026-05-28 | 2026-05-30 | 2026-06-02 | 2026-06-03 | 2026-05-20 | 2026-05-20 | 2026-06-17 | 2026-06-19 | B1 | 2026-06-23 | 2026-06-26 | 2026-06-30 | 2026-07-01 | 2026-06-26 | 2026-06-26 | 2026-07-15 | 2026-07-17 | C1 | 2026-07-21 | 2026-07-22 | 2026-07-28 | 2026-08-05 |  | 2026-07-22 | 2026-08-05 | 2026-07-28 | 2026-08-05 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0.2459% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP20-PLR-ISO-9001 | 20-May-2026 11:32:45 | MM-ZTK-1F-IP20-PLR-ISO-9001 | 07-Jul-2026 21:22:06 | MM-ZTK-1F-IP20-PLR-ISO-9001 | 28-Jul-2026 09:14:32 | AFC | Approved | APPR | 13-Aug-2026 05:26:15
107 | 82 | IP20 | PLR | ISO | 9002 | dwg | MM-ZTK-1F-IP20-PLR-ISO-9002 | IP20 Tie-in Spool Isometric at ZWP20 |  |  | R1 | 2026-06-22 | 2026-06-29 | 2026-07-02 | A1 | 2026-07-04 | 2026-07-06 | 2026-07-09 | 2026-07-10 | 2026-07-03 | 2026-07-10 | 2026-07-24 | 2026-07-26 | B1 | 2026-07-30 | 2026-08-02 | 2026-08-06 | 2026-08-07 | 2026-08-14 | 2026-08-07 | 2026-08-21 | 2026-08-23 | C1 | 2026-08-27 | 2026-08-28 | 2026-08-28 | 2026-09-11 |  | 2026-08-28 | 2026-09-11 | 2026-09-07 | 2026-09-11 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP20-PLR-ISO-9002 | 03-Jul-2026 13:25:15 | MM-ZTK-1F-IP20-PLR-ISO-9002 | 17-Aug-2026 14:42:33 | MM-ZTK-1F-IP20-PLR-ISO-9002 | 28-Aug-2026 18:10:51 | AFC | Approved | APPR | 07-Sep-2026 06:24:55
108 | 83 | IP20 | PLR | ISO | 9003 | dwg | MM-ZTK-1F-IP20-PLR-ISO-9003 | IP20 Tie-in Spool Isometric at ZWP16 |  |  | R1 | 2026-06-29 | 2026-07-06 | 2026-07-09 | A1 | 2026-07-11 | 2026-07-13 | 2026-07-16 | 2026-07-17 | 2026-07-03 | 2026-07-17 | 2026-07-31 | 2026-08-02 | B1 | 2026-08-06 | 2026-08-09 | 2026-08-13 | 2026-08-14 | 2026-08-14 | 2026-08-14 | 2026-08-28 | 2026-08-30 | C1 | 2026-09-03 | 2026-09-04 | 2026-08-28 | 2026-09-18 |  | 2026-09-04 | 2026-09-18 |  | 2026-09-18 | 1 | 0.8197% | 0.8197% | 0.6557% | -0.1639% | 0.8197% | 0.6557% | -0.1639% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0.08197% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP20-PLR-ISO-9003 | 03-Jul-2026 13:26:45 | MM-ZTK-1F-IP20-PLR-ISO-9003 | 17-Aug-2026 14:43:12 | MM-ZTK-1F-IP20-PLR-ISO-9003 | 28-Aug-2026 18:11:18 | AFC | Approved with Comment | AWC | 07-Sep-2026 06:26:17
109 | [43 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [122 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | bar: 2026-02-06 to 2028-05-26
110 | IP21 Pipeline Design from ZWP21 to PLEM14 |  |  | IP21 | ZWP21 | PLEM14 |  | IP21 Pipeline Design from ZWP21 to PLEM14 | [164 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | bar: 2026-02-06 to 2028-05-26
111 | Reports: IP21 Pipeline | [6 empty] | Reports: IP21 Pipeline | [164 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | bar: 2026-02-06 to 2028-05-26
112 | 84 | IP21 | PLR | RPT | 9001 | docx | MM-ZTK-1F-IP21-PLR-RPT-9001 | IP21 Pipeline Routing Study and Design |  |  | R1 | 2026-04-09 | 2026-04-16 | 2026-04-19 | A1 | 2026-04-21 | 2026-04-23 | 2026-04-26 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-05-11 | 2026-05-13 | B1 | 2026-05-17 | 2026-05-20 | 2026-05-24 | 2026-05-25 | 2026-06-25 | 2026-06-25 | 2026-06-08 | 2026-06-10 | C1 | 2026-06-14 | 2026-06-15 | 2026-07-21 | 2026-06-29 |  | 2026-07-13 | 2026-06-29 | 2026-07-24 | 2026-07-23 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0% | 0.2459% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP21-PLR-RPT-9001 | 27-Apr-2026 10:33:03 | MM-ZTK-1F-IP21-PLR-RPT-9001 | 25-Jun-2026 14:27:25 | MM-ZTK-1F-IP21-PLR-RPT-9001 | 21-Jul-2026 12:37:33 | AFC | Approved | APPR | 30-Jul-2026 03:53:16
113 | 85 | IP21 | PLR | RPT | 9002 | docx | MM-ZTK-1F-IP21-PLR-RPT-9002 | IP21 Pipeline On-Bottom Roughness and In-place Stress Analysis |  |  | R1 | 2026-06-12 | 2026-06-19 | 2026-06-22 | A1 | 2026-06-24 | 2026-06-26 | 2026-06-29 | 2026-06-30 | 2026-08-06 | 2026-06-30 | 2026-07-14 | 2026-07-16 | B1 | 2026-07-20 | 2026-07-23 | 2026-07-27 | 2026-07-28 | 2026-08-27 | 2026-07-28 | 2026-08-11 | 2026-08-13 | C1 | 2026-08-17 | 2026-08-18 | 2026-09-11 | 2026-09-01 |  | 2026-08-18 | 2026-09-01 | 2026-09-25 | 2026-09-01 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0.1639% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP21-PLR-RPT-9002 | 06-Aug-2026 12:10:46 | MM-ZTK-1F-IP21-PLR-RPT-9002 | 27-Aug-2026 12:03:14 | MM-ZTK-1F-IP21-PLR-RPT-9002 | 11-Sep-2026 21:02:48 | AFC | Approved | APPR | 20-Sep-2026 11:44:21
114 | 86 | IP21 | PLR | RPT | 9003 | docx | MM-ZTK-1F-IP21-PLR-RPT-9003 | IP21 Pipeline Lateral Buclking Analysis |  |  | R1 | 2026-07-16 | 2026-07-23 | 2026-07-26 | A1 | 2026-07-28 | 2026-07-30 | 2026-08-02 | 2026-08-03 | 2026-07-10 | 2026-08-03 | 2026-08-17 | 2026-08-19 | B1 | 2026-08-23 | 2026-08-26 | 2026-08-30 | 2026-08-31 | 2026-08-14 | 2026-08-31 | 2026-09-14 | 2026-09-16 | C1 | 2026-09-20 | 2026-09-21 | 2026-08-02 | 2026-10-05 |  | 2026-09-21 | 2026-10-05 | 2026-09-07 | 2026-10-05 | 1 | 0.8197% | 0.6557% | 0.8197% | 0.1639% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.08197% | 0.1639% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP21-PLR-RPT-9003 | 12-Jul-2026 11:44:02 | MM-ZTK-1F-IP21-PLR-RPT-9003 | 17-Aug-2026 14:46:17 | MM-ZTK-1F-IP21-PLR-RPT-9003 | 02-Sep-2026 18:24:50 | AFC | Approved | APPR | 07-Sep-2026 11:05:41
115 | 87 | IP21 | PLR | RPT | 9004 | docx | MM-ZTK-1F-IP21-PLR-RPT-9004 | IP21 Pipeline Walking Analysis |  |  | R1 | 2026-08-17 | 2026-08-24 | 2026-08-27 | A1 | 2026-08-29 | 2026-08-31 | 2026-09-03 | 2026-09-04 | 2026-08-17 | 2026-09-04 | 2026-09-18 | 2026-09-20 | B1 | 2026-09-24 | 2026-09-27 | 2026-10-01 | 2026-10-02 | 2026-09-03 | 2026-10-02 | 2026-10-16 | 2026-10-18 | C1 | 2026-10-22 | 2026-10-23 | 2026-09-17 | 2026-11-06 |  | 2026-10-23 | 2026-11-06 | 2026-09-25 | 2026-11-06 | 1 | 0.8197% | 0.5738% | 0.8197% | 0.2459% | 0.5738% | 0.8197% | 0.2459% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0.1639% | 0% | 0.08197% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP21-PLR-RPT-9004 | 17-Aug-2026 18:41:09 | MM-ZTK-1F-IP21-PLR-RPT-9004 | 03-Sep-2026 16:49:48 | MM-ZTK-1F-IP21-PLR-RPT-9004 | 17-Sep-2026 13:35:45 | AFC | Approved | APPR | 20-Sep-2026 11:45:30
116 | [43 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [122 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | bar: 2026-02-06 to 2028-05-26
117 | Reports: IP21 Risers and Tie-In Spools | [6 empty] | Reports: IP21 Risers and Tie-In Spools | [164 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | bar: 2026-02-06 to 2028-05-26
118 | 88 | IP21 | PLR | RPT | 9005 | docx | MM-ZTK-1F-IP21-PLR-RPT-9005 | IP21 at ZWP21 : Riser and Tie-In Spool Stress Analysis |  |  | R1 | 2026-05-28 | 2026-06-04 | 2026-06-07 | A1 | 2026-06-09 | 2026-06-11 | 2026-06-14 | 2026-06-15 | 2026-07-10 | 2026-07-02 | 2026-06-29 | 2026-07-01 | B1 | 2026-07-05 | 2026-07-08 | 2026-07-12 | 2026-07-13 | 2026-08-24 | 2026-07-13 | 2026-07-27 | 2026-07-29 | C1 | 2026-08-02 | 2026-08-03 | 2026-09-03 | 2026-08-17 |  | 2026-08-03 | 2026-08-17 |  | 2026-08-17 | 1 | 0.8197% | 0.8197% | 0.6557% | -0.1639% | 0.8197% | 0.6557% | -0.1639% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1639% | 0.08197% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP21-PLR-RPT-9005 | 12-Jul-2026 11:44:27 | MM-ZTK-1F-IP21-PLR-RPT-9005 | 24-Aug-2026 11:05:19 | MM-ZTK-1F-IP21-PLR-RPT-9005 | 03-Sep-2026 16:50:20 | AFC | Approved with Comment | AWC | 07-Sep-2026 11:15:32
119 | 89 | IP21 | PLR | RPT | 9006 | docx | MM-ZTK-1F-IP21-PLR-RPT-9006 | IP21 at PLEM14 : Riser and Tie-In Spool Stress Analysis |  |  | R1 | 2026-06-04 | 2026-06-11 | 2026-06-14 | A1 | 2026-06-16 | 2026-06-18 | 2026-06-21 | 2026-06-22 | 2026-07-15 | 2026-06-30 | 2026-07-06 | 2026-07-08 | B1 | 2026-07-12 | 2026-07-15 | 2026-07-19 | 2026-07-20 | 2026-08-20 | 2026-07-20 | 2026-08-03 | 2026-08-05 | C1 | 2026-08-09 | 2026-08-10 | 2026-09-03 | 2026-08-24 |  | 2026-08-10 | 2026-08-24 |  | 2026-08-24 | 1 | 0.8197% | 0.8197% | 0.6557% | -0.1639% | 0.8197% | 0.6557% | -0.1639% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0.08197% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP21-PLR-RPT-9006 | 15-Jul-2026 18:45:33 | MM-ZTK-1F-IP21-PLR-RPT-9006 | 20-Aug-2026 17:25:13 | MM-ZTK-1F-IP21-PLR-RPT-9006 | 03-Sep-2026 18:18:56 | AFC | Approved with Comment | AWC | 07-Sep-2026 11:16:58
120 | 90 | IP21 | PLR | RPT | 9007 | docx | MM-ZTK-1F-IP21-PLR-RPT-9007 | IP21 at ZWP21 : Riser and Tie-In Spool Seismic Analysis |  |  | R1 | 2026-10-05 | 2026-10-12 | 2026-10-15 | A1 | 2026-10-17 | 2026-10-19 | 2026-10-22 | 2026-10-23 | 2026-09-08 | 2026-10-23 | 2026-11-06 | 2026-11-08 | B1 | 2026-11-12 | 2026-11-15 | 2026-11-19 | 2026-11-20 |  | 2026-11-20 | 2026-12-04 | 2026-12-06 | C1 | 2026-12-10 | 2026-12-11 |  | 2026-12-25 |  | 2026-12-11 | 2026-12-25 |  | 2026-12-25 | 1 | 0.8197% | 0% | 0.4098% | 0.4098% | 0% | 0.4098% | 0.4098% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP21-PLR-RPT-9007 | 08-Sep-2026 18:34:44 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
121 | 91 | IP21 | PLR | RPT | 9008 | docx | MM-ZTK-1F-IP21-PLR-RPT-9008 | IP21 at PLEM14 : Riser and Tie-In Spool Seismic Analysis |  |  | R1 | 2026-10-13 | 2026-10-20 | 2026-10-23 | A1 | 2026-10-25 | 2026-10-27 | 2026-10-30 | 2026-10-31 |  | 2026-10-31 | 2026-11-14 | 2026-11-16 | B1 | 2026-11-20 | 2026-11-23 | 2026-11-27 | 2026-11-28 |  | 2026-11-28 | 2026-12-12 | 2026-12-14 | C1 | 2026-12-18 | 2026-12-19 |  | 2027-01-02 |  | 2026-12-19 | 2027-01-02 |  | 2027-01-02 | 1 | 0.8197% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| 92 | 0 | PLR | RPT | 9008 | docx | MM-ZTK-1F-IP21-PLR-RPT-9009 | IP21 Pipeline On-Bottom Stability and Stress Analysis (Seismic) |  |  | R1 | 2026-07-21 | 2026-07-28 | 2026-07-31 | A1 | 2026-08-02 | 2026-08-04 | 2026-08-07 | 2026-08-08 | 2026-08-03 | 2026-08-08 | 2026-08-22 | 2026-08-24 | B1 | 2026-08-28 | 2026-08-31 | 2026-09-04 | 2026-09-05 | 2026-08-26 | 2026-09-05 | 2026-09-19 | 2026-09-21 | C1 | 2026-09-25 | 2026-09-26 | 2026-09-08 | 2026-10-10 |  | 2026-09-26 | 2026-10-10 | 2026-09-25 | 2026-10-10 | 1 | 0.8197% | 0.6557% | 0.8197% | 0.1639% | 0.6557% | 0.8197% | 0.1639% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0.1639% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP21-PLR-RPT-9009 | 03-Aug-2026 11:02:32 | MM-ZTK-1F-IP21-PLR-RPT-9009 | 26-Aug-2026 08:45:27 | MM-ZTK-1F-IP21-PLR-RPT-9009 | 08-Sep-2026 12:36:01 | AFC | Approved | APPR | 13-Sep-2026 01:49:31
122 | [43 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [122 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | bar: 2026-02-06 to 2028-05-26
123 | Drawings: IP21 Pipeline | [6 empty] | Drawings: IP21 Pipeline | [164 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | bar: 2026-02-06 to 2028-05-26
124 | 93 | IP21 | PLR | DWG | 9001 | dwg | MM-ZTK-1F-IP21-PLR-DWG-9001 | IP21 Pipeline Route Drawing from ZWP21 to PLEM14 |  |  | R1 | 2026-04-17 | 2026-04-24 | 2026-04-27 | A1 | 2026-04-29 | 2026-05-01 | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-06 | 2026-05-19 | 2026-05-21 | B1 | 2026-05-25 | 2026-05-28 | 2026-06-01 | 2026-06-02 | 2026-06-23 | 2026-06-23 | 2026-06-16 | 2026-06-18 | C1 | 2026-06-22 | 2026-06-23 | 2026-07-10 | 2026-07-07 |  | 2026-07-11 | 2026-07-07 | 2026-07-17 | 2026-07-21 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0.08197% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP21-PLR-DWG-9001 | 06-May-2026 08:28:39 | MM-ZTK-1F-IP21-PLR-DWG-9001 | 23-Jun-2026 16:45:17 | MM-ZTK-1F-IP21-PLR-DWG-9001 | 10-Jul-2026 16:56:34 | AFC | Approved | APPR | 20-Jul-2026 03:18:20
125 | 94 | IP21 | PLR | DWG | 9002 | dwg | MM-ZTK-1F-IP21-PLR-DWG-9002 | IP21 Pipeline Alignment Sheets: ZWP21 to PLEM14 |  |  | R1 | 2026-07-23 | 2026-07-30 | 2026-08-02 | A1 | 2026-08-04 | 2026-08-06 | 2026-08-09 | 2026-08-10 | 2026-08-14 | 2026-08-10 | 2026-08-24 | 2026-08-26 | B1 | 2026-08-30 | 2026-09-02 | 2026-09-06 | 2026-09-07 | 2026-08-31 | 2026-09-07 | 2026-09-21 | 2026-09-23 | C1 | 2026-09-27 | 2026-09-28 | 2026-09-11 | 2026-10-12 |  | 2026-09-28 | 2026-10-12 | 2026-09-25 | 2026-10-12 | 1 | 0.8197% | 0.6557% | 0.8197% | 0.1639% | 0.6557% | 0.8197% | 0.1639% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0.1639% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP21-PLR-DWG-9002 | 17-Aug-2026 14:44:36 | MM-ZTK-1F-IP21-PLR-DWG-9002 | 31-Aug-2026 14:02:16 | MM-ZTK-1F-IP21-PLR-DWG-9002 | 11-Sep-2026 21:01:14 | AFC | Approved | APPR | 20-Sep-2026 11:41:53
126 | 95 | IP21 | PLR | DWG | 9003 | dwg | MM-ZTK-1F-IP21-PLR-DWG-9003 | IP21 Pipeline Schematic Diagram |  |  | R1 | 2026-07-29 | 2026-08-05 | 2026-08-08 | A1 | 2026-08-10 | 2026-08-12 | 2026-08-15 | 2026-08-16 | 2026-08-24 | 2026-08-16 | 2026-08-30 | 2026-09-01 | B1 | 2026-09-05 | 2026-09-08 | 2026-09-12 | 2026-09-13 | 2026-09-11 | 2026-09-13 | 2026-09-27 | 2026-09-29 | C1 | 2026-10-03 | 2026-10-04 | 2026-09-25 | 2026-10-18 |  | 2026-10-04 | 2026-10-18 | 2026-09-29 | 2026-10-18 | 1 | 0.8197% | 0.5738% | 0.8197% | 0.2459% | 0.6557% | 0.8197% | 0.1639% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0.1639% | 0% | 0.08197% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP21-PLR-DWG-9003 | 24-Aug-2026 11:04:47 | MM-ZTK-1F-IP21-PLR-DWG-9003 | 11-Sep-2026 21:01:49 | MM-ZTK-1F-IP21-PLR-DWG-9003 | 25-Sep-2026 16:15:58 | AFC | Approved | APPR | 29-Sep-2026 08:30:45
127 | 96 | IP21 | PLR | DWG | 9004 | dwg | MM-ZTK-1F-IP21-PLR-DWG-9004 | IP21 Pipeline Platform Approach at ZWP21 |  |  | R1 | 2026-05-11 | 2026-05-18 | 2026-05-21 | A1 | 2026-05-23 | 2026-05-25 | 2026-05-28 | 2026-05-29 | 2026-05-21 | 2026-05-21 | 2026-06-12 | 2026-06-14 | B1 | 2026-06-18 | 2026-06-21 | 2026-06-25 | 2026-06-26 | 2026-06-26 | 2026-06-26 | 2026-07-10 | 2026-07-12 | C1 | 2026-07-16 | 2026-07-17 | 2026-07-10 | 2026-07-31 |  | 2026-07-17 | 2026-07-31 | 2026-07-10 | 2026-07-31 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0.2459% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP21-PLR-DWG-9004 | 21-May-2026 09:41:20 | MM-ZTK-1F-IP21-PLR-DWG-9004 | 26-Jun-2026 20:35:12 | MM-ZTK-1F-IP21-PLR-DWG-9004 | 10-Jul-2026 12:19:23 | AFC | Approved | APPR | 12-Jul-2026 05:41:34
128 | 97 | IP21 | PLR | DWG | 9005 | dwg | MM-ZTK-1F-IP21-PLR-DWG-9005 | IP21 Pipeline PLEM Approach at PLEM14 |  |  | R1 | 2026-05-11 | 2026-05-18 | 2026-05-21 | A1 | 2026-05-23 | 2026-05-25 | 2026-05-28 | 2026-05-29 | 2026-05-21 | 2026-05-21 | 2026-06-12 | 2026-06-14 | B1 | 2026-06-18 | 2026-06-21 | 2026-06-25 | 2026-06-26 | 2026-06-26 | 2026-06-26 | 2026-07-10 | 2026-07-12 | C1 | 2026-07-16 | 2026-07-17 | 2026-07-10 | 2026-07-31 |  | 2026-07-17 | 2026-07-31 | 2026-08-14 | 2026-07-31 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0.08197% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP21-PLR-DWG-9005 | 21-May-2026 09:41:59 | MM-ZTK-1F-IP21-PLR-DWG-9005 | 26-Jun-2026 20:35:37 | MM-ZTK-1F-IP21-PLR-DWG-9005 | 10-Jul-2026 12:19:47 | AFC | Approved with Comment | AWC | 12-Jul-2026 04:56:41
129 | [43 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [122 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | bar: 2026-02-06 to 2028-05-26
130 | GA: IP21 Risers and Tie-in Spools | [6 empty] | GA: IP21 Risers and Tie-in Spools | [164 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | bar: 2026-02-06 to 2028-05-26
131 | 98 | IP21 | PLR | GA | 9001 | dwg | MM-ZTK-1F-IP21-PLR-GA-9001 | Riser GA Drawings at ZWP21 |  |  | R1 | 2026-05-18 | 2026-05-25 | 2026-05-28 | A1 | 2026-05-30 | 2026-06-01 | 2026-06-04 | 2026-06-05 | 2026-05-20 | 2026-05-20 | 2026-06-19 | 2026-06-21 | B1 | 2026-06-25 | 2026-06-28 | 2026-07-02 | 2026-07-03 | 2026-07-17 | 2026-07-03 | 2026-07-17 | 2026-07-19 | C1 | 2026-07-23 | 2026-07-24 | 2026-07-31 | 2026-08-07 |  | 2026-07-24 | 2026-08-07 | 2026-08-07 | 2026-08-07 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0.08197% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP21-PLR-GA-9001 | 20-May-2026 12:48:36 | MM-ZTK-1F-IP21-PLR-GA-9001 | 12-Jul-2026 11:43:11 | MM-ZTK-1F-IP21-PLR-GA-9001 | 03-Aug-2026 11:02:06 | AFC | Approved | APPR | 17-Aug-2026 08:39:45
132 | 99 | IP21 | PLR | GA | 9002 | dwg | MM-ZTK-1F-IP21-PLR-GA-9002 | IP21 Tie-in Spool GA Drawing at ZWP21 |  |  | R1 | 2026-07-10 | 2026-07-17 | 2026-07-20 | A1 | 2026-07-22 | 2026-07-24 | 2026-07-27 | 2026-07-28 | 2026-07-24 | 2026-07-28 | 2026-08-11 | 2026-08-13 | B1 | 2026-08-17 | 2026-08-20 | 2026-08-24 | 2026-08-25 | 2026-08-20 | 2026-08-25 | 2026-09-08 | 2026-09-10 | C1 | 2026-09-14 | 2026-09-15 | 2026-08-29 | 2026-09-29 |  | 2026-09-15 | 2026-09-29 | 2026-09-07 | 2026-09-29 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0.08197% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP21-PLR-GA-9002 | 24-Jul-2026 17:08:04 | MM-ZTK-1F-IP21-PLR-GA-9002 | 20-Aug-2026 09:37:06 | MM-ZTK-1F-IP21-PLR-GA-9002 | 29-Aug-2026 14:07:16 | AFC | Approved | APPR | 07-Sep-2026 10:20:20
133 | 100 | IP21 | PLR | GA | 9003 | dwg | MM-ZTK-1F-IP21-PLR-GA-9003 | IP21 Tie-in Spool GA Drawing at PLEM14 |  |  | R1 | 2026-07-16 | 2026-07-23 | 2026-07-26 | A1 | 2026-07-28 | 2026-07-30 | 2026-08-02 | 2026-08-03 | 2026-07-24 | 2026-08-03 | 2026-08-17 | 2026-08-19 | B1 | 2026-08-23 | 2026-08-26 | 2026-08-30 | 2026-08-31 | 2026-08-20 | 2026-08-31 | 2026-09-14 | 2026-09-16 | C1 | 2026-09-20 | 2026-09-21 | 2026-08-29 | 2026-10-05 |  | 2026-09-21 | 2026-10-05 | 2026-09-07 | 2026-10-05 | 1 | 0.8197% | 0.6557% | 0.8197% | 0.1639% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0.08197% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP21-PLR-GA-9003 | 24-Jul-2026 17:08:30 | MM-ZTK-1F-IP21-PLR-GA-9003 | 20-Aug-2026 09:37:56 | MM-ZTK-1F-IP21-PLR-GA-9003 | 29-Aug-2026 14:07:41 | AFC | Approved | APPR | 07-Sep-2026 05:38:41
134 | [43 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [122 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | bar: 2026-02-06 to 2028-05-26
135 | Isometric: IP21 Risers and Tie-in Spools | [6 empty] | Isometric: IP21 Risers and Tie-in Spools | [164 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | bar: 2026-02-06 to 2028-05-26
136 | 101 | IP21 | PLR | ISO | 9001 | dwg | MM-ZTK-1F-IP21-PLR-ISO-9001 | IP21 Riser Isometric at ZWP21 |  |  | R1 | 2026-05-30 | 2026-06-06 | 2026-06-09 | A1 | 2026-06-11 | 2026-06-13 | 2026-06-16 | 2026-06-17 | 2026-06-26 | 2026-06-26 | 2026-07-01 | 2026-07-03 | B1 | 2026-07-07 | 2026-07-10 | 2026-07-14 | 2026-07-15 | 2026-07-17 | 2026-07-15 | 2026-07-29 | 2026-07-31 | C1 | 2026-08-04 | 2026-08-05 | 2026-07-28 | 2026-08-19 |  | 2026-08-05 | 2026-08-19 | 2026-07-28 | 2026-08-19 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0.1639% | 0% | 0.2459% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP21-PLR-ISO-9001 | 26-Jun-2026 20:36:04 | MM-ZTK-1F-IP21-PLR-ISO-9001 | 12-Jul-2026 11:43:37 | MM-ZTK-1F-IP21-PLR-ISO-9001 | 28-Jul-2026 09:14:59 | AFC | Approved | APPR | 13-Aug-2026 05:27:23
137 | 102 | IP21 | PLR | ISO | 9002 | dwg | MM-ZTK-1F-IP21-PLR-ISO-9002 | IP21 Tie-in Spool Isometric at ZWP21 |  |  | R1 | 2026-07-03 | 2026-07-10 | 2026-07-13 | A1 | 2026-07-15 | 2026-07-17 | 2026-07-20 | 2026-07-21 | 2026-07-03 | 2026-07-21 | 2026-08-04 | 2026-08-06 | B1 | 2026-08-10 | 2026-08-13 | 2026-08-17 | 2026-08-18 | 2026-08-14 | 2026-08-18 | 2026-09-01 | 2026-09-03 | C1 | 2026-09-07 | 2026-09-08 | 2026-08-28 | 2026-09-22 |  | 2026-09-08 | 2026-09-22 | 2026-09-07 | 2026-09-22 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP21-PLR-ISO-9002 | 03-Jul-2026 13:27:34 | MM-ZTK-1F-IP21-PLR-ISO-9002 | 17-Aug-2026 14:45:07 | MM-ZTK-1F-IP21-PLR-ISO-9002 | 28-Aug-2026 18:12:15 | AFC | Approved | APPR | 07-Sep-2026 11:38:05
138 | 103 | IP21 | PLR | ISO | 9003 | dwg | MM-ZTK-1F-IP21-PLR-ISO-9003 | IP21 Tie-in Spool Isometric at PLEM14 |  |  | R1 | 2026-07-09 | 2026-07-16 | 2026-07-19 | A1 | 2026-07-21 | 2026-07-23 | 2026-07-26 | 2026-07-27 | 2026-07-03 | 2026-07-27 | 2026-08-10 | 2026-08-12 | B1 | 2026-08-16 | 2026-08-19 | 2026-08-23 | 2026-08-24 | 2026-08-14 | 2026-08-24 | 2026-09-07 | 2026-09-09 | C1 | 2026-09-13 | 2026-09-14 | 2026-08-28 | 2026-09-28 |  | 2026-09-14 | 2026-09-28 | 2026-09-07 | 2026-09-28 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP21-PLR-ISO-9003 | 03-Jul-2026 13:29:06 | MM-ZTK-1F-IP21-PLR-ISO-9003 | 17-Aug-2026 14:45:40 | MM-ZTK-1F-IP21-PLR-ISO-9003 | 28-Aug-2026 18:12:41 | AFC | Approved | APPR | 07-Sep-2026 11:36:57
139 | [43 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [122 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | bar: 2026-02-06 to 2028-05-26
140 | IP22 Pipeline Design from ZWP22 to ZWP8 |  |  | IP22 | ZWP22 | ZWP8 |  | IP22 Pipeline Design from ZWP22 to ZWP8 | [164 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | bar: 2026-02-06 to 2028-05-26
141 | Reports: IP22 Pipeline | [6 empty] | Reports: IP22 Pipeline | [164 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | bar: 2026-02-06 to 2028-05-26
142 | 104 | IP22 | PLR | RPT | 9001 | docx | MM-ZTK-1F-IP22-PLR-RPT-9001 | IP22 Pipeline Routing Study and Design |  |  | R1 | 2026-05-25 | 2026-06-01 | 2026-06-04 | A1 | 2026-06-06 | 2026-06-08 | 2026-06-11 | 2026-06-12 | 2026-06-26 | 2026-06-26 | 2026-06-26 | 2026-06-28 | B1 | 2026-07-02 | 2026-07-05 | 2026-07-09 | 2026-07-10 | 2026-07-27 | 2026-07-10 | 2026-07-24 | 2026-07-26 | C1 | 2026-07-30 | 2026-07-31 | 2026-08-20 | 2026-08-14 |  | 2026-07-31 | 2026-08-14 | 2026-08-20 | 2026-08-14 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.2459% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP22-PLR-RPT-9001 | 26-Jun-2026 09:58:53 | MM-ZTK-1F-IP22-PLR-RPT-9001 | 27-Jul-2026 08:49:02 | MM-ZTK-1F-IP22-PLR-RPT-9001 | 20-Aug-2026 09:40:31 | AFC | Approved | APPR | 24-Aug-2026 12:38:18
143 | 105 | IP22 | PLR | RPT | 9002 | docx | MM-ZTK-1F-IP22-PLR-RPT-9002 | IP22 Pipeline On-Bottom Roughness and In-place Stress Analysis |  |  | R1 | 2026-06-19 | 2026-06-26 | 2026-06-29 | A1 | 2026-07-01 | 2026-07-03 | 2026-07-06 | 2026-07-07 | 2026-07-15 | 2026-07-07 | 2026-07-21 | 2026-07-23 | B1 | 2026-07-27 | 2026-07-30 | 2026-08-03 | 2026-08-04 | 2026-08-14 | 2026-08-04 | 2026-08-18 | 2026-08-20 | C1 | 2026-08-24 | 2026-08-25 | 2026-08-28 | 2026-09-08 |  | 2026-08-25 | 2026-09-08 | 2026-09-07 | 2026-09-08 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP22-PLR-RPT-9002 | 15-Jul-2026 18:46:05 | MM-ZTK-1F-IP22-PLR-RPT-9002 | 14-Aug-2026 18:13:14 | MM-ZTK-1F-IP22-PLR-RPT-9002 | 28-Aug-2026 18:14:08 | AFC | Approved | APPR | 07-Sep-2026 11:42:51
144 | 106 | IP22 | PLR | RPT | 9003 | docx | MM-ZTK-1F-IP22-PLR-RPT-9003 | IP22 Pipeline Lateral Buclking Analysis |  |  | R1 | 2026-07-30 | 2026-08-06 | 2026-08-09 | A1 | 2026-08-11 | 2026-08-13 | 2026-08-16 | 2026-08-17 | 2026-08-14 | 2026-08-17 | 2026-08-31 | 2026-09-02 | B1 | 2026-09-06 | 2026-09-09 | 2026-09-13 | 2026-09-14 | 2026-08-02 | 2026-09-14 | 2026-09-28 | 2026-09-30 | C1 | 2026-10-04 | 2026-10-05 | 2026-08-02 | 2026-10-19 |  | 2026-10-05 | 2026-10-19 | 2026-09-07 | 2026-10-19 | 1 | 0.8197% | 0.5738% | 0.8197% | 0.2459% | 0.6557% | 0.8197% | 0.1639% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.2459% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP22-PLR-RPT-9003 | 17-Aug-2026 14:47:43 | #N/A | #N/A | MM-ZTK-1F-IP22-PLR-RPT-9003 | 02-Sep-2026 18:25:27 | AFC | Approved | APPR | 07-Sep-2026 11:06:52
145 | 107 | IP22 | PLR | RPT | 9004 | docx | MM-ZTK-1F-IP22-PLR-RPT-9004 | IP22 Pipeline Walking Analysis |  |  | R1 | 2026-08-26 | 2026-09-02 | 2026-09-05 | A1 | 2026-09-07 | 2026-09-09 | 2026-09-12 | 2026-09-13 | 2026-08-24 | 2026-09-13 | 2026-09-27 | 2026-09-29 | B1 | 2026-10-03 | 2026-10-06 | 2026-10-10 | 2026-10-11 | 2026-09-04 | 2026-10-11 | 2026-10-25 | 2026-10-27 | C1 | 2026-10-31 | 2026-11-01 | 2026-09-25 | 2026-11-15 |  | 2026-11-01 | 2026-11-15 | 2026-09-30 | 2026-11-15 | 1 | 0.8197% | 0.4098% | 0.8197% | 0.4098% | 0.4098% | 0.8197% | 0.4098% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0.1639% | 0% | 0% | 0.08197% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP22-PLR-RPT-9004 | 24-Aug-2026 11:07:13 | MM-ZTK-1F-IP22-PLR-RPT-9004 | 04-Sep-2026 16:19:12 | MM-ZTK-1F-IP22-PLR-RPT-9004 | 25-Sep-2026 13:29:24 | AFC | Approved | APPR | 30-Sep-2026 06:44:46
146 | [43 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [122 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | bar: 2026-02-06 to 2028-05-26
147 | Reports: IP22 Risers and Tie-in Spools | [6 empty] | Reports: IP22 Risers and Tie-in Spools | [164 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | bar: 2026-02-06 to 2028-05-26
148 | 108 | IP22 | PLR | RPT | 9005 | docx | MM-ZTK-1F-IP22-PLR-RPT-9005 | IP22 at ZWP22 : Riser and Tie-In Spool Stress Analysis |  |  | R1 | 2026-06-08 | 2026-06-15 | 2026-06-18 | A1 | 2026-06-20 | 2026-06-22 | 2026-06-25 | 2026-06-26 | 2026-08-01 | 2026-07-10 | 2026-07-10 | 2026-07-12 | B1 | 2026-07-16 | 2026-07-19 | 2026-07-23 | 2026-07-24 | 2026-08-24 | 2026-07-24 | 2026-08-07 | 2026-08-09 | C1 | 2026-08-13 | 2026-08-14 | 2026-09-09 | 2026-08-28 |  | 2026-08-14 | 2026-08-28 | 2026-09-25 | 2026-08-28 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0.1639% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP22-PLR-RPT-9005 | 27-Jul-2026 08:49:32 | MM-ZTK-1F-IP22-PLR-RPT-9005 | 24-Aug-2026 10:04:08 | MM-ZTK-1F-IP22-PLR-RPT-9005 | 09-Sep-2026 18:44:53 | AFC | Approved | APPR | 20-Sep-2026 11:15:09
149 | 109 | IP22 | PLR | RPT | 9006 | docx | MM-ZTK-1F-IP22-PLR-RPT-9006 | IP22 at ZWP8 : Riser and Tie-In Spool Stress Analysis |  |  | R1 | 2026-06-15 | 2026-06-22 | 2026-06-25 | A1 | 2026-06-27 | 2026-06-29 | 2026-07-02 | 2026-07-03 | 2026-06-30 | 2026-07-03 | 2026-07-17 | 2026-07-19 | B1 | 2026-07-23 | 2026-07-26 | 2026-07-30 | 2026-07-31 | 2026-08-07 | 2026-07-31 | 2026-08-14 | 2026-08-16 | C1 | 2026-08-20 | 2026-08-21 | 2026-09-07 | 2026-09-04 |  | 2026-08-21 | 2026-09-04 | 2026-09-25 | 2026-09-04 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP22-PLR-RPT-9006 | 30-Jun-2026 12:05:30 | MM-ZTK-1F-IP22-PLR-RPT-9006 | 07-Aug-2026 18:04:55 | MM-ZTK-1F-IP22-PLR-RPT-9006 | 07-Sep-2026 10:32:06 | AFC | Approved | APPR | 13-Sep-2026 16:49:39
150 | 110 | IP22 | PLR | RPT | 9007 | docx | MM-ZTK-1F-IP22-PLR-RPT-9007 | IP22 at ZWP22 : Riser and Tie-In Spool Seismic Analysis |  |  | R1 | 2026-10-29 | 2026-11-05 | 2026-11-08 | A1 | 2026-11-10 | 2026-11-12 | 2026-11-15 | 2026-11-16 |  | 2026-11-16 | 2026-11-30 | 2026-12-02 | B1 | 2026-12-06 | 2026-12-09 | 2026-12-13 | 2026-12-14 |  | 2026-12-14 | 2026-12-28 | 2026-12-30 | C1 | 2027-01-03 | 2027-01-04 |  | 2027-01-18 |  | 2027-01-04 | 2027-01-18 |  | 2027-01-18 | 1 | 0.8197% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
151 | 111 | IP22 | PLR | RPT | 9008 | docx | MM-ZTK-1F-IP22-PLR-RPT-9008 | IP22 at ZWP8 : Riser and Tie-In Spool Seismic Analysis |  |  | R1 | 2026-11-06 | 2026-11-13 | 2026-11-16 | A1 | 2026-11-18 | 2026-11-20 | 2026-11-23 | 2026-11-24 |  | 2026-11-24 | 2026-12-08 | 2026-12-10 | B1 | 2026-12-14 | 2026-12-17 | 2026-12-21 | 2026-12-22 |  | 2026-12-22 | 2027-01-05 | 2027-01-07 | C1 | 2027-01-11 | 2027-01-12 |  | 2027-01-26 |  | 2027-01-12 | 2027-01-26 |  | 2027-01-26 | 1 | 0.8197% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| 112 | 0 | PLR | RPT | 9008 | docx | MM-ZTK-1F-IP22-PLR-RPT-9009 | IP22 Pipeline On-Bottom Stability and Stress Analysis (Seismic) |  |  | R1 | 2026-08-06 | 2026-08-13 | 2026-08-16 | A1 | 2026-08-18 | 2026-08-20 | 2026-08-23 | 2026-08-24 | 2026-08-21 | 2026-08-24 | 2026-09-07 | 2026-09-09 | B1 | 2026-09-13 | 2026-09-16 | 2026-09-20 | 2026-09-21 |  | 2026-09-21 | 2026-10-05 | 2026-10-07 | C1 | 2026-10-11 | 2026-10-12 | 2026-08-29 | 2026-10-26 |  | 2026-10-12 | 2026-10-26 | 2026-09-07 | 2026-10-26 | 1 | 0.8197% | 0.5738% | 0.6557% | 0.08197% | 0.5738% | 0.6557% | 0.08197% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0.08197% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP22-PLR-RPT-9009 | 21-Aug-2026 09:43:26 | #N/A | #N/A | MM-ZTK-1F-IP22-PLR-RPT-9009 | 29-Aug-2026 14:09:02 | AFC | Approved | APPR | 07-Sep-2026 11:19:12
152 | [43 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [122 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | bar: 2026-02-06 to 2028-05-26
153 | Drawings: IP22 Pipeline | [6 empty] | Drawings: IP22 Pipeline | [164 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | bar: 2026-02-06 to 2028-05-26
154 | 113 | IP22 | PLR | DWG | 9001 | dwg | MM-ZTK-1F-IP22-PLR-DWG-9001 | IP22 Pipeline Route Drawing from ZWP22 to ZWP8 |  |  | R1 | 2026-04-17 | 2026-04-24 | 2026-04-27 | A1 | 2026-04-29 | 2026-05-01 | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-06 | 2026-05-19 | 2026-05-21 | B1 | 2026-05-25 | 2026-05-28 | 2026-06-01 | 2026-06-02 | 2026-06-23 | 2026-06-23 | 2026-06-16 | 2026-06-18 | C1 | 2026-06-22 | 2026-06-23 | 2026-07-10 | 2026-07-07 |  | 2026-07-11 | 2026-07-07 | 2026-07-17 | 2026-07-21 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0.08197% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP22-PLR-DWG-9001 | 05-May-2026 15:12:34 | MM-ZTK-1F-IP22-PLR-DWG-9001 | 23-Jun-2026 16:45:47 | MM-ZTK-1F-IP22-PLR-DWG-9001 | 10-Jul-2026 16:57:00 | AFC | Approved | APPR | 20-Jul-2026 03:12:12
155 | 114 | IP22 | PLR | DWG | 9002 | dwg | MM-ZTK-1F-IP22-PLR-DWG-9002 | IP22 Pipeline Alignment Sheets: ZWP22 to ZWP8 |  |  | R1 | 2026-08-06 | 2026-08-13 | 2026-08-16 | A1 | 2026-08-18 | 2026-08-20 | 2026-08-23 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-09-07 | 2026-09-09 | B1 | 2026-09-13 | 2026-09-16 | 2026-09-20 | 2026-09-21 | 2026-09-07 | 2026-09-21 | 2026-10-05 | 2026-10-07 | C1 | 2026-10-11 | 2026-10-12 | 2026-09-24 | 2026-10-26 |  | 2026-10-12 | 2026-10-26 | 2026-09-29 | 2026-10-26 | 1 | 0.8197% | 0.5738% | 0.8197% | 0.2459% | 0.5738% | 0.8197% | 0.2459% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0.1639% | 0% | 0.08197% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP22-PLR-DWG-9002 | 24-Aug-2026 11:05:47 | MM-ZTK-1F-IP22-PLR-DWG-9002 | 07-Sep-2026 10:30:51 | MM-ZTK-1F-IP22-PLR-DWG-9002 | 24-Sep-2026 10:54:31 | AFC | Approved | APPR | 29-Sep-2026 08:13:44
156 | 115 | IP22 | PLR | DWG | 9003 | dwg | MM-ZTK-1F-IP22-PLR-DWG-9003 | IP22 Pipeline Schematic Diagram |  |  | R1 | 2026-08-12 | 2026-08-19 | 2026-08-22 | A1 | 2026-08-24 | 2026-08-26 | 2026-08-29 | 2026-08-30 | 2026-08-24 | 2026-08-30 | 2026-09-13 | 2026-09-15 | B1 | 2026-09-19 | 2026-09-22 | 2026-09-26 | 2026-09-27 | 2026-09-08 | 2026-09-27 | 2026-10-11 | 2026-10-13 | C1 | 2026-10-17 | 2026-10-18 | 2026-09-25 | 2026-11-01 |  | 2026-10-18 | 2026-11-01 | 2026-09-29 | 2026-11-01 | 1 | 0.8197% | 0.5738% | 0.8197% | 0.2459% | 0.5738% | 0.8197% | 0.2459% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0.1639% | 0% | 0.08197% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP22-PLR-DWG-9003 | 24-Aug-2026 11:06:12 | MM-ZTK-1F-IP22-PLR-DWG-9003 | 08-Sep-2026 12:36:30 | MM-ZTK-1F-IP22-PLR-DWG-9003 | 25-Sep-2026 16:17:25 | AFC | Approved | APPR | 29-Sep-2026 08:29:19
157 | 116 | IP22 | PLR | DWG | 9004 | dwg | MM-ZTK-1F-IP22-PLR-DWG-9004 | IP22 Pipeline Platform Approach at ZWP22 |  |  | R1 | 2026-05-22 | 2026-05-29 | 2026-06-01 | A1 | 2026-06-03 | 2026-06-05 | 2026-06-08 | 2026-06-09 | 2026-06-26 | 2026-07-29 | 2026-06-23 | 2026-06-25 | B1 | 2026-06-29 | 2026-07-02 | 2026-07-06 | 2026-07-07 | 2026-07-10 | 2026-07-07 | 2026-07-21 | 2026-07-23 | C1 | 2026-07-27 | 2026-07-28 | 2026-07-24 | 2026-08-11 |  | 2026-07-28 | 2026-08-11 | 2026-07-25 | 2026-08-11 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0.1639% | 0% | 0.08197% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.4918% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP22-PLR-DWG-9004 | 27-Jun-2026 19:11:46 | MM-ZTK-1F-IP22-PLR-DWG-9004 | 10-Jul-2026 12:20:15 | MM-ZTK-1F-IP22-PLR-DWG-9004 | 24-Jul-2026 12:07:02 | AFC | Approved | APPR | 30-Jul-2026 03:35:19
158 | 117 | IP22 | PLR | DWG | 9005 | dwg | MM-ZTK-1F-IP22-PLR-DWG-9005 | IP22 Pipeline Platform Approach at ZWP8 |  |  | R1 | 2026-05-28 | 2026-06-04 | 2026-06-07 | A1 | 2026-06-09 | 2026-06-11 | 2026-06-14 | 2026-06-15 | 2026-05-26 | 2026-05-26 | 2026-06-29 | 2026-07-01 | B1 | 2026-07-05 | 2026-07-08 | 2026-07-12 | 2026-07-13 | 2026-06-26 | 2026-06-26 | 2026-07-27 | 2026-07-29 | C1 | 2026-08-02 | 2026-08-03 | 2026-07-10 | 2026-08-17 |  | 2026-08-03 | 2026-08-17 |  | 2026-08-17 | 1 | 0.8197% | 0.8197% | 0.6557% | -0.1639% | 0.8197% | 0.6557% | -0.1639% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0.08197% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP22-PLR-DWG-9005 | 26-May-2026 16:49:47 | MM-ZTK-1F-IP22-PLR-DWG-9005 | 26-Jun-2026 20:36:32 | MM-ZTK-1F-IP22-PLR-DWG-9005 | 10-Jul-2026 12:20:39 | AFC | Approved with Comment | AWC | 12-Jul-2026 05:39:19
159 | [43 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [122 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | bar: 2026-02-06 to 2028-05-26
160 | GA: IP22 Risers and Tie-in Spools | [6 empty] | GA: IP22 Risers and Tie-in Spools | [164 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | bar: 2026-02-06 to 2028-05-26
161 | 118 | IP22 | PLR | GA | 9001 | dwg | MM-ZTK-1F-IP22-PLR-GA-9001 | Riser GA Drawings at ZWP22 |  |  | R1 | 2026-05-14 | 2026-05-21 | 2026-05-24 | A1 | 2026-05-26 | 2026-05-28 | 2026-05-31 | 2026-06-01 | 2026-05-26 | 2026-05-26 | 2026-06-15 | 2026-06-17 | B1 | 2026-06-21 | 2026-06-24 | 2026-06-28 | 2026-06-29 | 2026-07-10 | 2026-06-29 | 2026-07-13 | 2026-07-15 | C1 | 2026-07-19 | 2026-07-20 | 2026-07-31 | 2026-08-03 |  | 2026-07-20 | 2026-08-03 | 2026-08-07 | 2026-08-03 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP22-PLR-GA-9001 | 26-May-2026 16:50:20 | MM-ZTK-1F-IP22-PLR-GA-9001 | 12-Jul-2026 11:44:53 | MM-ZTK-1F-IP22-PLR-GA-9001 | 03-Aug-2026 11:03:04 | AFC | Approved | APPR | 17-Aug-2026 08:40:59
162 | 119 | IP22 | PLR | GA | 9002 | dwg | MM-ZTK-1F-IP22-PLR-GA-9002 | IP22 Tie-in Spool GA Drawing at ZWP22 |  |  | R1 | 2026-07-22 | 2026-07-29 | 2026-08-01 | A1 | 2026-08-03 | 2026-08-05 | 2026-08-08 | 2026-08-09 | 2026-07-24 | 2026-08-09 | 2026-08-23 | 2026-08-25 | B1 | 2026-08-29 | 2026-09-01 | 2026-09-05 | 2026-09-06 | 2026-08-20 | 2026-09-06 | 2026-09-20 | 2026-09-22 | C1 | 2026-09-26 | 2026-09-27 | 2026-08-29 | 2026-10-11 |  | 2026-09-27 | 2026-10-11 | 2026-09-07 | 2026-10-11 | 1 | 0.8197% | 0.6557% | 0.8197% | 0.1639% | 0.6557% | 0.8197% | 0.1639% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0.08197% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP22-PLR-GA-9002 | 24-Jul-2026 17:08:55 | MM-ZTK-1F-IP22-PLR-GA-9002 | 20-Aug-2026 09:38:36 | MM-ZTK-1F-IP22-PLR-GA-9002 | 29-Aug-2026 14:08:08 | AFC | Approved | APPR | 07-Sep-2026 11:14:07
163 | 120 | IP22 | PLR | GA | 9003 | dwg | MM-ZTK-1F-IP22-PLR-GA-9003 | IP22 Tie-in Spool GA Drawing at ZWP8 |  |  | R1 | 2026-07-28 | 2026-08-04 | 2026-08-07 | A1 | 2026-08-09 | 2026-08-11 | 2026-08-14 | 2026-08-15 | 2026-07-24 | 2026-08-15 | 2026-08-29 | 2026-08-31 | B1 | 2026-09-04 | 2026-09-07 | 2026-09-11 | 2026-09-12 | 2026-08-20 | 2026-09-12 | 2026-09-26 | 2026-09-28 | C1 | 2026-10-02 | 2026-10-03 | 2026-08-29 | 2026-10-17 |  | 2026-10-03 | 2026-10-17 | 2026-09-07 | 2026-10-17 | 1 | 0.8197% | 0.5738% | 0.8197% | 0.2459% | 0.6557% | 0.8197% | 0.1639% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0.08197% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP22-PLR-GA-9003 | 24-Jul-2026 17:09:20 | MM-ZTK-1F-IP22-PLR-GA-9003 | 20-Aug-2026 09:39:23 | MM-ZTK-1F-IP22-PLR-GA-9003 | 29-Aug-2026 14:08:34 | AFC | Approved | APPR | 07-Sep-2026 11:18:06
164 | [43 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [122 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | bar: 2026-02-06 to 2028-05-26
165 | Isometric: IP22 Risers and Tie-in Spools | [6 empty] | Isometric: IP22 Risers and Tie-in Spools | [164 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | bar: 2026-02-06 to 2028-05-26
166 | 121 | IP22 | PLR | ISO | 9001 | dwg | MM-ZTK-1F-IP22-PLR-ISO-9001 | IP22 Riser Isometric at ZWP22 |  |  | R1 | 2026-07-03 | 2026-07-10 | 2026-07-13 | A1 | 2026-07-15 | 2026-07-17 | 2026-07-20 | 2026-07-21 | 2026-07-31 | 2026-07-21 | 2026-08-04 | 2026-08-06 | B1 | 2026-08-10 | 2026-08-13 | 2026-08-17 | 2026-08-18 | 2026-08-24 | 2026-08-18 | 2026-09-01 | 2026-09-03 | C1 | 2026-09-07 | 2026-09-08 | 2026-09-07 | 2026-09-22 |  | 2026-09-08 | 2026-09-22 | 2026-09-25 | 2026-09-22 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP22-PLR-ISO-9001 | 03-Aug-2026 11:03:32 | MM-ZTK-1F-IP22-PLR-ISO-9001 | 24-Aug-2026 11:06:43 | MM-ZTK-1F-IP22-PLR-ISO-9001 | 07-Sep-2026 10:31:27 | AFC | Approved | APPR | 13-Sep-2026 16:47:21
167 | 122 | IP22 | PLR | ISO | 9002 | dwg | MM-ZTK-1F-IP22-PLR-ISO-9002 | IP22 Tie-in Spool Isometric at ZWP22 |  |  | R1 | 2026-07-15 | 2026-07-22 | 2026-07-25 | A1 | 2026-07-27 | 2026-07-29 | 2026-08-01 | 2026-08-02 | 2026-07-03 | 2026-08-02 | 2026-08-16 | 2026-08-18 | B1 | 2026-08-22 | 2026-08-25 | 2026-08-29 | 2026-08-30 | 2026-08-14 | 2026-08-30 | 2026-09-13 | 2026-09-15 | C1 | 2026-09-19 | 2026-09-20 | 2026-08-28 | 2026-10-04 |  | 2026-09-20 | 2026-10-04 | 2026-09-07 | 2026-10-04 | 1 | 0.8197% | 0.6557% | 0.8197% | 0.1639% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP22-PLR-ISO-9002 | 03-Jul-2026 13:30:40 | MM-ZTK-1F-IP22-PLR-ISO-9002 | 17-Aug-2026 14:46:43 | MM-ZTK-1F-IP22-PLR-ISO-9002 | 28-Aug-2026 18:13:06 | AFC | Approved | APPR | 07-Sep-2026 11:40:24
168 | 123 | IP22 | PLR | ISO | 9003 | dwg | MM-ZTK-1F-IP22-PLR-ISO-9003 | IP22 Tie-in Spool Isometric at ZWP8 |  |  | R1 | 2026-07-21 | 2026-07-28 | 2026-07-31 | A1 | 2026-08-02 | 2026-08-04 | 2026-08-07 | 2026-08-08 | 2026-07-03 | 2026-08-08 | 2026-08-22 | 2026-08-24 | B1 | 2026-08-28 | 2026-08-31 | 2026-09-04 | 2026-09-05 | 2026-08-14 | 2026-09-05 | 2026-09-19 | 2026-09-21 | C1 | 2026-09-25 | 2026-09-26 | 2026-08-28 | 2026-10-10 |  | 2026-09-26 | 2026-10-10 | 2026-09-07 | 2026-10-10 | 1 | 0.8197% | 0.6557% | 0.8197% | 0.1639% | 0.6557% | 0.8197% | 0.1639% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP22-PLR-ISO-9003 | 03-Jul-2026 13:31:43 | MM-ZTK-1F-IP22-PLR-ISO-9003 | 17-Aug-2026 14:47:11 | MM-ZTK-1F-IP22-PLR-ISO-9003 | 28-Aug-2026 18:13:31 | AFC | Approved | APPR | 07-Sep-2026 11:41:31
169 | [43 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [122 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | bar: 2026-02-06 to 2028-05-26
170 | IP23 Pipeline Design from ZWP23 to PLEM7 |  |  | IP23 | ZWP23 | PLEM7 |  | IP23 Pipeline Design from ZWP23 to PLEM7 | [164 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | bar: 2026-02-06 to 2028-05-26
171 | Reports: IP23 Pipeline | [6 empty] | Reports: IP23 Pipeline | [164 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | bar: 2026-02-06 to 2028-05-26
172 | 124 | IP23 | PLR | RPT | 9001 | docx | MM-ZTK-1F-IP23-PLR-RPT-9001 | IP23 Pipeline Routing Study and Design |  |  | R1 | 2026-05-22 | 2026-05-29 | 2026-06-01 | A1 | 2026-06-03 | 2026-06-05 | 2026-06-08 | 2026-06-09 | 2026-08-01 | 2026-07-29 | 2026-06-23 | 2026-06-25 | B1 | 2026-06-29 | 2026-07-02 | 2026-07-06 | 2026-07-07 | 2026-08-20 | 2026-07-07 | 2026-07-21 | 2026-07-23 | C1 | 2026-07-27 | 2026-07-28 | 2026-08-20 | 2026-08-11 |  | 2026-07-28 | 2026-08-11 | 2026-08-20 | 2026-08-11 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.4918% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP23-PLR-RPT-9001 | 27-Jul-2026 08:49:57 | #N/A | #N/A | MM-ZTK-1F-IP23-PLR-RPT-9001 | 20-Aug-2026 07:54:41 | AFC | Approved | APPR | 24-Aug-2026 13:08:01
173 | 125 | IP23 | PLR | RPT | 9002 | docx | MM-ZTK-1F-IP23-PLR-RPT-9002 | IP23 Pipeline On-Bottom Roughness and In-place Stress Analysis |  |  | R1 | 2026-06-26 | 2026-07-03 | 2026-07-06 | A1 | 2026-07-08 | 2026-07-10 | 2026-07-13 | 2026-07-14 | 2026-08-01 | 2026-07-14 | 2026-07-28 | 2026-07-30 | B1 | 2026-08-03 | 2026-08-06 | 2026-08-10 | 2026-08-11 | 2026-08-21 | 2026-08-11 | 2026-08-25 | 2026-08-27 | C1 | 2026-08-31 | 2026-09-01 | 2026-09-11 | 2026-09-15 |  | 2026-09-01 | 2026-09-15 | 2026-09-25 | 2026-09-15 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP23-PLR-RPT-9002 | 31-Jul-2026 18:15:58 | MM-ZTK-1F-IP23-PLR-RPT-9002 | 21-Aug-2026 13:59:29 | MM-ZTK-1F-IP23-PLR-RPT-9002 | 11-Sep-2026 12:48:20 | AFC | Approved | APPR | 20-Sep-2026 11:16:23
174 | 126 | IP23 | PLR | RPT | 9003 | docx | MM-ZTK-1F-IP23-PLR-RPT-9003 | IP23 Pipeline Lateral Buclking Analysis |  |  | R1 | 2026-08-13 | 2026-08-20 | 2026-08-23 | A1 | 2026-08-25 | 2026-08-27 | 2026-08-30 | 2026-08-31 | 2026-08-14 | 2026-08-31 | 2026-09-14 | 2026-09-16 | B1 | 2026-09-20 | 2026-09-23 | 2026-09-27 | 2026-09-28 | 2026-08-02 | 2026-09-28 | 2026-10-12 | 2026-10-14 | C1 | 2026-10-18 | 2026-10-19 | 2026-08-02 | 2026-11-02 |  | 2026-10-19 | 2026-11-02 | 2026-09-07 | 2026-11-02 | 1 | 0.8197% | 0.5738% | 0.8197% | 0.2459% | 0.5738% | 0.8197% | 0.2459% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.2459% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP23-PLR-RPT-9003 | 17-Aug-2026 14:49:35 | #N/A | #N/A | MM-ZTK-1F-IP23-PLR-RPT-9003 | 02-Sep-2026 18:26:01 | AFC | Approved | APPR | 07-Sep-2026 11:08:01
175 | 127 | IP23 | PLR | RPT | 9004 | docx | MM-ZTK-1F-IP23-PLR-RPT-9004 | IP23 Pipeline Walking Analysis |  |  | R1 | 2026-09-16 | 2026-09-23 | 2026-09-26 | A1 | 2026-09-28 | 2026-09-30 | 2026-10-03 | 2026-10-04 | 2026-09-04 | 2026-10-04 | 2026-10-18 | 2026-10-20 | B1 | 2026-10-24 | 2026-10-27 | 2026-10-31 | 2026-11-01 | 2026-09-18 | 2026-11-01 | 2026-11-15 | 2026-11-17 | C1 | 2026-11-21 | 2026-11-22 |  | 2026-12-06 |  | 2026-11-22 | 2026-12-06 |  | 2026-12-06 | 1 | 0.8197% | 0% | 0.5738% | 0.5738% | 0.4098% | 0.5738% | 0.1639% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP23-PLR-RPT-9004 | 04-Sep-2026 16:19:40 | MM-ZTK-1F-IP23-PLR-RPT-9004 | 18-Sep-2026 17:29:00 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
176 | [43 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [122 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | bar: 2026-02-06 to 2028-05-26
177 | Reports: IP23 Risers and Tie-in Spools | [6 empty] | Reports: IP23 Risers and Tie-in Spools | [164 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | bar: 2026-02-06 to 2028-05-26
178 | 128 | IP23 | PLR | RPT | 9005 | docx | MM-ZTK-1F-IP23-PLR-RPT-9005 | IP23 at ZWP23 : Riser and Tie-In Spool Stress Analysis |  |  | R1 | 2026-06-11 | 2026-06-18 | 2026-06-21 | A1 | 2026-06-23 | 2026-06-25 | 2026-06-28 | 2026-06-29 | 2026-07-10 | 2026-06-29 | 2026-07-13 | 2026-07-15 | B1 | 2026-07-19 | 2026-07-22 | 2026-07-26 | 2026-07-27 | 2026-08-21 | 2026-07-27 | 2026-08-10 | 2026-08-12 | C1 | 2026-08-16 | 2026-08-17 | 2026-09-17 | 2026-08-31 |  | 2026-08-17 | 2026-08-31 | 2026-09-25 | 2026-08-31 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0% | 0.08197% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP23-PLR-RPT-9005 | 12-Jul-2026 11:45:21 | MM-ZTK-1F-IP23-PLR-RPT-9005 | 21-Aug-2026 14:00:13 | MM-ZTK-1F-IP23-PLR-RPT-9005 | 17-Sep-2026 13:36:24 | AFC | Approved | APPR | 26-Sep-2026 08:03:20
179 | 129 | IP23 | PLR | RPT | 9006 | docx | MM-ZTK-1F-IP23-PLR-RPT-9006 | IP23 at PLEM7 : Riser and Tie-In Spool Stress Analysis |  |  | R1 | 2026-06-18 | 2026-06-25 | 2026-06-28 | A1 | 2026-06-30 | 2026-07-02 | 2026-07-05 | 2026-07-06 | 2026-07-31 | 2026-07-06 | 2026-07-20 | 2026-07-22 | B1 | 2026-07-26 | 2026-07-29 | 2026-08-02 | 2026-08-03 | 2026-08-21 | 2026-08-03 | 2026-08-17 | 2026-08-19 | C1 | 2026-08-23 | 2026-08-24 | 2026-09-22 | 2026-09-07 |  | 2026-08-24 | 2026-09-07 | 2026-09-25 | 2026-09-07 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0.2459% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP23-PLR-RPT-9006 | 03-Aug-2026 11:03:57 | MM-ZTK-1F-IP23-PLR-RPT-9006 | 21-Aug-2026 09:44:06 | MM-ZTK-1F-IP23-PLR-RPT-9006 | 22-Sep-2026 11:59:39 | AFC | Approved | APPR | 26-Sep-2026 07:48:37
180 | 130 | IP23 | PLR | RPT | 9007 | docx | MM-ZTK-1F-IP23-PLR-RPT-9007 | IP23 at ZWP23 : Riser and Tie-In Spool Seismic Analysis |  |  | R1 | 2026-11-24 | 2026-12-01 | 2026-12-04 | A1 | 2026-12-06 | 2026-12-08 | 2026-12-11 | 2026-12-12 |  | 2026-12-12 | 2026-12-26 | 2026-12-28 | B1 | 2027-01-01 | 2027-01-04 | 2027-01-08 | 2027-01-09 |  | 2027-01-09 | 2027-01-23 | 2027-01-25 | C1 | 2027-01-29 | 2027-01-30 |  | 2027-02-13 |  | 2027-01-30 | 2027-02-13 |  | 2027-02-13 | 1 | 0.8197% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
181 | 131 | IP23 | PLR | RPT | 9008 | docx | MM-ZTK-1F-IP23-PLR-RPT-9008 | IP23 at PLEM7 : Riser and Tie-In Spool Seismic Analysis |  |  | R1 | 2026-12-02 | 2026-12-09 | 2026-12-12 | A1 | 2026-12-14 | 2026-12-16 | 2026-12-19 | 2026-12-20 |  | 2026-12-20 | 2027-01-03 | 2027-01-05 | B1 | 2027-01-09 | 2027-01-12 | 2027-01-16 | 2027-01-17 |  | 2027-01-17 | 2027-01-31 | 2027-02-02 | C1 | 2027-02-06 | 2027-02-07 |  | 2027-02-21 |  | 2027-02-07 | 2027-02-21 |  | 2027-02-21 | 1 | 0.8197% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| 132 | 0 | PLR | RPT | 9008 | docx | MM-ZTK-1F-IP23-PLR-RPT-9009 | IP23 Pipeline On-Bottom Stability and Stress Analysis (Seismic) |  |  | R1 | 2026-08-24 | 2026-08-31 | 2026-09-03 | A1 | 2026-09-05 | 2026-09-07 | 2026-09-10 | 2026-09-11 | 2026-08-18 | 2026-09-11 | 2026-09-25 | 2026-09-27 | B1 | 2026-10-01 | 2026-10-04 | 2026-10-08 | 2026-10-09 | 2026-09-03 | 2026-10-09 | 2026-10-23 | 2026-10-25 | C1 | 2026-10-29 | 2026-10-30 | 2026-09-03 | 2026-11-13 |  | 2026-10-30 | 2026-11-13 | 2026-09-07 | 2026-11-13 | 1 | 0.8197% | 0.4098% | 0.8197% | 0.4098% | 0.5738% | 0.8197% | 0.2459% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0.2459% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP23-PLR-RPT-9009 | 18-Aug-2026 10:57:49 | #N/A | #N/A | MM-ZTK-1F-IP23-PLR-RPT-9009 | 03-Sep-2026 16:50:53 | AFC | Approved | APPR | 07-Sep-2026 11:24:59
182 | [43 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [122 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | bar: 2026-02-06 to 2028-05-26
183 | Drawings: IP23 Pipeline | [6 empty] | Drawings: IP23 Pipeline | [164 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | bar: 2026-02-06 to 2028-05-26
184 | 133 | IP23 | PLR | DWG | 9001 | dwg | MM-ZTK-1F-IP23-PLR-DWG-9001 | IP23 Pipeline Route Drawing from ZWP23 to PLEM7 |  |  | R1 | 2026-04-27 | 2026-05-04 | 2026-05-07 | A1 | 2026-05-09 | 2026-05-11 | 2026-05-14 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-29 | 2026-05-31 | B1 | 2026-06-04 | 2026-06-07 | 2026-06-11 | 2026-06-12 | 2026-07-03 | 2026-06-30 | 2026-06-26 | 2026-06-28 | C1 | 2026-07-02 | 2026-07-03 | 2026-07-24 | 2026-07-17 |  | 2026-07-03 | 2026-07-17 | 2026-07-25 | 2026-07-17 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0% | 0% | 0.2459% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP23-PLR-DWG-9001 | 15-May-2026 17:48:11 | MM-ZTK-1F-IP23-PLR-DWG-9001 | 03-Jul-2026 09:49:56 | MM-ZTK-1F-IP23-PLR-DWG-9001 | 24-Jul-2026 17:09:48 | AFC | Approved | APPR | 30-Jul-2026 03:54:32
185 | 134 | IP23 | PLR | DWG | 9002 | dwg | MM-ZTK-1F-IP23-PLR-DWG-9002 | IP23 Pipeline Alignment Sheets: ZWP23 to PLEM7 |  |  | R1 | 2026-08-20 | 2026-08-27 | 2026-08-30 | A1 | 2026-09-01 | 2026-09-03 | 2026-09-06 | 2026-09-07 | 2026-09-08 | 2026-09-07 | 2026-09-21 | 2026-09-23 | B1 | 2026-09-27 | 2026-09-30 | 2026-10-04 | 2026-10-05 |  | 2026-10-05 | 2026-10-19 | 2026-10-21 | C1 | 2026-10-25 | 2026-10-26 | 2026-09-24 | 2026-11-09 |  | 2026-10-26 | 2026-11-09 | 2026-09-29 | 2026-11-09 | 1 | 0.8197% | 0.4098% | 0.6557% | 0.2459% | 0.5738% | 0.6557% | 0.08197% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0.08197% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP23-PLR-DWG-9002 | 08-Sep-2026 12:36:59 | #N/A | #N/A | MM-ZTK-1F-IP23-PLR-DWG-9002 | 24-Sep-2026 10:54:58 | AFC | Approved | APPR | 29-Sep-2026 08:12:19
186 | 135 | IP23 | PLR | DWG | 9003 | dwg | MM-ZTK-1F-IP23-PLR-DWG-9003 | IP23 Pipeline Schematic Diagram |  |  | R1 | 2026-08-26 | 2026-09-02 | 2026-09-05 | A1 | 2026-09-07 | 2026-09-09 | 2026-09-12 | 2026-09-13 | 2026-08-24 | 2026-09-13 | 2026-09-27 | 2026-09-29 | B1 | 2026-10-03 | 2026-10-06 | 2026-10-10 | 2026-10-11 | 2026-09-11 | 2026-10-11 | 2026-10-25 | 2026-10-27 | C1 | 2026-10-31 | 2026-11-01 | 2026-09-25 | 2026-11-15 |  | 2026-11-01 | 2026-11-15 | 2026-09-29 | 2026-11-15 | 1 | 0.8197% | 0.4098% | 0.8197% | 0.4098% | 0.4098% | 0.8197% | 0.4098% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0.1639% | 0% | 0.08197% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP23-PLR-DWG-9003 | 24-Aug-2026 11:07:40 | MM-ZTK-1F-IP23-PLR-DWG-9003 | 11-Sep-2026 21:04:15 | MM-ZTK-1F-IP23-PLR-DWG-9003 | 25-Sep-2026 16:17:56 | AFC | Approved | APPR | 29-Sep-2026 04:43:24
187 | 136 | IP23 | PLR | DWG | 9004 | dwg | MM-ZTK-1F-IP23-PLR-DWG-9004 | IP23 Pipeline Platform Approach at ZWP23 |  |  | R1 | 2026-05-27 | 2026-06-03 | 2026-06-06 | A1 | 2026-06-08 | 2026-06-10 | 2026-06-13 | 2026-06-14 | 2026-05-26 | 2026-05-26 | 2026-06-28 | 2026-06-30 | B1 | 2026-07-04 | 2026-07-07 | 2026-07-11 | 2026-07-12 | 2026-07-03 | 2026-07-12 | 2026-07-26 | 2026-07-28 | C1 | 2026-08-01 | 2026-08-02 | 2026-07-24 | 2026-08-16 |  | 2026-08-02 | 2026-08-16 | 2026-07-25 | 2026-08-16 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP23-PLR-DWG-9004 | 26-May-2026 16:50:47 | MM-ZTK-1F-IP23-PLR-DWG-9004 | 03-Jul-2026 09:50:27 | MM-ZTK-1F-IP23-PLR-DWG-9004 | 24-Jul-2026 12:36:21 | AFC | Approved | APPR | 30-Jul-2026 03:37:49
188 | 137 | IP23 | PLR | DWG | 9005 | dwg | MM-ZTK-1F-IP23-PLR-DWG-9005 | IP23 Pipeline PLEM Approach at PLEM7 |  |  | R1 | 2026-06-02 | 2026-06-09 | 2026-06-12 | A1 | 2026-06-14 | 2026-06-16 | 2026-06-19 | 2026-06-20 | 2026-05-26 | 2026-05-26 | 2026-07-04 | 2026-07-06 | B1 | 2026-07-10 | 2026-07-13 | 2026-07-17 | 2026-07-18 | 2026-07-03 | 2026-07-18 | 2026-08-01 | 2026-08-03 | C1 | 2026-08-07 | 2026-08-08 | 2026-07-24 | 2026-08-22 |  | 2026-08-08 | 2026-08-22 | 2026-08-21 | 2026-08-22 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP23-PLR-DWG-9005 | 26-May-2026 16:51:13 | MM-ZTK-1F-IP23-PLR-DWG-9005 | 03-Jul-2026 09:50:56 | MM-ZTK-1F-IP23-PLR-DWG-9005 | 24-Jul-2026 17:10:15 | AFC | Approved | APPR | 30-Jul-2026 12:27:16
189 | [43 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [122 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | bar: 2026-02-06 to 2028-05-26
190 | GA: IP23 Riser and Tie-in Spools | [6 empty] | GA: IP23 Riser and Tie-in Spools | [164 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | bar: 2026-02-06 to 2028-05-26
191 | 138 | IP23 | PLR | GA | 9001 | dwg | MM-ZTK-1F-IP23-PLR-GA-9001 | Riser GA Drawing at ZWP23 |  |  | R1 | 2026-05-27 | 2026-06-03 | 2026-06-06 | A1 | 2026-06-08 | 2026-06-10 | 2026-06-13 | 2026-06-14 | 2026-06-26 | 2026-06-26 | 2026-06-28 | 2026-06-30 | B1 | 2026-07-04 | 2026-07-07 | 2026-07-11 | 2026-07-12 | 2026-07-21 | 2026-07-12 | 2026-07-26 | 2026-07-28 | C1 | 2026-08-01 | 2026-08-02 | 2026-08-10 | 2026-08-16 |  | 2026-08-02 | 2026-08-16 | 2026-08-10 | 2026-08-16 | 1 | 0.8197% | 0.8197% | 0.8197% | 0% | 0.8197% | 0.8197% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.2459% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP23-PLR-GA-9001 | 26-Jun-2026 20:36:59 | MM-ZTK-1F-IP23-PLR-GA-9001 | 21-Jul-2026 08:37:42 | MM-ZTK-1F-IP23-PLR-GA-9001 | 10-Aug-2026 12:03:25 | AFC | Approved | APPR | 24-Aug-2026 13:12:46
192 | 139 | IP23 | PLR | GA | 9002 | dwg | MM-ZTK-1F-IP23-PLR-GA-9002 | IP23 Tie-in Spool GA Drawing at ZWP23 |  |  | R1 | 2026-08-03 | 2026-08-10 | 2026-08-13 | A1 | 2026-08-15 | 2026-08-17 | 2026-08-20 | 2026-08-21 | 2026-07-24 | 2026-08-21 | 2026-09-04 | 2026-09-06 | B1 | 2026-09-10 | 2026-09-13 | 2026-09-17 | 2026-09-18 | 2026-08-20 | 2026-09-18 | 2026-10-02 | 2026-10-04 | C1 | 2026-10-08 | 2026-10-09 | 2026-08-29 | 2026-10-23 |  | 2026-10-09 | 2026-10-23 | 2026-09-07 | 2026-10-23 | 1 | 0.8197% | 0.5738% | 0.8197% | 0.2459% | 0.6557% | 0.8197% | 0.1639% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0.08197% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP23-PLR-GA-9002 | 24-Jul-2026 17:10:41 | MM-ZTK-1F-IP23-PLR-GA-9002 | 20-Aug-2026 07:53:39 | MM-ZTK-1F-IP23-PLR-GA-9002 | 29-Aug-2026 14:09:28 | AFC | Approved | APPR | 07-Sep-2026 11:20:21
193 | 140 | IP23 | PLR | GA | 9003 | dwg | MM-ZTK-1F-IP23-PLR-GA-9003 | IP23 Tie-in Spool GA Drawing at PLEM7 |  |  | R1 | 2026-08-07 | 2026-08-14 | 2026-08-17 | A1 | 2026-08-19 | 2026-08-21 | 2026-08-24 | 2026-08-25 | 2026-07-24 | 2026-08-25 | 2026-09-08 | 2026-09-10 | B1 | 2026-09-14 | 2026-09-17 | 2026-09-21 | 2026-09-22 | 2026-08-20 | 2026-09-22 | 2026-10-06 | 2026-10-08 | C1 | 2026-10-12 | 2026-10-13 | 2026-08-29 | 2026-10-27 |  | 2026-10-13 | 2026-10-27 | 2026-09-07 | 2026-10-27 | 1 | 0.8197% | 0.5738% | 0.8197% | 0.2459% | 0.5738% | 0.8197% | 0.2459% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0.08197% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP23-PLR-GA-9003 | 24-Jul-2026 17:11:05 | MM-ZTK-1F-IP23-PLR-GA-9003 | 20-Aug-2026 07:54:09 | MM-ZTK-1F-IP23-PLR-GA-9003 | 29-Aug-2026 14:09:55 | AFC | Approved | APPR | 07-Sep-2026 11:21:27
194 | [43 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [122 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | bar: 2026-02-06 to 2028-05-26
195 | Isometric: IP23 Riser and Tie-in Spools | [6 empty] | Isometric: IP23 Riser and Tie-in Spools | [164 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | bar: 2026-02-06 to 2028-05-26
196 | 141 | IP23 | PLR | ISO | 9001 | dwg | MM-ZTK-1F-IP23-PLR-ISO-9001 | IP23 Riser Isometric at ZWP23 |  |  | R1 | 2026-06-09 | 2026-06-16 | 2026-06-19 | A1 | 2026-06-21 | 2026-06-23 | 2026-06-26 | 2026-06-27 | 2026-05-26 | 2026-05-26 | 2026-07-11 | 2026-07-13 | B1 | 2026-07-17 | 2026-07-20 | 2026-07-24 | 2026-07-25 | 2026-07-28 | 2026-07-25 | 2026-08-08 | 2026-08-10 | C1 | 2026-08-14 | 2026-08-15 | 2026-08-21 | 2026-08-29 |  | 2026-08-15 | 2026-08-29 |  | 2026-08-29 | 1 | 0.8197% | 0.8197% | 0.6557% | -0.1639% | 0.8197% | 0.6557% | -0.1639% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP23-PLR-ISO-9001 | 26-May-2026 16:51:49 | MM-ZTK-1F-IP23-PLR-ISO-9001 | 28-Jul-2026 09:15:26 | MM-ZTK-1F-IP23-PLR-ISO-9001 | 24-Aug-2026 17:16:57 | AFC | Approved with Comment | AWC | 31-Aug-2026 10:43:34
197 | 142 | IP23 | PLR | ISO | 9002 | dwg | MM-ZTK-1F-IP23-PLR-ISO-9002 | IP23 Tie-in Spool Isometric at ZWP23 |  |  | R1 | 2026-07-27 | 2026-08-03 | 2026-08-06 | A1 | 2026-08-08 | 2026-08-10 | 2026-08-13 | 2026-08-14 | 2026-07-03 | 2026-08-14 | 2026-08-28 | 2026-08-30 | B1 | 2026-09-03 | 2026-09-06 | 2026-09-10 | 2026-09-11 | 2026-08-14 | 2026-09-11 | 2026-09-25 | 2026-09-27 | C1 | 2026-10-01 | 2026-10-02 | 2026-08-28 | 2026-10-16 |  | 2026-10-02 | 2026-10-16 | 2026-09-07 | 2026-10-16 | 1 | 0.8197% | 0.6557% | 0.8197% | 0.1639% | 0.6557% | 0.8197% | 0.1639% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP23-PLR-ISO-9002 | 03-Jul-2026 13:32:51 | MM-ZTK-1F-IP23-PLR-ISO-9002 | 17-Aug-2026 14:48:24 | MM-ZTK-1F-IP23-PLR-ISO-9002 | 28-Aug-2026 18:14:34 | AFC | Approved | APPR | 07-Sep-2026 11:43:57
198 | 143 | IP23 | PLR | ISO | 9003 | dwg | MM-ZTK-1F-IP23-PLR-ISO-9003 | IP23 Tie-in Spool Isometric at PLEM7 |  |  | R1 | 2026-07-31 | 2026-08-07 | 2026-08-10 | A1 | 2026-08-12 | 2026-08-14 | 2026-08-17 | 2026-08-18 | 2026-07-03 | 2026-08-18 | 2026-09-01 | 2026-09-03 | B1 | 2026-09-07 | 2026-09-10 | 2026-09-14 | 2026-09-15 | 2026-08-14 | 2026-09-15 | 2026-09-29 | 2026-10-01 | C1 | 2026-10-05 | 2026-10-06 | 2026-08-28 | 2026-10-20 |  | 2026-10-06 | 2026-10-20 | 2026-09-07 | 2026-10-20 | 1 | 0.8197% | 0.5738% | 0.8197% | 0.2459% | 0.6557% | 0.8197% | 0.1639% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0% | 0% | 0.1639% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4098% | 0% | 0% | 0% | 0.1639% | 0% | 0% | 0.08197% | 0% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | MM-ZTK-1F-IP23-PLR-ISO-9003 | 03-Jul-2026 13:34:16 | MM-ZTK-1F-IP23-PLR-ISO-9003 | 17-Aug-2026 14:49:00 | MM-ZTK-1F-IP23-PLR-ISO-9003 | 28-Aug-2026 18:14:59 | AFC | Approved | APPR | 07-Sep-2026 11:45:05
199 | [44 empty] | 85.74% | 90.98% | 5.246% | 88.2% | 90.98% | 2.787% | Plan Weekly | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.8197% | 1.639% | 0.8197% | 0.8197% | 0.7377% | 4.262% | 4.18% | 5.738% | 7.705% | 4.508% | 3.934% | 4.672% | 4.754% | 4.59% | 4.262% | 4.344% | 5.656% | 5.738% | 3.852% | 2.787% | 3.443% | 2.541% | 1.967% | 1.967% | 2.459% | 1.885% | 1.639% | 1.23% | 1.393% | 0.4918% | 0.9836% | 0.5738% | 0.3279% | 0.4098% | 0.5738% | 0.8197% | 0% | 0.2459% | 0.2459% | 0.3279% | 0.1639% | 0.08197% | 0.08197% | 0.1639% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.23% | 1.639% | 0.8197% | 0.8197% | 4.508% | 4.508% | 0.4098% | 1.967% | 1.967% | 10.49% | 6.393% | 5.574% | 3.77% | 6.148% | 3.525% | 4.098% | 5.738% | 6.393% | 5.328% | 3.115% | 7.049% | 0.9016% | 2.951% | 1.639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.23% | 1.639% | 0.8197% | 0.8197% | 4.508% | 4.508% | 0.4098% | 1.967% | 1.967% | 10.9% | 5.328% | 4.59% | 4.836% | 5% | 5.082% | 4.344% | 5.656% | 5.574% | 3.852% | 2.787% | 3.443% | 2.541% | 1.967% | 1.967% | 2.459% | 1.885% | 1.639% | 1.23% | 1.393% | 0.4918% | 0.9836% | 0.5738% | 0.3279% | 0.4098% | 0.5738% | 0.8197% | 0% | 0.2459% | 0.2459% | 0.3279% | 0.1639% | 0.08197% | 0.08197% | 0.1639% | 0.1639% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[51 empty] | Plan Cumm | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.8197% | 2.459% | 3.279% | 4.098% | 4.836% | 9.098% | 13.28% | 19.02% | 26.72% | 31.23% | 35.16% | 39.84% | 44.59% | 49.18% | 53.44% | 57.79% | 63.44% | 69.18% | 73.03% | 75.82% | 79.26% | 81.8% | 83.77% | 85.74% | 88.2% | 90.08% | 91.72% | 92.95% | 94.34% | 94.84% | 95.82% | 96.39% | 96.72% | 97.13% | 97.7% | 98.52% | 98.52% | 98.77% | 99.02% | 99.34% | 99.51% | 99.59% | 99.67% | 99.84% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.23% | 2.869% | 3.689% | 4.508% | 9.016% | 13.52% | 13.93% | 15.9% | 17.87% | 28.36% | 34.75% | 40.33% | 44.1% | 50.25% | 53.77% | 57.87% | 63.61% | 70% | 75.33% | 78.44% | 85.49% | 86.39% | 89.34% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.23% | 2.869% | 3.689% | 4.508% | 9.016% | 13.52% | 13.93% | 15.9% | 17.87% | 28.77% | 34.1% | 38.69% | 43.52% | 48.52% | 53.61% | 57.95% | 63.61% | 69.18% | 73.03% | 75.82% | 79.26% | 81.8% | 83.77% | 85.74% | 88.2% | 90.08% | 91.72% | 92.95% | 94.34% | 94.84% | 95.82% | 96.39% | 96.72% | 97.13% | 97.7% | 98.52% | 98.52% | 98.77% | 99.02% | 99.34% | 99.51% | 99.59% | 99.67% | 99.84% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[51 empty] | Actual Weekly | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.23% | 1.639% | 0.8197% | 0.8197% | 4.508% | 4.508% | 0.4098% | 1.967% | 1.967% | 10.49% | 6.393% | 5.574% | 3.77% | 6.148% | 3.525% | 4.098% | 5.738% | 6.393% | 5.328% | 3.115% | 7.049% | 0.9016% | 2.951% | 1.639% | 0% | [24 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[7 empty] | 2026-10-09 | Step | [10 empty] | Plan | Actual | Dev | [29 empty] | Actual Cumm | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.23% | 2.869% | 3.689% | 4.508% | 9.016% | 13.52% | 13.93% | 15.9% | 17.87% | 28.36% | 34.75% | 40.33% | 44.1% | 50.25% | 53.77% | 57.87% | 63.61% | 70% | 75.33% | 78.44% | 85.49% | 86.39% | 89.34% | 90.98% | 90.98% | [24 empty] | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98% | 90.98%
[7 empty] | IFR | Issued For Review | [10 empty] | 137 | 135 | 2 | [29 empty] | Forecast Weekly | 2026-02-06: 0%; 2026-02-13: 0%; 2026-02-20: 0%; 2026-02-27: 0%; 2026-03-06: 0%; 2026-03-13: 0%; 2026-03-20: 0%; 2026-03-27: 0%; 2026-04-03: 0%; 2026-04-10: 0%; 2026-04-17: 0%; 2026-04-24: 1.23%; 2026-05-01: 1.639%; 2026-05-08: 0.8197%; 2026-05-15: 0.8197%; 2026-05-22: 4.508%; 2026-05-29: 4.508%; 2026-06-05: 0.4098%; 2026-06-12: 1.967%; 2026-06-19: 1.967%; 2026-06-26: 10.9%; 2026-07-03: 5.328%; 2026-07-10: 4.59%; 2026-07-17: 4.836%; 2026-07-24: 5%; 2026-07-31: 5.082%; 2026-08-07: 4.344%; 2026-08-14: 5.656%; 2026-08-21: 5.574%; 2026-08-28: 3.852%; 2026-09-04: 2.787%; 2026-09-11: 3.443%; 2026-09-18: 2.541%; 2026-09-25: 1.967%; 2026-10-02: 1.967%; 2026-10-09: 2.459%; 2026-10-16: 1.885%; 2026-10-23: 1.639%; 2026-10-30: 1.23%; 2026-11-06: 1.393%; 2026-11-13: 0.4918%; 2026-11-20: 0.9836%; 2026-11-27: 0.5738%; 2026-12-04: 0.3279%; 2026-12-11: 0.4098%; 2026-12-18: 0.5738%; 2026-12-25: 0.8197%; 2027-01-01: 0%; 2027-01-08: 0.2459%; 2027-01-15: 0.2459%; 2027-01-22: 0.3279%; 2027-01-29: 0.1639%; 2027-02-05: 0.08197%; 2027-02-12: 0.08197%; 2027-02-19: 0.1639%; 2027-02-26: 0.1639%; 2027-03-05: 0%; 2027-03-12: 0%; 2027-03-19: 0%; 2027-03-26: 0%
[7 empty] | IFA | Issued For Approval | [10 empty] | 111 | 127 | -16 | [29 empty] | Forecast Cumm | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.23% | 2.869% | 3.689% | 4.508% | 9.016% | 13.52% | 13.93% | 15.9% | 17.87% | 28.77% | 34.1% | 38.69% | 43.52% | 48.52% | 53.61% | 57.95% | 63.61% | 69.18% | 73.03% | 75.82% | 79.26% | 81.8% | 83.77% | 85.74% | 88.2% | 90.08% | 91.72% | 92.95% | 94.34% | 94.84% | 95.82% | 96.39% | 96.72% | 97.13% | 97.7% | 98.52% | 98.52% | 98.77% | 99.02% | 99.34% | 99.51% | 99.59% | 99.67% | 99.84% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[7 empty] | IFC | Issued for Construction | [10 empty] | 121 | 128 | -7 | [30 empty] | 2026-07-03: -0.4098%; 2026-07-10: 0.4918%; 2026-07-17: -0.4918%
[7 empty] | AFC | Approved for Construction | [10 empty] | 107 | 107 | 0
[7 empty] | 2026-10-16 | Step | [10 empty] | Plan | Actual | Dev
[7 empty] | IFR | Issued For Review | [10 empty] | 137 | 135 | 2
[7 empty] | IFA | Issued For Approval | [10 empty] | 113 | 127 | -14
[7 empty] | IFC | Issued for Construction | [10 empty] | 126 | 128 | -2
[7 empty] | AFC | Approved for Construction | [10 empty] | 114 | 107 | 7
[19 empty] | 2026-10-02 |  | 2026-10-09
[8 empty] | Step | [10 empty] | Prev Week | This Week | Todate
[7 empty] | IFR | Issued For Review | [10 empty] | 135 | 0 | 135
[7 empty] | IFA | Issued For Approval | [10 empty] | 127 | 0 | 127
[7 empty] | IFC | Issued for Construction | [10 empty] | 128 | 0 | 128
[7 empty] | AFC | Approved for Construction | [10 empty] | 107 | 0 | 107
[8 empty] | Step | [10 empty] | Total | Progress | Rem | [6 empty] | %
[7 empty] | IFR | Issued For Review | [10 empty] | 143 | 135 | 8 | [6 empty] | 94.41%
[7 empty] | IFA | Issued For Approval | [10 empty] | 143 | 127 | 16 | [6 empty] | 88.81%
[7 empty] | IFC | Issued for Construction | [10 empty] | 143 | 128 | 15 | [6 empty] | 89.51%
[7 empty] | AFC | Approved for Construction | [10 empty] | 143 | 107 | 36 | [6 empty] | 74.83%

## MS Project
From File: | 26032 Zawtika 1F Detailed Engineering Design11-3
| Document Number | Task Name | Duration | Start | Finish | Predecessors
1 |  | Zawtika Detailed Engineering Design | 182.75 days | 2026-03-16 | 2026-11-25
2 |  | Project Initiation | 5 days | 2026-03-16 | 2026-03-20
3 |  | Basis of Design | 51.75 days | 2026-03-23 | 2026-06-02
4 | MM-ZTK-1F-IPX-PLR-BOD-9001 | Pipeline and Riser Design Basis and Design Criteria | 40 days | 2026-03-23 | 2026-04-11 | 2
5 | MM-ZTK-1F-IPX-PLR-BOD-9002 | Seismic Consideration for Subsea Pipeline in Seismic Hazardous Area | 40 days | 2026-03-23 | 2026-04-11 | 2
6 | MM-ZTK-1F-IPX-PRO-BOD-9001 | Design Basis for Pipeline and Riser Flow Assurance Studies | 15 days | 2026-05-12 | 2026-05-04 | 9
7 |  | General Report | 93.75 days | 2026-03-23 | 2026-07-30
8 | MM-ZTK-1F-IPX-PLR-RPT-9001 | Pipeline Wall Thickness Analysis Report (IP20, IP21, IP22, IP23) | 35 days | 2026-03-23 | 2026-04-26 | 4SS
9 | MM-ZTK-1F-IPX-PLR-RPT-9002 | Pipeline On-Bottom Stability Analysis (IP20, IP21, IP22, IP23) | 8 days | 2026-04-30 | 2026-05-04
10 | MM-ZTK-1F-IPX-PLR-RPT-9003 | Pipeline Fault Crossing Analysis | 15 days | 2026-05-12 | 2026-05-20 | 9
11 | MM-ZTK-1F-IPX-PLR-RPT-9004 | Pipeline External Anti-Corrosion Coating and Cathodic Protection Design (IP20, IP21, IP22, IP23) | 10 days | 2026-03-30 | 2026-05-08 | 4SS+5 days
12 | MM-ZTK-1F-IPX-PLR-RPT-9005 | Pipeline End Expansion Analysis (IP20, IP21, IP22, IP23) | 7 days | 2026-04-30 | 2026-05-04 | 9SS
13 | MM-ZTK-1F-IPX-PLR-RPT-9006 | Pipeline Allowable Free Span Calculation (IP20, IP21, IP22, IP23) | 7 days | 2026-05-11 | 2026-05-20
14 | MM-ZTK-1F-IPX-PLR-RPT-9007 | Pipeline-Soil Interaction Study (IP20, IP21, IP22, IP23) | 10 days | 2026-03-30 | 2026-04-10 | 8SS+5 days
15 | MM-ZTK-1F-IPX-PLR-RPT-9008 | Riser Span Analysis (IP20, IP21, IP22, IP23) | 10 days | 2026-04-30 | 2026-05-04
16 | MM-ZTK-1F-IPX-PLR-RPT-9009 | Riser Hanger Flange Design Report (IP20, IP21, IP22, IP23) | 15 days | 2026-07-09 | 2026-07-30 | 160FS+20 days
17 | MM-ZTK-1F-IPX-PRO-RPT-9001 | Pipeline Flow Assurance - Steady State Analysis (IP20, IP21, IP22, IP23) | 20 days | 2026-05-14 | 2026-06-11
18 | MM-ZTK-1F-IPX-PRO-RPT-9002 | Pipeline Flow Assurance -Transient Analysis (IP20, IP21, IP22, IP23) | 30 days | 2026-06-04 | 2026-07-16 | 17SS+15 days
19 |  | General Drawings | 92.75 days | 2026-04-13 | 2026-08-19
20 | MM-ZTK-1F-IPX-PLR-DWG-9000 | Pipeline Drawing Index | 3 days | 2026-05-14 | 2026-05-28 | 28
21 | MM-ZTK-1F-IPX-PLR-DWG-9001 | Overall Field Layout | 5 days | 2026-05-18 | 2026-05-25
22 | MM-ZTK-1F-IPX-PLR-DWG-9002 | Field Joint Coating Details Drawing | 5 days | 2026-05-13 | 2026-05-18 | 11
23 | MM-ZTK-1F-IPX-PLR-DWG-9003 | Pipeline Body and Coating Details Drawing | 4 days | 2026-05-11 | 2026-05-15 | 9SS+7 days
24 | MM-ZTK-1F-IPX-PLR-DWG-9004 | Pipeline Hot Induction Bend Details Drawing | 4 days | 2026-05-13 | 2026-05-19
25 | MM-ZTK-1F-IPX-PLR-DWG-9005 | Pipeline Anode Details Drawing | 5 days | 2026-05-04 | 2026-05-11
26 | MM-ZTK-1F-IPX-PLR-DWG-9006 | Riser Hanger Flange Drawing (NPS18) | 5 days | 2026-07-09 | 2026-07-16 | 16SS
27 | MM-ZTK-1F-IPX-PLR-DWG-9007 | Riser Hanger Flange Drawing (NPS10) | 5 days | 2026-07-16 | 2026-07-23 | 26
28 | MM-ZTK-1F-IPX-PLR-DWG-9008 | Flange Protector Details Drawing (NPS18) | 10 days | 2026-07-31 | 2026-08-14 | 173
29 |  | Material Take-Off | 14 days | 2026-05-12 | 2026-06-01
30 | MM-ZTK-1F-IPX-PLR-MTO-9001 | Material Take Off for 18" LSAW Line Pipe and Bend Mother-Pipe | 4 days | 2026-05-12 | 2026-05-18
31 | MM-ZTK-1F-IPX-PLR-MTO-9002 | Material Take Off for 10" Seamless Line Pipe and Bend Mother-Pipe | 3 days | 2026-05-14 | 2026-05-19 | 30SS+2 days
32 | MM-ZTK-1F-IPX-PLR-MTO-9003 | Material Take Off for Concrete Weight Coating | 3 days | 2026-05-26 | 2026-05-29 | 9SS+5 days,169
33 | MM-ZTK-1F-IPX-PLR-MTO-9004 | Material Take Off for Hot Induction Bends | 3 days | 2026-05-19 | 2026-05-22 | 36
34 | MM-ZTK-1F-IPX-PLR-MTO-9005 | Material Take Off for Pipeline/Riser External Anti-Corrosion Coating | 3 days | 2026-05-22 | 2026-05-27 | 33
35 | MM-ZTK-1F-IPX-PLR-MTO-9006 | Material Take Off for Sacrificial Bracelet Anode | 4 days | 2026-05-12 | 2026-05-18
36 | MM-ZTK-1F-IPX-PLR-MTO-9007 | Material Take Off for Flanges, Fittings, Gaskets and Fasteners | 3 days | 2026-05-14 | 2026-05-19
37 | MM-ZTK-1F-IPX-PLR-MTO-9008 | Material Take Off for Field Joint Coating | 5 days | 2026-05-25 | 2026-06-01 | 35FS+5 days
38 |  | Technical Bid Evaluation | 25 days | 2026-06-04 | 2026-07-09
39 | MM-ZTK-1F-IPX-PLR-TBE-9001 | Technical Bid Evaluation for 18" LSAW Line Pipe and Bend Mother-Pipe | 5 days | 2026-06-04 | 2026-06-11 | 51FS+10 days
40 | MM-ZTK-1F-IPX-PLR-TBE-9002 | Technical Bid Evaluation for 10" Seamless Line Pipe and Bend Mother-Pipe | 5 days | 2026-06-05 | 2026-06-12 | 52FS+10 days
41 | MM-ZTK-1F-IPX-PLR-TBE-9003 | Technical Bid Evaluation for Concrete Weight Coating | 5 days | 2026-06-18 | 2026-06-25 | 53FS+10 days
42 | MM-ZTK-1F-IPX-PLR-TBE-9004 | Technical Bid Evaluation for Hot Induction Bends | 5 days | 2026-06-05 | 2026-06-12 | 51FS+10 days,52FS+10 days
43 | MM-ZTK-1F-IPX-PLR-TBE-9005 | Technical Bid Evaluation for Pipeline/Riser External Anti-Corrosion Coating | 5 days | 2026-06-18 | 2026-06-25 | 53FS+10 days
44 | MM-ZTK-1F-IPX-PLR-TBE-9006 | Technical Bid Evaluation for Sacrificial Bracelet Anode | 5 days | 2026-06-11 | 2026-06-18 | 55FS+10 days
45 | MM-ZTK-1F-IPX-PLR-TBE-9007 | Technical Bid Evaluation for Flanges | 5 days | 2026-06-17 | 2026-06-24 | 56FS+10 days,40
46 | MM-ZTK-1F-IPX-PLR-TBE-9008 | Technical Bid Evaluation for Fittings | 5 days | 2026-07-02 | 2026-07-09 | 57FS+10 days,49
47 | MM-ZTK-1F-IPX-PLR-TBE-9009 | Technical Bid Evaluation for Gaskets | 5 days | 2026-06-24 | 2026-07-01 | 58FS+10 days,45
48 | MM-ZTK-1F-IPX-PLR-TBE-9010 | Technical Bid Evaluation for Fasteners | 5 days | 2026-07-02 | 2026-07-09 | 59FS+10 days,49
49 | MM-ZTK-1F-IPX-PLR-TBE-9011 | Technical Bid Evaluation for Field Joint Coating | 5 days | 2026-06-25 | 2026-07-02 | 60FS+10 days,45
50 |  | Material Requisition Package | 18 days | 2026-05-18 | 2026-06-11
51 | MM-ZTK-1F-IPX-PLR-MR-9001 | Material Requisition For 18" LSAW Line Pipe, Bend Mother Pipe And Hot Induction Bend | 3 days | 2026-05-18 | 2026-05-21 | 30,62
52 | MM-ZTK-1F-IPX-PLR-MR-9002 | Material Requisition For 10” SMLS Line Pipe, Bend Mother Pipe And Hot Induction Bend | 3 days | 2026-05-19 | 2026-05-22 | 31,63
53 | MM-ZTK-1F-IPX-PLR-MR-9003 | Material Requisition For Pipeline External Anticorrosion Coating & Concrete Weight Coating & Bend Coating & Riser/Spool External Anticorrosion Coating | 3 days | 2026-06-01 | 2026-06-04 | 32,64,66,72,33,34,22
54 | MM-ZTK-1F-IPX-PLR-MR-9004 | Material Requisition For Neoprene Coating For Riser Splash Zone | 3 days | 2026-05-29 | 2026-06-03 | 34,66
55 | MM-ZTK-1F-IPX-PLR-MR-9005 | Material Requisition for Sacrificial Bracelet Anodes | 3 days | 2026-05-25 | 2026-05-28 | 35,67
56 | MM-ZTK-1F-IPX-PLR-MR-9006 | Material Requisition for Flanges | 3 days | 2026-05-29 | 2026-06-03 | 36,68
57 | MM-ZTK-1F-IPX-PLR-MR-9007 | Material Requisition for Fittings | 3 days | 2026-05-29 | 2026-06-03 | 36,68
58 | MM-ZTK-1F-IPX-PLR-MR-9008 | Material Requisition for Gaskets | 3 days | 2026-05-29 | 2026-06-03 | 36,68
59 | MM-ZTK-1F-IPX-PLR-MR-9009 | Material Requisition for Fasteners | 3 days | 2026-05-29 | 2026-06-03 | 36,68
60 | MM-ZTK-1F-IPX-PLR-MR-9010 | Material Requisition for Field Joint Coating | 3 days | 2026-06-08 | 2026-06-11 | 37,69,22
61 |  | Particular Specification | 46 days | 2026-05-01 | 2026-07-06
62 | MM-ZTK-1F-IPX-PLR-SPE-9001 | Project Particular Specification & Datasheet for 18" LSAW Line Pipe and Bend Mother-Pipe | 5 days | 2026-05-01 | 2026-05-08
63 | MM-ZTK-1F-IPX-PLR-SPE-9002 | Project Particular Specification & Datasheet for 10" Seamless Line Pipe and Bend Mother-Pipe | 5 days | 2026-05-01 | 2026-05-08 | 62SS
64 | MM-ZTK-1F-IPX-PLR-SPE-9003 | Project Particular Specification & Datasheet for Concrete Weight Coating | 5 days | 2026-05-08 | 2026-05-15 | 63
65 | MM-ZTK-1F-IPX-PLR-SPE-9004 | Project Particular Specification & Datasheet for Hot Induction Bends | 5 days | 2026-05-15 | 2026-05-22 | 64
66 | MM-ZTK-1F-IPX-PLR-SPE-9005 | Project Particular Specification & Datasheet for Pipeline/Riser External Anti-Corrosion Coating | 5 days | 2026-05-22 | 2026-05-29 | 65
67 | MM-ZTK-1F-IPX-PLR-SPE-9006 | Project Particular Specification & Datasheet for Sacrificial Bracelet Anode | 5 days | 2026-05-18 | 2026-05-25
68 | MM-ZTK-1F-IPX-PLR-SPE-9007 | Project Particular Specification & Datasheet for Flanges, Fittings, Gaskets and Fasteners | 5 days | 2026-05-22 | 2026-05-29 | 66SS
69 | MM-ZTK-1F-IPX-PLR-SPE-9008 | Project Particular Specification & Datasheet for Field Joint Coating | 5 days | 2026-06-01 | 2026-06-08 | 72
70 | MM-ZTK-1F-IPX-PLR-SPE-9009 | Project Particular Specification & Datasheet for Pre-commissioning | 5 days | 2026-06-29 | 2026-07-06 | 71FS+5 days
71 | MM-ZTK-1F-IPX-PLR-SPE-9010 | Project Particular Specification & Datasheet for Welding of Pipeline according to API 1104 | 5 days | 2026-06-15 | 2026-06-22 | 69FS+5 days
72 | MM-ZTK-1F-IPX-PLR-SPE-9011 | Project Particular Specification & Datasheet for Bend Anti-Corrosion Coating | 5 days | 2026-05-25 | 2026-06-01 | 67
73 |  | IP20 Pipeline Design from ZWP20 to ZWP16 | 103 days | 2026-04-20 | 2026-09-10
74 |  | Report: IP20 Pipeline | 73 days | 2026-04-20 | 2026-07-30
75 | MM-ZTK-1F-IP20-PLR-RPT-9001 | IP20 Pipeline Routing Study and Design | 15 days | 2026-04-20 | 2026-04-05
76 | MM-ZTK-1F-IP20-PLR-RPT-9002 | IP20 Pipeline On-Bottom Roughness and In-place Stress Analysis | 7 days | 2026-05-20 | 2026-05-29 | 9,13
77 | MM-ZTK-1F-IP20-PLR-RPT-9003 | IP20 Pipeline Lateral Buclking Analysis | 10 days | 2026-06-11 | 2026-06-25 | 160
78 | MM-ZTK-1F-IP20-PLR-RPT-9004 | IP20 Pipeline Walking Analysis | 10 days | 2026-07-16 | 2026-07-30 | 18
79 |  | Report: IP20 Risers and Tie-In Spools | 88 days | 2026-05-11 | 2026-09-10
80 | MM-ZTK-1F-IP20-PLR-RPT-9005 | IP20 at ZWP20 : Riser and Tie-In Spool Stress Analysis | 5 days | 2026-05-11 | 2026-05-18
81 | MM-ZTK-1F-IP20-PLR-RPT-9006 | IP20 at ZWP16 : Riser and Tie-In Spool Stress Analysis | 5 days | 2026-05-18 | 2026-05-25 | 80
82 | MM-ZTK-1F-IP20-PLR-RPT-9007 | IP20 at ZWP20 : Riser and Tie-In Spool Seismic Analysis | 12 days | 2026-08-17 | 2026-09-02 | 163
83 | MM-ZTK-1F-IP20-PLR-RPT-9008 | IP20 at ZWP16 : Riser and Tie-In Spool Seismic Analysis | 6 days | 2026-09-02 | 2026-09-10 | 82
84 | Seismic-Check | Pipeline Seismic Check | 21 days | 2026-05-12 | 2026-06-10
85 | MM-ZTK-1F-IP20-PLR-RPT-9009 | IP20 Pipeline Seismic Analysis | 12 days | 2026-06-10 | 2026-06-26 | 84
86 |  | Drawings: IP20 Pipeline | 57 days | 2026-04-20 | 2026-07-08
87 | MM-ZTK-1F-IP20-PLR-DWG-9001 | IP20 Pipeline Route Drawing from ZWP20 to ZWP16 | 18 days | 2026-04-20 | 2026-04-05 | 75SS
88 | MM-ZTK-1F-IP20-PLR-DWG-9002 | IP20 Pipeline Alignment Sheets: ZWP20 to ZWP16 | 5 days | 2026-06-25 | 2026-07-02 | 13,77
89 | MM-ZTK-1F-IP20-PLR-DWG-9003 | IP20 Pipeline Schematic Diagram | 4 days | 2026-07-02 | 2026-07-08 | 88
90 | MM-ZTK-1F-IP20-PLR-DWG-9004 | IP20 Pipeline Platform Approach at ZWP20 | 4 days | 2026-05-04 | 2026-05-08 | 87SS+10 days
91 | MM-ZTK-1F-IP20-PLR-DWG-9005 | IP20 Pipeline Platform Approach at ZWP16 | 4 days | 2026-05-08 | 2026-05-14 | 90
92 |  | GA: IP20 Risers and Tie-in Spools | 50 days | 2026-04-20 | 2026-06-29
93 | MM-ZTK-1F-IP20-PLR-GA-9001 | Riser GA Drawings at ZWP20 | 16 days | 2026-04-20 | 2026-05-12 | 75SS
94 | MM-ZTK-1F-IP20-PLR-GA-9002 | IP20 Tie-in Spool GA Drawing at ZWP20 | 5 days | 2026-06-15 | 2026-06-22 | 98
95 | MM-ZTK-1F-IP20-PLR-GA-9003 | IP20 Tie-in Spool GA Drawing at ZWP16 | 5 days | 2026-06-22 | 2026-06-29 | 94
96 |  | Isometric: IP20 Risers and Tie-in Spools | 13 days | 2026-06-03 | 2026-06-22
97 | MM-ZTK-1F-IP20-PLR-ISO-9001 | IP20 Riser Isometric at ZWP20 | 4 days | 2026-05-03 | 2026-05-09 | 171FS+10 days
98 | MM-ZTK-1F-IP20-PLR-ISO-9002 | IP20 Tie-in Spool Isometric at ZWP20 | 5 days | 2026-06-08 | 2026-06-15 | 81FS+10 days
99 | MM-ZTK-1F-IP20-PLR-ISO-9003 | IP20 Tie-in Spool Isometric at ZWP16 | 5 days | 2026-06-15 | 2026-06-22 | 98
100 |  | IP21 Pipeline Design from ZWP21 to PLEM14 | 116 days | 2026-04-27 | 2026-10-06
101 |  | Report: IP21 Pipeline | 75 days | 2026-04-27 | 2026-08-10
102 | MM-ZTK-1F-IP21-PLR-RPT-9001 | IP21 Pipeline Routing Study and Design | 5 days | 2026-03-27 | 2026-04-09 | 113SS
103 | MM-ZTK-1F-IP21-PLR-RPT-9002 | IP21 Pipeline On-Bottom Roughness and In-place Stress Analysis | 5 days | 2026-05-29 | 2026-06-05 | 76
104 | MM-ZTK-1F-IP21-PLR-RPT-9003 | IP21 Pipeline Lateral Buclking Analysis | 10 days | 2026-06-25 | 2026-07-09 | 77
105 | MM-ZTK-1F-IP21-PLR-RPT-9004 | IP21 Pipeline Walking Analysis | 7 days | 2026-07-30 | 2026-08-10 | 78
106 |  | Report: IP21 Risers and Tie-In Spools | 103 days | 2026-05-14 | 2026-10-06
107 | MM-ZTK-1F-IP21-PLR-RPT-9005 | IP21 at ZWP21 : Riser and Tie-In Spool Stress Analysis | 5 days | 2026-05-14 | 2026-05-21 | 80SS+3 days
108 | MM-ZTK-1F-IP21-PLR-RPT-9006 | IP21 at PLEM14 : Riser and Tie-In Spool Stress Analysis | 5 days | 2026-05-21 | 2026-05-28 | 107
109 | MM-ZTK-1F-IP21-PLR-RPT-9007 | IP21 at ZWP21 : Riser and Tie-In Spool Seismic Analysis | 12 days | 2026-09-10 | 2026-09-28 | 83
110 | MM-ZTK-1F-IP21-PLR-RPT-9008 | IP21 at PLEM14 : Riser and Tie-In Spool Seismic Analysis | 6 days | 2026-09-28 | 2026-10-06 | 109
111 | MM-ZTK-1F-IP21-PLR-RPT-9009 | IP21 Pipeline Seismic Analysis | 12 days | 2026-06-26 | 2026-07-14 | 85
112 |  | Drawings: IP21 Pipeline | 62 days | 2026-04-27 | 2026-07-22
113 | MM-ZTK-1F-IP21-PLR-DWG-9001 | IP21 Pipeline Route Drawing from ZWP21 to PLEM14 | 12 days | 2026-03-27 | 2026-04-17 | 87SS+5 days
114 | MM-ZTK-1F-IP21-PLR-DWG-9002 | IP21 Pipeline Alignment Sheets: ZWP21 to PLEM14 | 5 days | 2026-07-09 | 2026-07-16 | 13104
115 | MM-ZTK-1F-IP21-PLR-DWG-9003 | IP21 Pipeline Schematic Diagram | 4 days | 2026-07-16 | 2026-07-22 | 114
116 | MM-ZTK-1F-IP21-PLR-DWG-9004 | IP21 Pipeline Platform Approach at ZWP21 | 4 days | 2026-04-13 | 2026-05-04 | 113
117 | MM-ZTK-1F-IP21-PLR-DWG-9005 | IP21 Pipeline PLEM Approach at PLEM14 | 4 days | 2026-04-19 | 2026-05-04 | 116
118 |  | GA: IP21 Risers and Tie-in Spools | 53 days | 2026-04-27 | 2026-07-09
119 | MM-ZTK-1F-IP21-PLR-GA-9001 | Riser GA Drawings at ZWP21 | 10 days | 2026-04-27 | 2026-05-11 | 93SS+5 days
120 | MM-ZTK-1F-IP21-PLR-GA-9002 | IP21 Tie-in Spool GA Drawing at ZWP21 | 4 days | 2026-06-29 | 2026-07-03 | 95
121 | MM-ZTK-1F-IP21-PLR-GA-9003 | IP21 Tie-in Spool GA Drawing at PLEM14 | 4 days | 2026-07-03 | 2026-07-09 | 120
122 |  | Isometric: IP21 Risers and Tie-in Spools | 12 days | 2026-06-16 | 2026-07-02
123 | MM-ZTK-1F-IP21-PLR-ISO-9001 | IP21 Riser Isometric at ZWP21 | 4 days | 2026-05-16 | 2026-05-23 | 97FS+5 days
124 | MM-ZTK-1F-IP21-PLR-ISO-9002 | IP21 Tie-in Spool Isometric at ZWP21 | 4 days | 2026-06-22 | 2026-06-26 | 99
125 | MM-ZTK-1F-IP21-PLR-ISO-9003 | IP21 Tie-in Spool Isometric at PLEM14 | 4 days | 2026-06-26 | 2026-07-02 | 124
126 |  | IP22 Pipeline Design from ZWP22 to ZWP8 | 130 days | 2026-05-01 | 2026-10-30
127 |  | Report: IP22 Pipeline | 72 days | 2026-05-11 | 2026-08-19
128 | MM-ZTK-1F-IP22-PLR-RPT-9001 | IP22 Pipeline Routing Study and Design | 5 days | 2026-05-11 | 2026-05-18 | 139SS+5 days
129 | MM-ZTK-1F-IP22-PLR-RPT-9002 | IP22 Pipeline On-Bottom Roughness and In-place Stress Analysis | 5 days | 2026-06-05 | 2026-06-12 | 103
130 | MM-ZTK-1F-IP22-PLR-RPT-9003 | IP22 Pipeline Lateral Buclking Analysis | 10 days | 2026-07-09 | 2026-07-23 | 104
131 | MM-ZTK-1F-IP22-PLR-RPT-9004 | IP22 Pipeline Walking Analysis | 7 days | 2026-08-10 | 2026-08-19 | 105
132 |  | Report: IP22 Risers and Tie-in Spools | 114 days | 2026-05-25 | 2026-10-30
133 | MM-ZTK-1F-IP22-PLR-RPT-9005 | IP22 at ZWP22 : Riser and Tie-In Spool Stress Analysis | 5 days | 2026-05-25 | 2026-06-01 | 81
134 | MM-ZTK-1F-IP22-PLR-RPT-9006 | IP22 at ZWP8 : Riser and Tie-In Spool Stress Analysis | 5 days | 2026-06-01 | 2026-06-08 | 133
135 | MM-ZTK-1F-IP22-PLR-RPT-9007 | IP22 at ZWP22 : Riser and Tie-In Spool Seismic Analysis | 12 days | 2026-10-06 | 2026-10-22 | 110
136 | MM-ZTK-1F-IP22-PLR-RPT-9008 | IP22 at ZWP8 : Riser and Tie-In Spool Seismic Analysis | 6 days | 2026-10-22 | 2026-10-30 | 135
137 | MM-ZTK-1F-IP22-PLR-RPT-9009 | IP22 Pipeline Seismic Analysis | 12 days | 2026-07-14 | 2026-07-30 | 111
138 |  | Drawings: IP22 Pipeline | 67 days | 2026-05-04 | 2026-08-05
139 | MM-ZTK-1F-IP22-PLR-DWG-9001 | IP22 Pipeline Route Drawing from ZWP22 to ZWP8 | 5 days | 2026-04-04 | 2026-04-17 | 113SS+5 days
140 | MM-ZTK-1F-IP22-PLR-DWG-9002 | IP22 Pipeline Alignment Sheets: ZWP22 to ZWP8 | 5 days | 2026-07-23 | 2026-07-30 | 13130
141 | MM-ZTK-1F-IP22-PLR-DWG-9003 | IP22 Pipeline Schematic Diagram | 4 days | 2026-07-30 | 2026-08-05 | 140
142 | MM-ZTK-1F-IP22-PLR-DWG-9004 | IP22 Pipeline Platform Approach at ZWP22 | 4 days | 2026-05-11 | 2026-05-15 | 139
143 | MM-ZTK-1F-IP22-PLR-DWG-9005 | IP22 Pipeline Platform Approach at ZWP8 | 4 days | 2026-05-15 | 2026-05-21 | 142
144 |  | GA: IP22 Risers and Tie-in Spools | 57 days | 2026-05-01 | 2026-07-21
145 | MM-ZTK-1F-IP22-PLR-GA-9001 | Riser GA Drawings at ZWP22 | 4 days | 2026-05-01 | 2026-05-07 | 119SS+4 days
146 | MM-ZTK-1F-IP22-PLR-GA-9002 | IP22 Tie-in Spool GA Drawing at ZWP22 | 4 days | 2026-07-09 | 2026-07-15 | 121
147 | MM-ZTK-1F-IP22-PLR-GA-9003 | IP22 Tie-in Spool GA Drawing at ZWP8 | 4 days | 2026-07-15 | 2026-07-21 | 146
148 |  | Isometric: IP22 Risers and Tie-in Spools | 16 days | 2026-06-22 | 2026-07-14
149 | MM-ZTK-1F-IP22-PLR-ISO-9001 | IP22 Riser Isometric at ZWP22 | 4 days | 2026-06-22 | 2026-06-26 | 123
150 | MM-ZTK-1F-IP22-PLR-ISO-9002 | IP22 Tie-in Spool Isometric at ZWP22 | 4 days | 2026-07-02 | 2026-07-08 | 125
151 | MM-ZTK-1F-IP22-PLR-ISO-9003 | IP22 Tie-in Spool Isometric at ZWP8 | 4 days | 2026-07-08 | 2026-07-14 | 150
152 |  | IP23 Pipeline Design from ZWP23 to PLEM7 | 144 days | 2026-05-07 | 2026-11-25
153 |  | Report: IP23 Pipeline | 88 days | 2026-05-08 | 2026-09-09
154 | MM-ZTK-1F-IP23-PLR-RPT-9001 | IP23 Pipeline Routing Study and Design | 5 days | 2026-05-08 | 2026-05-15 | 165SS+1 day
155 | MM-ZTK-1F-IP23-PLR-RPT-9002 | IP23 Pipeline On-Bottom Roughness and In-place Stress Analysis | 5 days | 2026-06-12 | 2026-06-19 | 129
156 | MM-ZTK-1F-IP23-PLR-RPT-9003 | IP23 Pipeline Lateral Buclking Analysis | 10 days | 2026-07-23 | 2026-08-06 | 130
157 | MM-ZTK-1F-IP23-PLR-RPT-9004 | IP23 Pipeline Walking Analysis | 15 days | 2026-08-19 | 2026-09-09 | 131
158 |  | Report: IP23 Risers and Tie-in Spools | 129 days | 2026-05-28 | 2026-11-25
159 | MM-ZTK-1F-IP23-PLR-RPT-9005 | IP23 at ZWP23 : Riser and Tie-In Spool Stress Analysis | 5 days | 2026-05-28 | 2026-06-04 | 108
160 | MM-ZTK-1F-IP23-PLR-RPT-9006 | IP23 at PLEM7 : Riser and Tie-In Spool Stress Analysis | 5 days | 2026-06-04 | 2026-06-11 | 159
161 | MM-ZTK-1F-IP23-PLR-RPT-9007 | IP23 at ZWP23 : Riser and Tie-In Spool Seismic Analysis | 12 days | 2026-10-30 | 2026-11-17 | 136
162 | MM-ZTK-1F-IP23-PLR-RPT-9008 | IP23 at PLEM7 : Riser and Tie-In Spool Seismic Analysis | 6 days | 2026-11-17 | 2026-11-25 | 161
163 | MM-ZTK-1F-IP23-PLR-RPT-9009 | IP23 Pipeline Seismic Analysis | 12 days | 2026-07-30 | 2026-08-17 | 137
164 |  | Drawings: IP23 Pipeline | 74 days | 2026-05-07 | 2026-08-19
165 | MM-ZTK-1F-IP23-PLR-DWG-9001 | IP23 Pipeline Route Drawing from ZWP23 to PLEM7 | 5 days | 2026-04-07 | 2026-04-27 | 139SS+3 days
166 | MM-ZTK-1F-IP23-PLR-DWG-9002 | IP23 Pipeline Alignment Sheets: ZWP23 to PLEM7 | 5 days | 2026-08-06 | 2026-08-13 | 13156
167 | MM-ZTK-1F-IP23-PLR-DWG-9003 | IP23 Pipeline Schematic Diagram | 4 days | 2026-08-13 | 2026-08-19 | 166
168 | MM-ZTK-1F-IP23-PLR-DWG-9004 | IP23 Pipeline Platform Approach at ZWP23 | 4 days | 2026-05-14 | 2026-05-20 | 165
169 | MM-ZTK-1F-IP23-PLR-DWG-9005 | IP23 Pipeline PLEM Approach at PLEM7 | 4 days | 2026-05-20 | 2026-05-26 | 168
170 |  | GA: IP23 Riser and Tie-in Spools | 56 days | 2026-05-14 | 2026-07-31
171 | MM-ZTK-1F-IP23-PLR-GA-9001 | Riser GA Drawing at ZWP23 | 4 days | 2026-05-14 | 2026-05-20 | 145FS+5 days
172 | MM-ZTK-1F-IP23-PLR-GA-9002 | IP23 Tie-in Spool GA Drawing at ZWP23 | 4 days | 2026-07-21 | 2026-07-27 | 147
173 | MM-ZTK-1F-IP23-PLR-GA-9003 | IP23 Tie-in Spool GA Drawing at PLEM7 | 4 days | 2026-07-27 | 2026-07-31 | 172
174 |  | Isometric: IP23 Riser and Tie-in Spools | 20 days | 2026-06-26 | 2026-07-24
175 | MM-ZTK-1F-IP23-PLR-ISO-9001 | IP23 Riser Isometric at ZWP23 | 4 days | 2026-05-26 | 2026-06-02 | 149
176 | MM-ZTK-1F-IP23-PLR-ISO-9002 | IP23 Tie-in Spool Isometric at ZWP23 | 4 days | 2026-07-14 | 2026-07-20 | 151
177 | MM-ZTK-1F-IP23-PLR-ISO-9003 | IP23 Tie-in Spool Isometric at PLEM7 | 4 days | 2026-07-20 | 2026-07-24 | 176