## Dashboard
Consolidated Basic Engineering Open Points Closeout Register (Structural Scope)
| Gap Register_Open Points | 1
| Gap Register_Closed Points | 12
| Hold Register_Open Points | 1
| Hold Register_Closed Points | 14
| PPR Findings_Open Points | 0
| PPR Findings_Closed Points | 4
| Total Open Points | 2
| Total Closed Points | 30

## STR Gap Register
ZAWTIKA DEVELOPMENT PROJECT PHASE 1F
Gap Register
NO. | DISCIPLINE | REFERENCE DOC / DWG | GAP FROM REF. PACKAGE | Z1F REQUIREMENT | GAP CLOSE-OUT BY | CVENTEK / T&I Response | STATUS
1 | General |  |  | EPCI / Detailed Engineering CONTRACTOR(s) shall be aware of HOLD, TBA, VTA items which were identified in all Basis Engineering Deliverables and finalize the design parameters during EPCIC phase. | EPCI CONTRACTOR |  | Open
2 | Safety | SIL Verification Reports TH-BUN4-BE-WPG2-INS-RPT-0001. |  | It is recommended that all equipment, including associated system used for all identified SIFs, shall at least meet the prescriptive SIL requirements in accordance with relevant project specifications, as summarised in the following Table 4.1. In detailed design engineering stage shall consider the prescriptive SIL requirements that at least shall meet the minimum projet specifications stipulated in Table 4.1. that presented the list of minimum specification (prescriptive SIL requirement). This requirement is requested to consider in EPCIC. | EPCI CONTRACTOR |  | Open
3 | Safety | TH-BUN4-BE-WPG2-SAF-RPT-0003 | From basic engieerning, SIL classification of SIF04, PAHH-2001 - Production Manifold and Export Line presssure high high consider NNMI target likelihood and not consider case that WHP is directly connect to CPP. | In case that WHP is directly connect to CPP (ZWP-23), the consequence might be occured at CPP resulting in different target likelihood and SIL requirement. | EPCI CONTRACTOR |  | Open
4 | Safety | TH-BUN4-BE-WPG2-SAF-RPT-0009 | Dropped Object Study (DOS) (Topside & Associate Pipeline) | It is recommended that once the export and import pipelines approach information become available (e.g. during EPCI phase), a dropped object assessment of export and import pipelines during TAD Rig/Barge approach in drilling phase should be performed to quantify or understand the dropped object risk. This dropped object assessment will serve as one of criteria or inputs for designing the pipeline route or approach to minimise the dropped object risk. The verification on dropped object hazard in the case of sub sea pipeline if any routing within TAD crane radius shall be performed in EPCIC phase. This requirement to be highlighted and requested to carried out by EPCIC. | EPCI CONTRACTOR |  | Open
5 | Structure | Z1F Site-specific Jacket Basic Engineering deliverables | The BUN4 Design '2' Topsides SACS model was adopted with some minor modifications in this project. | The geometry and load input of the Topsides SACS model shall be verified and updated with the latest or actual information accordingly before it can be used in the detailed engineering phase. | EPCI CONTRACTOR | The model is verified and rerun to ensure the structural integrity. The results are presented in FEED verification report. Ongoing update input from other discipline Topsides WCR is Rev C1 and do not expect any major change from other disciplines, this matter can be closed. | Closed
6 | Structure | Z1F Site-specific Jacket Basic Engineering deliverables | In this project, the weight of secondary and tertiary items, such as anodes, internal ring stiffeners, hydrostatic ring stiffeners, etc., were approximated using historical data. | These weights shall be verified and updated with the latest or actual information during the detailed engineering phase. | EPCI CONTRACTOR | This can be closed once all jacket deliverables Rev A1 have been submitted. However, there are chages of design due to updated WD & will be updated in Rev B1. All completed and closed | Closed
7 | Piping | Following Z1F Basic Engineering deliverables, but not limited to; Equipment Layout, TH-BUN4-BE-WPG2-PIP-LAY-0001 to 0009 Piping General Arrangement, TH-BUN4-BE-WPG2-PIP-GA-0001 to 0025 Piping Material Specification, TH-BUN4-BE-WPG2-PIP-SPE-0001 Pipe Stress Analysis Report, TH-BUN4-BE-WPG2-PIP-CAL-0004 Pipe Stress Critical Line List, TH-BUN4-BE-WPG2-PIP-LIS-0001 Piping Specialty Item List, TH-BUN4-BE-WPG2-PIP-LIS-0002 Datasheet for Barrel Reducer, TH-BUN4-BE-WPG2-PIP-DTS-0008 Datasheet for Quick Opening Closure, TH-BUN-BE-WPG2-PIP-DTS-0009 Datasheet for Pig Launcher/Receiver, TH-BUN4-BE-WPG2-PIP-DTS-0010 MTO for Piping Manual Valves, TH-BUN4-BE-WPG2-PIP-MTO-0001 MTO for Piping Bulks, TH-BUN4-BE-WPG2-PIP-MTO-0002 AVEVA E3D | The location of the risers and riser size at ZWP-20, ZWP-21 and ZWP-22 will be changed from Basic Engineering Deliverables. Note that ZWP-23 to be followed Basic Engineering Deliverables. | Based on the FEED pipeline, the following riser location and riser size are to be developed: ZWP-20 : One 18" export riser (pre-installed) is located inside the jacket at leg A2 One 18" import riser (pre-installed) is located inside the jacket at leg A1 (Refer to MM-ZTK-BE-1F-IP20-PLR-GA-0001) ZWP-21 : One 18" export riser (pre-installed) is located inside the jacket at leg A1 One 10" import riser (pre-installed) is located inside the jacket at leg A2 (Refer to MM-ZTK-BE-1F-IP21-PLR-GA-0001) ZWP-22 : One 18" export riser (pre-installed) is located inside the jacket at leg A2 One 10" import riser (pre-installed) is located inside the jacket at leg A1 (Refer to MM-ZTK-BE-1F-IP22-PLR-GA-0001) For ZWP-23, refer to MM-ZTK-BE-1F-IP23-PLR-GA-0001 The specific topside pipe routing for each platform to be developed in accordance with the topside piping 3D snapshot. All related drawings, documents and AVEVA E3D to be developed or updated. EPCI / Detailed Engineering CONTRACTOR(s) shall verify and confirm them based on the latest/ actual information during the EPCI phase. See attached file (EXE-A2_Attachment-1_Z1F Topside Piping 3D snapshot) for more detail of this item. | EPCI CONTRACTOR |  | Open
8 | Structure | Z1F Site-specific Jacket Basic Engineering deliverables | The locations of the risers and riser clamps shown in the Z1F Site-specific Jacket Basic Engineering deliverables are indicative. | EPCI / Detailed Engineering CONTRACTOR(s) shall verify and confirm them based on the latest/ actual information during the EPCI phase. | EPCI CONTRACTOR | Info received from mermaid, with minor comments, this can be closed after Mermain submits the next revision CVT issued Riser Support Location to Mermaid. This matter can be closed | Closed
9 | Process | TH-BUN4-BE-WPG2-PRO-PID-0012 and all related document | From basic engieerning, Export ESDV is not required | In case that WHP is directly connect to CPP (ZWP-23), ESDV at export and overpressure protection must be required based on company spec. | EPCI CONTRACTOR |  | Open
10 | Process | PIPING AND INSTRUMENTATION DIAGRAM HAZARDOUS OPEN DRAINS AND CLOSED DRAINS SYSTEM TH-BUN4-BE-WPG2-PRO-PID-0021 | Revise note 27 | Revise note 27 to "27. WHEN COMBINED TEST SEPARATOR AND CLOSED DRAIN SUMP VESSEL VOLUME IS REQUIRED FOR UNLOADING OPERATION, OPERATOR SHALL CLOSE THIS VALVE BEFORE UNLOADING OPERATION. THE PAHH-5003 WILL BE BYPASSED AUTOMATICALLY UNDER THIS MODE." | EPCI CONTRACTOR |  | Open
11 | Instrument | Instrument Level Sketch TH-BUN4-BE-WPG2-INS-DWG-0003 | Specific Gravity Value | Specific Gravity shall be updated according to the latest process data. | EPCI CONTRACTOR |  | Open
12 | Instrument | Instrument Datasheet for Actuated Compact Ball Valve TH-BUN4-BE-WPG2-INS-DTS-0005 |  | The selected valve body is A182 UNS41000 which is MSS to be revised to A182 F51 (DSS) according to BUN4 Material Slection Report (TH-BUN4-BE-WPG2-COR-RPT-0001). | EPCI CONTRACTOR |  | Open
13 | Instrument | Instrument Datasheet for Actuated Ball Valve TH-BUN4-BE-WPG2-INS-DTS-0004 |  | The selected valve trim (ball) is 316 SS which is MSS to be revised to A182 F51 (DSS) according to BUN4 Material Slection Report (TH-BUN4-BE-WPG2-COR-RPT-0001) and Datasheet for Manual Valves (TH-BUN4-BE-WPG2-PIP-DTS-0001) | EPCI CONTRACTOR |  | Open
14 | Structure | Topside Computer Modelling & Load Formulation Report TH-BUN4-BE-WPG2-STR-CAL-1001, Rev.C1 Weight Control Report - Topsides MM-ZTK-BE-1F-ZWPX-STR-WCR-1001, Rev.C1 | Topsides Computer Modelling & Load Formulation Report and all weight items in Weight Control Report - Topsides shall be verified and confirmed. | In the Zawtika Phase 1F - Jacket Site-Specific Basic Engineering study, Topsides weight information and data for the Z1F Topsides Weight Control Report (WCR) were directly adopted from the Weight Control Report (WCR) of the Basic Engineering for the Bundled 4 Wellhead Platform project - Design '2' Topsides. Similarly, the SACS model for the in-service analyses was adopted, with some minor modifications, from the BUN4-Topsides Computer Modelling & Load Formulation Report. CONTRACTOR shall be responsible for verifying and confirming all weight items to reflect the latest and actual information and data, such Equipment Layout, Vendor data/ infiormation, etc., of each specific platform and the contigency factors used during EPCI phase. Furthermore, the geometry, design parameters used and load input of the Topsides in SACS model shall be verified and confirmed with the latest and actual information, such as Equipment layout, TAD Rigs loads, VENDOR data/information etc., accordingly before it can be used in the detailed engineering phase. | EPCI CONTRACTOR | The topside structural model now is checked against the latest TAD rig information and it is found that some members need to be upsized. This information is be informed to related discipline. For the latest vendor data, they will be updated against currnet information Ongoing update input from other discipline. Topsides WCR is Rev C1 and do not expect any major change from other disciplines, this matter can be closed | Closed
15 | Structure | TOPSIDE UPPER DECK PRIMARY STEEL FRAMING PLAN TH-BUN4-BE-WPG2-STR-DWG-1010, Rev.C1 TOPSIDE LOWER DECK PRIMARY STEEL FRAMING PLAN TH-BUN4-BE-WPG2-STR-DWG-1020, Rev.C1 TOPSIDE ELEVATION TRUSS ROW '1' TH-BUN4-BE-WPG2-STR-DWG-1130, Rev.C1 TOPSIDE ELEVATION TRUSS ROW '2' TH-BUN4-BE-WPG2-STR-DWG-1140, Rev.C1 TOPSIDE UPPER DECK MAIN JOINT FRAMING PLAN TH-BUN4-BE-WPG2-STR-DWG-1210, Rev.C1 | Topsides structural framing and members shall be verified and confirmed. | In the Zawtika Phase 1F - Jacket Site-Specific Basic Engineering study, the adopted BUN 4 -Design '2' Topsides has been preliminary checked and found as the following samples; - A skid beam on the South side appears to be 1000 mm short and require extension to be suitable with the TAD Rig of the GHTH model. The North side skid beam does not require an extension. - Secondary beam around padeyes, to support the gutter and hatch cover, appear to clash/ connected with padeyes which not be allowed due to the padeyes are required for using in decommissioning activity. These secondary members shall be rearranged to ensure no clashes with the padeyes. CONTRACTOR shall be responsible for verifying and confirming the Topsides framing and memebrs for all relevant operations, including the above finding such as the skid beam length in relation to the TAD Rig models, ensuring a clash-free arrangement of secondary beams around padeyes, etc., during EPCI phase | EPCI CONTRACTOR | This modification is updated into the drawing and structural model. 2nd beam around padeyes will be issued within this week. After CPY review, this mater can be closed. CVT issued and CPY returned comments AWC | Closed
16 | Structure | EQUIPMENT LAYOUT ELEVATION LOOKING NORTH TH-BUN4-BE-WPG2-PIP-LAY-0006, Rev.C1 | The future import piping riser shall be reviewed and confirmed. | According to PPR3 comment - Item # STR-8 highlights a discrepancy regarding the future import piping riser. The current design in BUN4 - Design '2' indicates a protrusion of it below the lower deck on east side without protection, whereas the ZMFP layout positions this import pipeline at south and the piping riser is within protected area of riser guard. CONTRACTOR shall be responsible for verifying and confirming the final location of this future import piping riser or the necessity of protection for Piping Riser Bend located below lower deck on the Eastside. This verification shall be based on the final equipment layout and outcomes of 3D model review workshop and HAZID study during EPCI phase. . | EPCI CONTRACTOR | After checking 3D model, the riser bend is protected by decking structure. | Closed
17 | Structure | TOPSIDE UPPER DECK FLOORING AND HANDRAIL LAYOUT TH-BUN4-BE-WPG2-STR-DWG-2110, Rev.C1 TOPSIDE LOWER DECK FLOORING AND HANDRAIL LAYOUT TH-BUN4-BE-WPG2-STR-DWG-2120, Rev.C1 | Topside flooring plate thickness shall be verified and confirmed. | CONTRACTOR shall be responsible for verifying and confirming the Topside flooring plate thickness against the final equipment layout and design criteria and subsequently update the SACS model accordingly during EPCI phase. | EPCI CONTRACTOR | Pending inout from GCME re: Dri=opped onject, due on 15-Jun-26 This matter is with CVT to complete analysis and close. TJE agreed to use 10mm THK floor plate instead of 8mm from FEED. This matter can be closed | Closed
18 | Structure | TOPSIDE LOWER DECK PRIMARY STEEL FRAMING PLAN TH-BUN4-BE-WPG2-STR-DWG-1020, Rev.C1 TOPSIDE LOWER DECK SECONDARY STEEL FRAMING PLAN TH-BUN4-BE-WPG2-STR-DWG-2020, Rev.C1 TOPSIDE MEZZANINE DECK FRAMING PLAN TH-BUN4-BE-WPG2-STR-DWG-2030, Rev.C1 TOPSIDE SUMP DECK FRAMING PLAN TH-BUN4-BE-WPG2-STR-DWG-2040, Rev.C1 | Topside structural framing and members size, especially, lower deck framing, shall be verified and confirmed. | The Zawtika Phase 1F - Jacket Site-Specific Basic Engineering study has found that some secondary members within the adopted BUN 4 -Design '2' Topsides SACS model do not align with the corresponding drawings. Furthermore, the arrangment and size of members around well bay area have been updated based on the analysis requirement. CONTRACTOR shall be responsible for verifying and confirming the topside framing against the latest equipment layouts, along with updating the geometry and load inputs of the Z1F Topsides SACS model before it can be used in the Detailed Engineering phase. | EPCI CONTRACTOR | This modification is updated into the drawing and structural model. SACS model update is ongoing, 2 additional members show in SACS but not showing in drawings on Mezz deck. Once CVT confirms, thuis matter can be closed. - Confirmed | Closed
19 | STR / SAF / PIP | TOPSIDE UPPER DECK PRIMARY STEEL FRAMING PLAN TH-BUN4-BE-WPG2-STR-DWG-1010, Rev.C1 TOPSIDE LOWER DECK PRIMARY STEEL FRAMING PLAN TH-BUN4-BE-WPG2-STR-DWG-1020, Rev.C1 TOPSIDE ELEVATION TRUSS ROW '1' TH-BUN4-BE-WPG2-STR-DWG-1130, Rev.C1 TOPSIDE ELEVATION TRUSS ROW '2' TH-BUN4-BE-WPG2-STR-DWG-1140, Rev.C1 TOPSIDE SECTION TH-BUN4-BE-WPG2-STR-DWG-1150, Rev.C1 TOPSIDE UPPER DECK MAIN JOINT FRAMING PLAN TH-BUN4-BE-WPG2-STR-DWG-1210, Rev.C1 TOPSIDE LOWER DECK MAIN JOINT FRAMING PLAN TH-BUN4-BE-WPG2-STR-DWG-1211, Rev.C1 | Topsides structural members size shall be verified and confirmed. | The Zawtika Phase 1F - Jacket Site-Specific Basic Engineering study has identified revised member sizes in the Well Bay area of the adopted BUN 4 - Design '2' Topsides.based on the analysis requirements. Furthermore, due to utilization of only one (1) Tender Assisted Drilling Rig (TADR) model as GHTH in the Zawtika Phase 1F - Jacket Site-Specific Basic Engineering study, some members are found to be overstressed and especially members at South side and Deck Legs. Consequently, these members shall be strengthened by upsizing as per the requirements from analysis results. CONTRACTOR shall be responsible for verifying and confirming the proposed strengthening members against the latest equipment layouts, design requirements, design criteria, and updated Topsides SACS model during EPCI phase. | EPCI CONTRACTOR | The topside structural model now is checked against the latest GHTH and T18 TAD rig information and it is found that some members need to be upsized. This information is be informed to related discipline. For the latest vendor data, they will be updated against currnet information. Both GHTH and T18 TAD rig have been considered. | Closed
20 | Structure | Naval Architectural Basis of Design MM-ZTK-BE-1F-ZWPX-NVA-BOD-0001, Rev.C1 ZWP20Jacket Barge Motion and Stability Analysis MM-ZTK-BE-1F-ZWP20-NVA-CAL-2011, Rev.C1 ZWP20 Jacket Launch Analysis Report MM-ZTK-BE-1F-ZWP20-NVA-CAL-2012, Rev.C1 ZWP20 Jacket Loadout Analysis Report MM-ZTK-BE-1F-ZWP20-STR-CAL-2014, Rev.C1 ZWP20 Jacket Transportation Analysis Report MM-ZTK-BE-1F-ZWP20-STR-CAL-2015, Rev.C1 ZWP20 Transportation Fatigue Analysis Report MM-ZTK-BE-1F-ZWP20-STR-CAL-2016, Rev.C1 ZWP21Jacket Barge Motion and Stability Analysis MM-ZTK-BE-1F-ZWP21-NVA-CAL-2011, Rev.C1 ZWP21 Jacket Launch Analysis Report MM-ZTK-BE-1F-ZWP21-NVA-CAL-2012, Rev.C1 ZWP21 Jacket Loadout Analysis Report MM-ZTK-BE-1F-ZWP21-STR-CAL-2014, Rev.C1 ZWP21 Jacket Transportation Analysis Report MM-ZTK-BE-1F-ZWP21-STR-CAL-2015, Rev.C1 ZWP21 Transportation Fatigue Analysis Report MM-ZTK-BE-1F-ZWP21-STR-CAL-2016, Rev.C1 | Naval Architectural Basis of Design shall be updated and included the Topsides Naval Architectural analyses. Topsides, Jackets, and Piles members size for each platform shall be confirmed under pre-service conditions. | In the Zawtika Phase 1F - Jacket Site-specific Basic Engineering study, only two representative jackets, ZWP20 and ZWP21, have been selected as the lower and upper bound conditions for the pre-service analysis, due to their shallowest and deepest water depths, respectively. The Topsides pre-services and naval architectural analyses ARE EXCLUDED from the scope of this study. Based from past projects' experiences and historical data, the following assumptions have been adopted for the analysis; - The tow route is assumed to be from Southeast China to the Installation Site, with a transportation window of October to November. - Two launch barges, Holmen Atlantic and FLB1, are assumed to transport ZWP20 and ZWP21 jackets, respectively. - Stowage Plans and sea-fastening members and locations of ZWP 20 and ZWP21 jackets on the launch barges are assumed. - Jackets are assumed to be loaded out by the skidding method. - The top rubber diaphragm of pile sleeves P5( ZWP20) and P4 and P5(ZPW21) has been proposed to be removed to improve the stability. The preliminary checks were performed under the pre-service conditions for only ZWP 20 and ZWP21 jackets. However, the pre-service analyses for ZWP22 and ZWP23 jackets and piles have not been performed. CONTRACTOR shall be responsible for reviewing and updating the Naval Architectural Basis of Design, including the Topsides naval architectural analysis, to incorporate the latest and actual information and data, such as Tow route data, Launch barges, Transportation barges, Stowage plan, Loadout method etc., during EPCI phase. Additionally, CONTRACTOR shall confirm the structural integrity of the Topsides, Jackets and Piles members size of each platform (ZWP20, ZWP21, ZWP22, and ZWP23) under pre-service conditions during the EPCI phase, prior to the procurement of materials. | EPCI CONTRACTOR | Tow route: Confirmed Launch arge: H.Pacific and H.Atlantic Stowage plan confirmed by SSC Jacket loadout using skid beam Top diahragm number TBA. Once Navak Arch reports Rev A1 submitted, this matter can be closed. Ongoing analyses due to changes of water depth All analyses as listed have been completed EXCEPT rework if 3rd barge comes on board and barge swap | Ongoing
21 | Structure | Structural Basis of Design MM-ZTK-BE-1F-ZWPX-STR-BOD-0001, Rev.C1 Jacket In-Place Analysis Report MM-ZTK-BE-1F-ZWP20-STR-CAL-2011, Rev.C1 MM-ZTK-BE-1F-ZWP21-STR-CAL-2011, Rev.C1 MM-ZTK-BE-1F-ZWP22-STR-CAL-2011, Rev.C1 MM-ZTK-BE-1F-ZWP23-STR-CAL-2011, Rev.C1 Jacket Dynamic Analysis Report MM-ZTK-BE-1F-ZWP20-STR-CAL-2012, Rev.C1 MM-ZTK-BE-1F-ZWP21-STR-CAL-2012, Rev.C1 MM-ZTK-BE-1F-ZWP22-STR-CAL-2012, Rev.C1 MM-ZTK-BE-1F-ZWP23-STR-CAL-2012, Rev.C1 Jacket In-Place Spectral Analysis Report MM-ZTK-BE-1F-ZWP20-STR-CAL-2013, Rev.C1 MM-ZTK-BE-1F-ZWP21-STR-CAL-2013, Rev.C1 MM-ZTK-BE-1F-ZWP22-STR-CAL-2013, Rev.C1 MM-ZTK-BE-1F-ZWP23-STR-CAL-2013, Rev.C1 Topsides and Jacket Seismic Analysis (ELE) Report MM-ZTK-BE-1F-ZWP20-STR-CAL-2031, Rev.C1 MM-ZTK-BE-1F-ZWP21-STR-CAL-2031, Rev.C1 MM-ZTK-BE-1F-ZWP22-STR-CAL-2031, Rev.C1 MM-ZTK-BE-1F-ZWP23-STR-CAL-2031, Rev.C1 Topsides and Jacket Seismic Analysis (ALE) Report MM-ZTK-BE-1F-ZWP20-STR-CAL-2032, Rev.C1 MM-ZTK-BE-1F-ZWP21-STR-CAL-2032, Rev.C1 MM-ZTK-BE-1F-ZWP22-STR-CAL-2032, Rev.C1 MM-ZTK-BE-1F-ZWP23-STR-CAL-2032, Rev.C1 | Structural Basis of Design shall be updated. Topsides, Jackets, and Piles members size for each platform shall be confirmed. Pile make-up and pile penetration length for all platforms shall be confirmed. | In the Zawtika Phase 1F - Jacket Site-specific Basic Engineering study, a Topsides design information and design data and parameters were adopted from the Basic engineering for Bundled 4 Wellhead Platform project- Design '2' Topsides for the structural basis of design and SACS model, with some minor modifications, for the in-service platform analysis in this project. Furthermore, the weight of some jacket primary steel items, as well as secondary and tertiary items, such as risers, anodes, boatlanding, internal ring stiffeners, hydrostatic ring stiffeners, diaphragm closure, launch cradle, installation aid items, etc., were approximated using historical data. The preliminary checks under in-service conditions were performed for all Jackets, but for Topsides, only seismic analyses were performed as part of this Basic Engineering study. However, the pre-service analyses for the individual Topsides, ZWP22 and ZWP23 Jackets, as well as the pile pre-service analyses, such as pile handling and stick-up analysis, pile drivability and fatigue analysis, pile transportation fatigue analysis have not been performed CONTRACTOR shall be responsible for reviewing and updating the Structural Basis of Design to incorporate the latest and actual information and data during EPCI phase. Furthermore, the geometry, design parameters used and load input of the Topsides SACS model, as well as the historical estimated weights for the Jacket, risers size and their locations, shall be verified and confirmed with the latest and actual information accordingly before it can be used in the detailed engineering phase. Additionally, CONTRACTOR shall confirm the structural integrity of the Topsides, Jackets and Piles members size of each platform (ZWP20, ZWP21, ZWP22, and ZWP23) under in-service conditions during the EPCI phase, prior to the procurement of materials. | EPCI CONTRACTOR | Structural Basis of Design has been updated. Topsides, Jackets, and Piles members size for each platform shall be confirmed.- pile TBC Pile make-up and pile penetration length for all platforms shall be confirmed.TBC, pending pile penetration optimisation Pending ZWP22 and ZWP20 Spectral Fatigue Fatigue analyses of every platform have been completed, thus matter can be closed | Closed
22 | Structure | Cathodic Protection Calculation Report MM-ZTK-BE-1F-ZWP20-COR-CAL-0001, Rev.C1 MM-ZTK-BE-1F-ZWP21-COR-CAL-0001, Rev.C1 MM-ZTK-BE-1F-ZWP22-COR-CAL-0001, Rev.C1 MM-ZTK-BE-1F-ZWP23-COR-CAL-0001, Rev.C1 | The numbers of anode and anode distribution shall be verified and confirmed. | In the Zawtika Phase 1F - Jacket Site-specific Basic Engineering study, the preliminary cathodic protection was performed based on the available primary jacket members' surface area as modeled in SACS model of each platform. CONTRACTOR shall be responsible for verifying and confirming the total number of anodes and their distribution of each platform. This should be performed by a NACE Level 3 certified professional, based on the latest jacket member sizes and other items to be protected by the cathodic protection system during EPCI phase, prior to the procurement of anodes. | EPCI CONTRACTOR | After further updates from TJE NACE level III personnel, this matter can be closed GCME NACE to continue works, this matter can be closed | Closed
23 | Structure | Jacket Weight Control Report MM-ZTK-BE-1F-ZWP20-STR-WCR-2001, Rev.C1 MM-ZTK-BE-1F-ZWP21-STR-WCR-2001, Rev.C1 MM-ZTK-BE-1F-ZWP22-STR-WCR-2001, Rev.C1 MM-ZTK-BE-1F-ZWP23-STR-WCR-2001, Rev.C1 | All weight items in the Jacket Weight Contorl Reports shall be verified and confirmed. | In the Zawtika Phase 1F - Jacket Site-specific Basic Engineering study, the weight of some jacket primary steel items, as well as secondary and tertiary items, such as risers, anodes, boatlanding, internal ring stiffeners, hydrostatic ring stiffeners, diaphragm closure, launch cradle, installation aid items, etc., were approximated using historical data. CONTRACTOR shall be responsible for verifying and confirming all weight items to reflect the latest and actual information and data of each platform during EPCI phase. | EPCI CONTRACTOR | Once Rev A1 reports for every jacket issued, this matter can be closed Ongoing works to confirm WCR due to changes of water depth and pile penetration optimisation Jacket WCR from change WD confirmed. | Closed
24 | Pipeline | MM-ZTK-BE-1F-IPX-PLR-BOD-0001 Pipeline and Riser Design Basis and Design Criteria | Transient temperature data is not available. | They shall be included in Detailed Engineering Design. | EPCI CONTRACTOR |  | Open
25 | Pipeline | MM-ZTK-BE-1F-IPX-PLR-BOD-0001 Pipeline and Riser Design Basis and Design Criteria | Pipeline bottom tension used in Basic Engineering Design is 570 kN. | If pipelay installation tension increase significantly, the following reports shall be revisited in Detailed Engineering Design. -Free Span -End expansion -Lateral buckling | EPCI CONTRACTOR |  | Open
26 | Pipeline | MM-ZTK-BE-1F-IPX-PLR-BOD-0001 Pipeline and Riser Design Basis and Design Criteria | IP22 pipeline route is deviated from the original survey route. | Geotechnical investigation should be updated if further survey is performed. | EPCI CONTRACTOR |  | Open
27 | Pipeline | MM-ZTK-BE-1F-IPX-PLR-BOD-0001 Pipeline and Riser Design Basis and Design Criteria | Walking screening analysis does not include effects of transient temperature because the transient temperature profiles are not available. | The effects of the transient temperature profiles shall be included in Detailed Engineering Design. | EPCI CONTRACTOR |  | Open
28 | Pipeline | MM-ZTK-BE-1F-IPX-PLR-BOD-0001 Pipeline and Riser Design Basis and Design Criteria | The jacket structure is not verified in riser clamp design. | The verification shall be carried out in Detailed Engineering Design. | EPCI CONTRACTOR |  | Open
29 | Pipeline | MM-ZTK-BE-1F-IPX-PLR-BOD-0002 Seismic Consideration for Subsea Pipeline in Seismic Hazardous Area | The scope does not include riser and tie-in spool flexibility analysis. | They shall be performed in Detailed Engineering Design. | EPCI CONTRACTOR |  | Open
30 | Pipeline | MM-ZTK-BE-1F-IPX-PLR-RPT-0002 Pipeline On-Bottom Stability Analysis Report | The anti-corrosion coating thickness of tie-in spool with concrete coating is changed from 2.2 mm to 2.5 mm thick 3LPP coating. The difference of overall diameter and submerged weight are within 0.12 % and 0.57%, respectively. These difference are considered insignificant. | The stability shall be confirmed in Detailed Engineering Design. | EPCI CONTRACTOR |  | Open
31 | Pipeline | MM-ZTK-BE-1F-IPX-PLR-RPT-0002 Pipeline On-Bottom Stability Analysis Report | The anti-corrosion coating thickness of pipeline is changed from 2.5 mm to 2.8 mm thick 3LPE coating. The difference of overall diameter and submerged weight are within 0.12 % and 0.08 %, respectively. These difference are considered insignificant. | The stability shall be confirmed in Detailed Engineering Design. | EPCI CONTRACTOR |  | Open
32 | Pipeline | MM-ZTK-BE-1F-IP20-PLR-RPT-0004 Pipeline Seismic Analysis Report: IP20 MM-ZTK-BE-1F-IP21-PLR-RPT-0004 Pipeline Seismic Analysis Report: IP21 MM-ZTK-BE-1F-IP22-PLR-RPT-0004 Pipeline Seismic Analysis Report: IP22 MM-ZTK-BE-1F-IP23-PLR-RPT-0004 Pipeline Seismic Analysis Report: IP23 | The scope does not include risers and tie-in stress spools analysis. | The riser and tie-in spool stress analysis shall be performed in Detailed Engineering Design. The existing PLEM tie-in spool shall be included in the flexibility analysis for PLEM14 and PLEM07. | EPCI CONTRACTOR |  | Open
33 | Pipeline | MM-ZTK-BE-1F-IP20-PLR-RPT-0004 Pipeline Seismic Analysis Report: IP20 MM-ZTK-BE-1F-IP21-PLR-RPT-0004 Pipeline Seismic Analysis Report: IP21 MM-ZTK-BE-1F-IP22-PLR-RPT-0004 Pipeline Seismic Analysis Report: IP22 MM-ZTK-BE-1F-IP23-PLR-RPT-0004 Pipeline Seismic Analysis Report: IP24 | The scope does not include Fault crossing analysis. | Fault crossing analysis shall be performed in Detailed Engineering Design. The analysis shall cover the active faults F5 and F6 on IP 23 route. | EPCI CONTRACTOR |  | Open
34 | Pipeline | MM-ZTK-BE-1F-IPX-PLR-RPT-0003 Pipeline Global buckling and Walking Screening | The global buckling analysis is performed with screening criteria. The pipelines do not satisfy the screening criteria. | Finite element analysis shall be performed in Detailed Engineering Design to analyze the susceptibility of global buckling. | EPCI CONTRACTOR |  | Open
35 | Pipeline | MM-ZTK-BE-1F-IPX-PLR-RPT-0003 Pipeline Global buckling and Walking Screening | Walking screening analysis does not include effects of transient temperature because the transient temperature profiles are not available. | The effects of the transient temperature profiles should be included in Detailed Engineering Design. | EPCI CONTRACTOR |  | Open
36 | Pipeline | MM-ZTK-BE-1F-IPX-PLR-RPT-0004 10" Riser Span Analysis and 10” Riser Clamp Design Report | Riser loads are transferred to the jacket structure. The jacket structure is not verified. | The verification of jacket structure shall be carried out in Detailed Engineering Design. | EPCI CONTRACTOR |  | Open
37 | Pipeline | MM-ZTK-BE-1F-IPX-PLR-RPT-0004 10" Riser Span Analysis and 10” Riser Clamp Design Report | The scope does not include riser flexibility analysis. | The riser clamp loads shall be confirmed in Detailed Engineering Design. | EPCI CONTRACTOR |  | Open
38 | Pipeline | MM-ZTK-BE-1F-IP20-PLR-RPT-0001 Pipeline Routing Study and Design: IP20 MM-ZTK-BE-1F-IP21-PLR-RPT-0001 Pipeline Routing Study and Design: IP21 MM-ZTK-BE-1F-IP22-PLR-RPT-0001 Pipeline Routing Study and Design: IP22 MM-ZTK-BE-1F-IP23-PLR-RPT-0001 Pipeline Routing Study and Design: IP23 | The semi-tender rig layout is obtained from previous phase. | The semi-tender rig layout should be updated if the layout is changed. | EPCI CONTRACTOR |  | Open
39 | Pipeline | MM-ZTK-BE-1F-IP21-PLR-DWG-0002 IP21 Pipeline Alignment Sheets: ZWP21 to PLEM14 | IP22 seabed features are obtianed from two different data sources. | If IP22 geophysical survey is performed in Detailed Engineering Design, the seabed features and contours shall be updated. | EPCI CONTRACTOR |  | Open
40 | Pipeline | MM-ZTK-BE-1F-IP20-PLR-GA-0002 IP20 Spool GA Drawing at ZWP20 MM-ZTK-BE-1F-IP20-PLR-GA-0003 IP20 Spool GA Drawing at ZWP16 MM-ZTK-BE-1F-IP21-PLR-GA-0002 IP21 Spool GA Drawing ZWP21 MM-ZTK-BE-1F-IP21-PLR-GA-0003 IP21 Spool GA Drawing at PLEM14 MM-ZTK-BE-1F-IP22-PLR-GA-0002 IP22 Spool GA Drawing at ZWP22 MM-ZTK-BE-1F-IP22-PLR-GA-0003 IP22 Spool GA Drawing at ZWP8 MM-ZTK-BE-1F-IP23-PLR-GA-0002 IP23 Spool GA Drawing at ZWP23 MM-ZTK-BE-1F-IP23-PLR-GA-0003 IP23 Spool GA Drawing at PLEM07 | The scope does not include spool flexibility analysis. | The spool flexibility analysis shall be performed in Detailed Engineering Design. | EPCI CONTRACTOR |  | Open
41 | Pipeline | MM-ZTK-BE-1F-IP20-PLR-GA-0002 IP20 Spool GA Drawing at ZWP20 MM-ZTK-BE-1F-IP20-PLR-GA-0003 IP20 Spool GA Drawing at ZWP16 MM-ZTK-BE-1F-IP21-PLR-GA-0002 IP21 Spool GA Drawing ZWP21 MM-ZTK-BE-1F-IP21-PLR-GA-0003 IP21 Spool GA Drawing at PLEM14 MM-ZTK-BE-1F-IP22-PLR-GA-0002 IP22 Spool GA Drawing at ZWP22 MM-ZTK-BE-1F-IP22-PLR-GA-0003 IP22 Spool GA Drawing at ZWP8 MM-ZTK-BE-1F-IP23-PLR-GA-0002 IP23 Spool GA Drawing at ZWP23 MM-ZTK-BE-1F-IP23-PLR-GA-0003 IP23 Spool GA Drawing at PLEM07 | The scope does not include seismic analysis of all tie-in spools. | The spool flexibility analysis under seismic loading shall be performed in Detailed Engineering Design. The effects of lateral displacement of pipeline ends during seismic loading shall be also considered in Detailed Engineering Design. | EPCI CONTRACTOR |  | Open
42 | Pipeline | MM-ZTK-BE-1F-IP20-PLR-GA-0002 IP20 Spool GA Drawing at ZWP20 MM-ZTK-BE-1F-IP20-PLR-GA-0003 IP20 Spool GA Drawing at ZWP16 MM-ZTK-BE-1F-IP21-PLR-GA-0002 IP21 Spool GA Drawing ZWP21 MM-ZTK-BE-1F-IP21-PLR-GA-0003 IP21 Spool GA Drawing at PLEM14 MM-ZTK-BE-1F-IP22-PLR-GA-0002 IP22 Spool GA Drawing at ZWP22 MM-ZTK-BE-1F-IP22-PLR-GA-0003 IP22 Spool GA Drawing at ZWP8 MM-ZTK-BE-1F-IP23-PLR-GA-0002 IP23 Spool GA Drawing at ZWP23 MM-ZTK-BE-1F-IP23-PLR-GA-0003 IP23 Spool GA Drawing at PLEM07 | The scope does not include the design flange protector. | The design of flange protector shall be included in Detailed Engineering Design. | EPCI CONTRACTOR |  | Open
43 | Pipeline | MM-ZTK-BE-1F-IP20-PLR-GA-0001 IP20 Riser GA Drawing at ZWP20 MM-ZTK-BE-1F-IP21-PLR-GA-0001 IP21 Riser GA Drawing at ZWP21 MM-ZTK-BE-1F-IP22-PLR-GA-0001 IP22 Riser GA Drawing at ZWP22 MM-ZTK-BE-1F-IP23-PLR-GA-0001 IP23 Riser GA Drawing ZWP23 MM-ZTK-BE-1F-IP21-PLR-DWG-0006 NPS 10 Riser GA Drawings at ZWP21 MM-ZTK-BE-1F-IP22-PLR-DWG-0006 NPS 10 Riser GA Drawings at ZWP22 | The scope does not include riser flexibility analysis. | The riser flexibility analysis shall be performed in Detailed Engineering Design. | EPCI CONTRACTOR |  | Open
44 | Pipeline | MM-ZTK-BE-1F-IP20-PLR-GA-0001 IP20 Riser GA Drawing at ZWP20 MM-ZTK-BE-1F-IP21-PLR-GA-0001 IP21 Riser GA Drawing at ZWP21 MM-ZTK-BE-1F-IP22-PLR-GA-0001 IP22 Riser GA Drawing at ZWP22 MM-ZTK-BE-1F-IP23-PLR-GA-0001 IP23 Riser GA Drawing ZWP23 | The scope does not include VIV span analysis of 18” risers. | The VIV span analysis of 18" risers shall be performed in Detailed Engineering Design. | EPCI CONTRACTOR |  | Open
45 | Pipeline | MM-ZTK-BE-1F-IP20-PLR-GA-0001 IP20 Riser GA Drawing at ZWP20 MM-ZTK-BE-1F-IP21-PLR-GA-0001 IP21 Riser GA Drawing at ZWP21 MM-ZTK-BE-1F-IP22-PLR-GA-0001 IP22 Riser GA Drawing at ZWP22 MM-ZTK-BE-1F-IP23-PLR-GA-0001 IP23 Riser GA Drawing ZWP23 MM-ZTK-BE-1F-IP21-PLR-DWG-0006 NPS 10 Riser GA Drawings at ZWP21 MM-ZTK-BE-1F-IP22-PLR-DWG-0006 NPS 10 Riser GA Drawings at ZWP22 | The scope does not include seismic analysis of all risers. | The seismic analysis for all risers shall be performed in Detailed Engineering Design. | EPCI CONTRACTOR |  | Open
46 | Pipeline | MM-ZTK-BE-1F-IP22-PLR-DWG-0006 NPS 10 Riser GA Drawings at ZWP22 | Design pressure of 168 barg is considered for 10" riser at ZWP22, while its design pressure is required only 70 barg. | For ZWP22 10” riser, the design pressure of 70 barg shall be revisited. While at ZWP21 can maintain design pressure of 168 barg. | EPCI CONTRACTOR |  | Open
47 | Pipeline | WAS-WPP-A-TNS-PL-DR-0004 Pipeline Bend Details | The bend coating is 1.25 mm thick HBE, while there are three options including 2LPP, HBE and SP8888 coating. | Bend coating shall be revisited. Contractor shall consider 2LPP, HBE and SP8888 in Detailed Engineering Design. The coating system shall follow document, 10008-STD-6-COR-003-R01, coating of bends and fittings for pipelines. | EPCI CONTRACTOR |  | Open
48 | Pipeline | MM-ZTK-BE-1F-IP20-PLR-RPT-0003 Pipeline Bottom roughness and in place stress analysis: IP 20 MM-ZTK-BE-1F-IP21-PLR-RPT-0003 Pipeline Bottom roughness and in place stress analysis: IP 21 MM-ZTK-BE-1F-IP22-PLR-RPT-0003 Pipeline Bottom roughness and in place stress analysis: IP 22 MM-ZTK-BE-1F-IP23-PLR-RPT-0003 Pipeline Bottom roughness and in place stress analysis: IP 23 | Several free spans exceed allowable spans. Mitigation measures are not defined. | The free spans exceeding the allowable span shall be rectified to avoid damage. For the area outside the sand wave zone, the convention support such as grout bags should be used for the free span rectification. For the sand wave seabed, if sand wave migration record is available, the record should be checked for sand wave mobility. If the record is not available, the sand wave mobility study should be performed. If the sand wave is susceptible to mobility, the pipeline should be buried using jet trenching. If sand wave is not susceptible to mobility, the convention supports such as grout bags are acceptable. | EPCI CONTRACTOR |  | Open
49 | Pipeline | MM-ZTK-BE-1F-IP20-PLR-MTO-0001 Material Take-Off : IP20 Pipeline MM-ZTK-BE-1F-IP21-PLR-MTO-0001 Material Take-Off : IP21 Pipeline MM-ZTK-BE-1F-IP22-PLR-MTO-0001 Material Take-Off : IP22 Pipeline MM-ZTK-BE-1F-IP23-PLR-MTO-0001 Material Take-Off : IP23 Pipeline | The anti-corrosion coating thickness of tie-in spool with concrete coating is changed from 2.2 mm to 2.5 mm thick 3LPP coating. | The coating description in MTO shall be updated. | EPCI CONTRACTOR |  | Open
50 | Pipeline | MM-ZTK-BE-1F-IP20-PLR-MTO-0001 Material Take-Off : IP20 Pipeline MM-ZTK-BE-1F-IP21-PLR-MTO-0001 Material Take-Off : IP21 Pipeline MM-ZTK-BE-1F-IP22-PLR-MTO-0001 Material Take-Off : IP22 Pipeline MM-ZTK-BE-1F-IP23-PLR-MTO-0001 Material Take-Off : IP23 Pipeline | The anti-corrosion coating thickness of pipeline is changed from 2.5 mm to 2.8 mm thick 3LPE coating. | The coating description in MTO shall be updated. | EPCI CONTRACTOR |  | Open
51 | Pipeline | MM-ZTK-BE-1F-IP20-PLR-MTO-0001 Material Take-Off : IP20 Pipeline MM-ZTK-BE-1F-IP21-PLR-MTO-0001 Material Take-Off : IP21 Pipeline MM-ZTK-BE-1F-IP22-PLR-MTO-0001 Material Take-Off : IP22 Pipeline MM-ZTK-BE-1F-IP23-PLR-MTO-0001 Material Take-Off : IP23 Pipeline | The bend coating is 1.25 mm thick HBE, while there are three options including 2LPP, HBE and SP8888 coating. | Bend coating shall be revisited. Contractor shall consider 2LPP, HBE and SP8888 in Detailed Engineering Design. | EPCI CONTRACTOR |  | Open
52 | Pipeline | MM-ZTK-BE-1F-IP22-PLR-GA-0002: IP22 Spool GA Drawing at ZWP22 | There is a new PLEM (Future) to be installed at ZWP-22. | Please Contractor consider the location for future PLEM tie-in near ZWP-22. The tie-in spool nearby the ZWP-22 shall be removeable and replace new new tie-in spool to connect to the furture PLEM. | EPCI CONTRACTOR |  | Open

## Hold Register
S.No | Hold on Document | Hold Number | Description of HOLDs | Resposible | Required Action | Response from CventeK | Response from T&I | Open/ Closed
1 | Basic Engineering Structural Design Basis Document | HOLD-1 | The topsides information and parameters have been adopted from the Basic Engineering for Bundled 4 Wellhead Platforms project, as detailed in Section 8 of the document titled “Structural Design Basis,” Reference [2.2.14], with minor adjustments from the available Zawtika Phase 1E project information. It is the responsibility of the EPCI CONTRACTOR to verify and confirm these parameters based on the latest and final information prior to use in the EPCI phase. 1. Equipment List as per Latets Layout 2. Dropped Object Loads 3. The Location for Personnel Access Ramp to be confirmed & Input from EDrill 2 Rig Team 4. Size of the equipment to be confirmed for PIG reciever 5. Burner Boom Data | EPCI Contractor | Verify and confirm topsides loads, Equipment loads and parameters based on final project data, Layout prior to EPCI execution. | Topsides WCR can proceed to Rev C1, this matter can be closed. |  | Closed
2 | Basic Engineering Structural Design Basis Document | HOLD-2 | In Provisional Jacket Site-Specific Basic Engineering for Zawtika Development Project Phase 1F, ZWP22 and ZWP23 Naval Architect Designs are excluded in its scope and barges for transportation are not selected. Therefore, Transportation Analysis are also excluded. It is the responsibility of the EPCI CONTRACTOR to verify and confirm these parameters based on the latest and final information during the EPCI phase. | EPCI Contractor / T&I | Confirm selected transportation barges and perform transportation / motion analysis accordingly. |  | SSC conformed H.Pacific and H. Atlantic are the two launch barge and tow route data, Third Barge is pending | Ongoing
3 | Basic Engineering Structural Design Basis Document | HOLD-3 | The launch barges for the transportation of ZWP20, ZWP21, ZWP22 and ZWP23 jackets, piles transportation barges, and heavy lift vessels shall be confirmed, and their information/data provided by the T&I contractor during the EPCI phase. | EPCI Contractor / T&I | Confirm launch vessel selection and provide vessel data (GA, stability data, ballast system, grillage layout, etc.) for analysis update. |  | ZWP23 is waiting for launch barge owner to confirm high bending utilisation for H.Atlantic Confirmed | Closed
4 | Basic Engineering Naval Architecture Design Basis Document | HOLD-1 | The launch barges for the transportation of ZWP20, ZWP21, ZWP22, and ZWP23 jackets shall be confirmed, and their information/data provided by the T&I CONTRACTOR during the EPCI phase. | T&I Contractor | Confirm launch vessel selection and provide vessel data (GA, stability data, ballast system, grillage layout, etc.) for analysis update. |  | SSC provided | Closed
5 | Basic Engineering Naval Architecture Design Basis Document | HOLD-2 | The stowage plan and transportation barge for piles shall be provided by T&I CONTRACTOR during the EPCI phase. | T&I Contractor | Confirm stowage Plan / selected transportation barges and perform transportation / motion analysis accordingly. |  | Pile TBC. Received Pile Stowage Plan. This matter can be closed | Closed
6 | Basic Engineering Naval Architecture Design Basis Document | HOLD-3 | The stowage plan for the ZWP20, ZWP21, ZWP22, and ZWP23 jackets for each designated launch barge shall be confirmed and provided by the T&I CONTRACTOR during the EPCI phase. | T&I Contractor | Confirm stowage plan / selected transportation barges and perform transportation / motion analysis accordingly. |  | Referrd to No. 3 | Closed
7 | Basic Engineering - Barge Motion/Launch Analysis/Floatation & Upending Analysis / Jacket Computer Modelling & Load Formulation Report | HOLD-1 | Barge data is based on Holmen Atlantic historical data. The data shall be verified and updated with the latest or actual information during the detailed engineering phase. | CventeK | Verify historical barge data and update with latest confirmed vessel particulars during detailed engineering. |  | Referrd to No. 3. H.Atlantc | Closed
8 | Basic Engineering - Barge Motion/Launch Analysis/Floatation & Upending Analysis / Jacket Computer Modelling & Load Formulation Report | HOLD-2 | In this project, the weight of certain primary steel items, as well as secondary and tertiary items such as anodes, boatlanding, internal ring stiffeners, hydrostatic ring stiffeners, diaphragm closure, launch cradle, installation aids, etc., were estimated using historical data. These weights shall be verified and updated with the latest or actual information during the detailed engineering phase. | CventeK | Recalculate and confirm actual weights based on finalized design and updated vendor data during detailed engineering. |  | Once all Rev A1 submitted, this can be closed All Primary Steel and Miscellaneous Steel comfirmed | Closed
9 | Basic Engineering - Inplace Analysis / Dynamic Analysis Report / Spectral Fatigue Analysis/ELE / ALE report | HOLD-1/3 | The BUN4 Design ‘2’ Topsides SACS model was adopted with minor modifications for this project. Therefore, the geometry and load inputs of the Topsides SACS model shall be verified and updated with the latest or actual information before being used in the detailed engineering phase. | CventeK | Verify and confirm topsides loads, Equipment loads and parameters based on final project data, Layout prior to EPCI execution. |  | Once all Rev A1 submitted, this can be closed Analyses completed | Closed
10 | Basic Engineering - Inplace Analysis / Dynamic Analysis Report / Spectral Fatigue Analysis /ELE / ALE /Primary MTO/Secondary MTO report | HOLD-2/4 | In this project, the weight of certain primary steel items, as well as secondary and tertiary items such as anodes, boatlanding, internal ring stiffeners, hydrostatic ring stiffeners, diaphragm closure, launch cradle, installation aids, etc., were estimated using historical data. These weights shall be verified and updated with the latest or actual information during the detailed engineering phase. | CventeK | Recalculate and confirm actual weights based on finalized design and updated vendor data during detailed engineering. |  | Once all Rev A1 submitted, this can be closed Analyses completed | Closed
11 | Basic Engineering -Spectral Fatigue Analysis report | HOLD-1 | The topsides spectral fatigue analysis, including fatigue life assessment covering damages from topsides in-service condition and transportation analysis, shall be performed and confirmed during the Detailed Engineering Phase. | CventeK | The topsides spectral fatigue analysis, including fatigue life assessment covering damages from topsides in-service condition and transportation analysis, to be performed and confirmed |  | Topsides in-service and transportaton fatigues analyses are ongoing, TBC Topsides fatigue - duration of 2nd topsides that is under standby may affect Topsides Fatigue, standby duration @ offshore site to be confirmed by T&I. T&I confirmed 30 days transportation and 30 days Standy for 2nd Topsides | Closed
12 | Basic Engineering - Spectral Fatigue Analysis report | HOLD-2 | The pile fatigue life assessment shall include damages arising from pile transportation and shall be performed and confirmed during the Detailed Engineering Phase. | CventeK | The pile fatigue life assessment shall include damages arising from pile transportation and to be performed and confirmed |  | To be included in pile transportation fatigue analysis -CVT to complete and issue reports | Closed
13 | Basic Engineering - Loadout Analysis report | HOLD-1 | In this project, the weight of certain primary steel items, as well as secondary and tertiary items such as anodes, boatlanding, internal ring stiffeners, hydrostatic ring stiffeners, diaphragm closure, launch cradle, installation aids, etc., were estimated using historical data. These weights shall be verified and updated with the latest or actual information during the detailed engineering phase. | CventeK | Recalculate and confirm actual weights based on finalized design and updated vendor data during detailed engineering. |  | Once all Rev A1 submitted, this can be closed Analyses completed | Closed
14 | Basic Engineering -Transportation / Tow fatigue Analysis/On-bottom analysis/WCR report | HOLD-1 | In this project, the weight of certain primary steel items, as well as secondary and tertiary items such as anodes, boatlanding, internal ring stiffeners, hydrostatic ring stiffeners, diaphragm closure, launch cradle, installation aids, etc., were estimated using historical data. These weights shall be verified and updated with the latest or actual information during the detailed engineering phase. | CventeK | Recalculate and confirm actual weights based on finalized design and updated vendor data during detailed engineering. |  | Once all Rev A1 submitted, this can be closed Analyses completed | Closed
15 | Basic Engineering -Pirmary Cutting Plan | HOLD-1 | Bill of Materials (BOM) and cutting plan for secondary and tertiary steel items were excluded. Additionally, pile sleeves, internal ring stiffeners, launch cradles, and similar components were estimated using historical data. These items shall be verified and updated with the latest or actual information during the Detailed Engineering phase. | CventeK | Include BOM & Cutting plan for Secondary & Tertiary steel items. BOM for pile sleeves, internal ring stiffeners, launch cradles, and similar components were estimated using historical data. These items to be verified and updated with the latest or actual information. |  | Ongoing Cutting plan to be done by next week for 1st member All Primary Steel and Miscellaneous Steel comfirmed | Closed

## PPR Findings
Project Peer Review - Finding Register
Project: | [9 empty] | PREP Phase: |  |  |  |  | Interview Period:
Findings and Recommendation by Peer Team | [11 empty] | N/A | Responses/Mitigations by Project Team |  |  |  |  | N/A 2 | Review Justification by Peer Team |  |  |  |  | Action during Detail Engineering
Reference | Severity | Discipline | Abbv | Sequence | Document Number | Clause | Readiness Area | Findings | Significance/Consequence | Recommendation | Finding by |  | Corrective Action Plan | References (Dwg or Doc No.) | Action By | Due Date | Target Completion |  | Comments | Justification | Impact Re-rating | Status | Date | Response By CventeK | Open/Closed
STR - 1 | Medium | STR - Structural | STR - | 1 | MM-ZTK-BE-1F-ZWP21-STR-CAL-2011: ZWP21 JACKET IN-PLACE ANALYSIS TH-BUN4-BE-WPG2-STR-WCR-1001 WEIGHT CONTROL REPORT - TOPSIDE | Table 2.1 | Facilities Engineering | Inplace analysis Topside operating weight = 1144.8 MT But WCR BUN4 Topside operating = 1287.2 MT |  | Adjust weight of analysis model to WCR value. |  |  | Topsides operating weight in SACS was rechecked and found that the value used in the analysis model is correct as it is. The value in topsides WCR differs from the Jacket In-place due to seveal reasons. One major reason is the carry down factor for open area live load for Jacket Inplace analysis is 50% less than the Topsides In-place and Topsides WCR. Refer to Attachment 1 for details. | [5 empty] | None. | Project has closed this gap | Low | Closed | 2024-02-04
STR - 2 | Medium | STR - Structural | STR - | 2 | MM-ZTK-BE-1F-ZWP21-STR-CAL-2011: ZWP21 JACKET IN-PLACE ANALYSIS | Pile capacity | Facilities Engineering | (1) Pile penetration length per API RP 2GEO (2011) - Method 3, Fugro-05 shall be 104m. But risk of pile punch throught at bottom layer. (2) The API RP 2GEO (2011) - Method 1, Simplified ICP-05 which give capacity in middle range and could reduce pile penetration length to 117m |  | Past Z1D project use API RP 2GEO (2011) - Method 1, Simplified ICP-05 which can save pile length of 7m-8m. |  |  | For soil layers with predominantly clay, the FUG-05 method may result in lower pile capacity compared to the UWA and ICP methods. Additionally, if we look at the ZWP21 pile capacity chart, the reason for using a 124m depth of penetration is due to the presence of weak clay layers from 108.5m to 140.5m below mudline, underlying a competent sand layer above. To maintain a minimum clearance of 3D diameter and avoid pile punch-through at the sand layer at 108.5m, the pile tip was set below these layers. According to the pile capacity chart, this places the pile tip in the clay layer at 124m penetration. Using the UWA-05 method would result in an approximate 3m saving. However, for design conservatism, it was agreed to use the FUG-05 method. | [5 empty] | The consideration of ICP-05 capacity curve could potential reduce pile length without concern of pile punch throught. Thus, it shall consider in DE phase execution of further optimize pile penetration. This to also reduce risk of handling heavy pile during installation. | Proposed gap closing plan is acceptable, to be addressed in next phase | Medium | Open | 2025-02-04 | This matter will be discussed in the week beginning 8-Jun-26 ZWP21 Pile penetration can be reduced to 119.0m.Once other related analyses, such as Pushover, Seismic ELE and Seismic ALE are completed, this matter canbe closed Results of ZWP21 Pushover, Seismic ELE and ALE Rev B1 confirmed | Closed
STR - 3 | Low | STR - Structural | STR - | 3 | MM-ZTK-BE-1F-ZWP21-STR-CAL-2031/2032 Seismic analysis ELE/ALE P0040546-H2 Rev.0_Draft, Seismic Hazard Assessment | Sect 5.5 | Facilities Engineering | Seismic Hazard Assessment, P0040546-H2 Rev.0, describe liqufaction expect to occur at 2 layers (1) mudline-5.5m (2) 17m-25m But Seismic ELE and ALE consider only one layer from mudline-25m which too conservative. |  | The layer from -5.5m to -17m shall still remain having resistance. |  |  | According to the recommendation in Table 6.1 of the Seismic Hazard Report (#P0040546-H2), t-z will be ignored from 0-25 m, and the recommended liquefied p-y should be applied. However, the governing case for pile penetration length of this jacket is from In-place analysis, not ELE. A sensitivity analysis was performed for Seismic ELE by ignoring the t-z in liquefiable sand layers from mudline to -5.5 m and from -17 to -25 m, but including the t-z capacity in sand and clay layers from -5.5 to -17 m below mudline. The results show a slight improvement when the t-z from -5.5 to 17 m is included. | [5 empty] | None. | Project has closed this gap | Low | Closed | 2025-02-04
STR - 4 | Low | STR - Structural | STR - | 4 | MM-ZTK-1F-ZWP21-STR-CAL-2012, ZWP21 JACKET DYNAMIC ANALYSIS REPORT | Analysis model | Facilities Engineering | Riser size and location in dynamic analysis model are not conform to SOR and inplace analysis. |  | update dynamic analysis and coresponding DAF use for inplace analysis. |  |  | Two pre-installed risers (18" and 10") will be updated in SACS Model and re-run for both dynamic and in-place analysis in Rev C1. | [5 empty] | None. | Project has closed this gap | Low | Closed | 2025-02-04
STR - 5 | Low | STR - Structural | STR - | 5 | MM-ZTK-BE-1F-ZWP21-STR-CAL-2013: ZWP21 JACKET IN-PLACE SPECTRAL FATIGUE ANALYSIS | Result | Facilities Engineering | 1. No combine fatigue with transportation result 2. Double side weld shall be avoid at short member (<3m) and small diameter (eg. 750mm) due to difficult to access the inside weld and perform NDT. |  | avoid double side weld or enlarge diameter. |  |  | 1) Due to the accelerated progress at the beginning of the project, the information was presented separately. However, fatigue damage from transportation and pile driving will be combined and shown in the In-place Fatigue Analysis Report Rev.C1. 2) The double-sided weld of the short element will be rechecked in Fatigue Rev.C1. | [5 empty] | Project team to check and ensure double side weld shall be avoid for short member and small tubular. | Project has clarified and closed this gap | Low | Open | 2025-02-04 | Need input from fabrication team Once shop drawings are presented/Fabricationn yard to check & follow this approach, this matter can be closed. Fabrication yard confirmed, there will ne no double side weld for short members <3m and small members, diameter <750mm. Fabrication yard also confirmed they can do doule side weld on 750mm diameter members | Closed
STR - 6 | Low | STR - Structural | STR - | 6 | MM-ZTK-BE-1F-ZWP21-NVA-CAL-2013, ZWP21 JACKET FLOATATION AND UPENDING ANALYSIS REPORT | A4.2 BASE CASE UPENDING PLOTS | Facilities Engineering | Hook load for upending sequence base case show hook load too low (29.3MT) at event no 29. | Risk of sling slag and slip-off during upending jacket. | hook load shall maintain min app. 100MT at all stage of lifting to ensure lifting sling active at all time. |  |  | The low hook load in the Z1F jacket is due to the removal of two top rubber diaphragms at pile sleeves P5 and P8, which resulted in an accelerated change in the pitch motion of the jacket after flooding A1-L and B1-L. This caused extra buoyancy exceeding the ballast water in A1-L and B1-L. Therefore, the top rubber diaphragm of pile sleeve P8 will not be removed, and the hook height will be raised to 18.0 meters,so the minimum hook load exceeds 100 MT. | [5 empty] | None. | Project has closed this gap | Low | Closed | 2025-02-04
STR - 7 | Medium | STR - Structural | STR - | 7 | MM-ZTK-BE-1F-ZWP21-STR-CAL-2021, ZWP21 PILE HANDLING AND STICK-UP ANALYSIS REPORT | Pile weight | Facilities Engineering | The weight of gripper pile of 608.7MT (143.5m) consider very heave and will cause difficult for offshore operation. 1. The LL from Z1D project with pile weight of 439MT (127.5m) have a lot of damage to pile seafastening while lifting, very risk to damage upending clamp due to weight of pile. ILT also have to maintenance by change the tooth every time after lift each pile. 2. only some ILT provider have capacity above 600MT |  | pile penetration length shall be optimized. |  |  | The pile weight for ZWP21 has been optimized by reducing the wall thickness and penetration, and it has been found to be acceptable. The current gripper pile base weight is 543.1 MT, which is less than 600 MT. | [5 empty] | Pile weight shall also further optimize per item STR-2. | Proposed gap closing plan is acceptable, to be addressed in next phase | Low | Open | 2025-02-04 | Together with STR-02, require further discussion in the week beginning 8-Jun-26 STR-02 can be closed | Closed
STR - 8 | Medium | STR - Structural | STR - | 8 | TH-BUN4-BE-WPG2-PIP-LAY-0006 EQUIPMENT LAYOUT ELEVATION LOOKING NORTH | ELEVATION LOOKING NORTH | Facilities Engineering | The future import pipeline protude below deck on east side without protection while ZMFP laout put this import pipeline at south and within protected area of riser guard. |  | The import pipeline shal relocate to protect area of riser guard. |  |  | Currently, the riser protector frame has been provided on the Platform South prevent vessels from drifting to clash with piping riser below lower deck for the platform which has 2 pre-installed risers. However, the furture import riser, as commented, is part of Budled -Design 2 Topside andwill be rechecked and confirmed its location, along with any additional protection, during the next engineering stage of the EPCI phase. | [5 empty] | Project team to investigate in next phase. | Proposed gap closing plan is acceptable, to be addressed in next phase | Medium | Open | 2025-02-04 | Confirmed with 3D model, the future riser and bend is protected under Topsides structure | Closed
STR - 9 | Medium | STR - Structural | STR - | 9 | MM-ZTK-BE-1F-ZWPX-STR-BOD-0001, Structural BOD | 4.16.5 Seismic Time History Data | Facilities Engineering | Seismic time history ZWP22 are difference from recommend Seismic event data from Seismic Hazard Assessment, P0040546-H2. Liquefaction criteria, P-y curve consider in ELE and ALE analysis are based on seismic event set define in Seismic Hazard Assessment which difference from ZWP22 design event set. |  | Why ZWP22 consider difference seismic set? |  |  | The data for ZWP22 in seismic report no. P0040546-H2 actually belongs to ZWP23. This error originated from a typo in the Rev.A1 report. RINA has corrected this in the latest revision, updating the report to reflect ZWP23. For ZWP22, seismic ground motion and liquefied PSI will be referred to the ZTK-38 location in the seismic hazard report during the Z1E phase. | [5 empty] | None. | Project has closed this gap | Low | Closed | 2025-02-04
OWE - 1 | Medium | OWE - Well & Drilling | OWE - | 1 | SOR Zawtika Project Phase 1F Development | 3.3.1 Opperational rig load | Wells and Drilling | Rig GHTH is under modification. The actual load will be higher than 1,556 MT. The final load on platform will be finalized ASAP. | Limited working load while drilling resulting in increase well cost and more potential for Non-productive time. | Wait for the updated figure from Myanmar Drilling Team and recheck to load. Modify if required. |  |  | The project team is awaiting the updated Rig GHTH weight information. This updated weight will be incorporated into the next engineering stage of the EPCI phase. | [5 empty] | None | Proposed gap closing plan is acceptable, to be addressed before proceeding to the decision gate | Low | Open | 2025-04-02 |  | Open
SAF - 1 | Medium | SAF - Safety | SAF - | 1 | General | General | Facilities Engineering | Risk identification assessment associated with the jacket & piling transportation and installation activities. | overlooking the potential associated risks and its appropriate risk treatments provision leading to the adverse and severe consequences. | Ensure risk assessment associated with the activities such as transportation, load-out, installation of the jacket & piling is carried out during detailed engineering and the findings and recommendations are incorporated. |  |  | The recommendations will be implemented during the next engineering stage of the EPCI phase, when the jacket and pile transportation and installation activities are conducted. | [5 empty] | None. | Proposed gap closing plan is acceptable, to be addressed in next phase | Low | Open | 2025-04-04 |  | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open
#N/A |  |  | #N/A | 0 | [17 empty] | Open